## Sheet1
Date Received | Project # | Project Page Link | PCV/Project Leader | Country | Prog Report | Final Report | Post Proj. Update | Photos | Video | Good Testimonials | Notes
2013-02-26 | W-115 | http://www.worldconnect-us.org/discoverprojects/ejo-hazaza-recycled-glass-bead-project/ | Kim Baskin/Chinelo Nwosu | RW |  | X |  |  |  | X | Final Report missing budget info and only has PCV testimonial (excellent) because replacement PCV is finishing up the chicken IGA; Very good story of a women's coop finding their own way;
2013-02-27 | K-631 | http://www.worldconnect-us.org/discoverprojects/biocafe-costa-ricas-youth-run-coffee-company/ | Eric Mitchell | CR |  | X |  | X |  |  | Fantastic photos for web/social media; Read Final Report to complete the story of this signature project
2013-02-27 | K-691 | not up on website yet | Taylor Westfall | CR |  | X |  |  |  |  | Would be great to congratulate the 18 JumpStart La Cruz graduates on our Facebook page, linking to the Jumpstart page if possible
2013-03-04 | W-119 | http://www.worldconnect-us.org/discoverprojects/womens-group-greenhouse/ | Adriana Lopera | CR | X |  |  | X |  | X | PCV and Beneficiary #2 Testimonials; great photos; Progress Report #2 details the successes and challenges of the first harvest;
2013-03-05 | K-628 | http://www.worldconnect-us.org/discoverprojects/expanding-education-classroom/ | Hannah Engel-Rebitzer | CR |  |  |  | X |  |  | Computers arrived, lab is open for the start of the school year
2013-03-07 | W-117 | http://www.worldconnect-us.org/discoverprojects/empowering-young-girls-informed-decisions-sexual-health/ | Claire Brackmann | CR |  | X |  | X |  |  | There are also two post-project reports that discuss some of the changes in knowledge from the sex-ed classes
2013-03-08 | K-701 | not up on website yet | Koji Ukai | ES |  |  |  | X |  |  | This is the project that the Sage School is fundraising for.
2013-03-08 | K-631 | http://www.worldconnect-us.org/discoverprojects/biocafe-costa-ricas-youth-run-coffee-company/ | Eric Mitchell | CR | X | [5 empty] | PCV submitted the remainder 2013 workplan
2013-03-17 | W-121 | http://www.worldconnect-us.org/discoverprojects/los-callejones-nw-sanitation-project/ | Cynthia Cowgill | DR |  | X |  | X |  |  | 95% of the community's households now have a new latrine.
2013-03-17 | W-122 | http://www.worldconnect-us.org/discoverprojects/los-callejones-nw-sanitation-project/ | Richard Cowgill | DR |  | X |  | X |  |  | 95% of the community's households now have a new latrine.
2013-03-18 | K-701 | not up on website yet | Koji Ukai | ES |  | X |  |  |  |  | The project's primary impact was in building the capacity of local leaders to focus on youth development
2013-03-19 | K-700 | not up on website yet | Ed Piersa | ES | X |  |  | X |  |  | Pretty good birds eye view photos of the court area before construction and mid construction
2013-03-19 | K-678 | http://www.worldconnect-us.org/discoverprojects/salemata-students-fight-stay-school/ | Jessica Frye | SG | X |  |  | X | X |  | See Progress Report #2: construction expected to be completed mid-april, inauguration ceremony set for May 28, 2013. Ministry of Health has recently kicked in an additional $4,000 to cover expenses for construction of bathrooms at the school.
2013-03-19 | W-118 | project is not up on website yet | Emily Deer | CR | X |  |  | X |  |  | 6/12 workshops have been completed. The PCV is being medically evacuated, but there is a strong local leader and project plan, so I've authorized the project to move forward according to plan.
2013-03-20 | K-677 | http://www.worldconnect-us.org/discoverprojects/school-based-fluoride-treatment-oral-health-promotion/ | Jacob Deering and Whitney Goldman | RW |  | X |  |  |  |  | PCVs have both now COSd. PC Rwanda shared the PC Completion Report for the project. I've requested that the Volunteers complete our Final Report form as well.
2013-03-21 | K-669 | http://www.worldconnect-us.org/discoverprojects/growing-healthy-happy-kids/ | Julia Mote |  |  |  | X | X |  |  | PCV checked in about some of the indicators and passed along photos of the school greenhouse;
2013-03-22 | K-706 | http://www.worldconnect-us.org/discoverprojects/bathroom-hygiene-project-girls/ | Molly Green | MA |  | X |  | X |  | X | Fantastic photos of the completed bathrooms and mural; Good Project Leader testimony; Girls attendance has not dropped this year as it has in years past due to this project;
2013-03-23 | K-418 | http://www.worldconnect-us.org/discoverprojects/dress-success/ | James Sykes | CR |  | X | X | X |  |  | Nearly two years from the end of this Kids to Kids project, the scouting program is still going strong in the community; This would be a great Facebook post;
2013-03-24 | W-132 | project is not up on website yet | Joseph Luedecke | PE | X |  |  | X | X |  | Progress Report #4: good testimonial beneficary #3;
2013-03-26 | K-687 | project is not up on website yet | Melinda Lanning | Costa Rica | X |  |  | X |  |  | Quality photos of students clearing land and working in the school garden. Project has a strong network of local agricultural experts supporting its sustainability. First harvest expected in mid-April
2013-03-28 | K-557 | project is not up on website yet | Forest Carter | El Salvador |  | X |  |  |  |  | PCVs cohort was forced to end service early due to political instability in 2011. Tech equipment was put into place but teacher training objectives were not completely met;
2013-03-29 | N/A | project is not up on the website yet | N/A | Haiti | X |  |  | X |  | X | Great photos as always from Nadia, nice beneficiary testimonials as well. Working to confirm the end date for the programming;
2013-04-01 | K-532 | http://www.worldconnect-us.org/discoverprojects/dance-escuela-san-isidro-l-c/ | Brian Polhamus | Costa Rica |  | X |  |  |  |  | Pretty classic K2K project, small grant funded costumes to establish multiple dance groups for kids. Groups are ongoing and community-led, and qualified for nationals this year (2013);
2013-04-01 | K-677 | http://www.worldconnect-us.org/discoverprojects/school-based-fluoride-treatment-oral-health-promotion/ | Jacob Deering and Whitney Goldman | RW |  | X |  | X |  | X | Great photos. Powerful story of one of the nurses at the Kivu Health Center who, as a child, wanted to be a dentist and had the opportunity to go to school, but the civil unrest that led to the genocide prevented him from being able to do so. Unfortunately, data on the reduction in caries amongst students (goal was for 30% reduction) and increase in knowledge on oral health amongst students was not collected due to PCVs' early termination of service. This is a major bummer, particularly the first goal. Beneficiary testimonial is emblematic of why the project is important.
2013-04-02 | K-647 | http://www.worldconnect-us.org/discoverprojects/expanding-science-education/ | Lauren Fitzgerald | KE |  |  | X |  |  |  | The school submitted results data showing the average score for its students on the science section of the national exam (KCSE) from 2008 - 2012. They will submit results from the 2013 exam when they become available, likely in Spring 2014. The hope is of course that the 2013 results will show an increase in the average scores after the first school year with a fully functioning science lab.
2013-04-03 | K-717 | project is not yet up on the website | Sara Gaul | RW | X |  |  | X |  | X | They have opened a small shop and workspace to sell/make the art and have identified a regular buyer (middleman) for markets around Rwanda and potentially internationally. With the support of another local CBO they have applied to be legally reigstered as a coop and have developed a business plan. Great photos and great PCV testimonial.
2013-04-03 | K-699 | project is not yet up on the website | Shelby Fallon | ES | X |  |  | X |  |  | Great community participation thus far. 5,000/10,000 bottles required to build the school have been collected and stuffed with trash;
2013-04-03 | K-712 | project is not yet up on the website | Amanda Slack | PE | X |  |  | X |  | X | The local mayor is directly supporting this project to ensure the students/school has an official market space up and running within two weeks. They have already generated income just from selling outside the school to practice the students' market behavior. Great Project Leader testimonial and fantastic Beneficiary #1 testimonial.
2013-04-04 | K-719 | http://www.worldconnect-us.org/discoverprojects/garden-college-adja-penda-ba/ | Lisa Curcuruto | SG | X |  |  |  |  | X | There is a local NGO called Symbiose which is interested in working with the school's Moringa trees once the garden is up and running. Great Beneficiary #1 testimonial.
2013-04-05 | K-710 | http://www.worldconnect-us.org/discoverprojects/modern-dance-academy-monsefu/ | Kimberly Ayers | PE |  | X |  |  |  | X | This is a big success story. Great before/after photos of the dance studio, a youth led business that generated $488 USD in the first month of operating. The Project Leader is 23 years old and runs the school with only minimial support/traning, in financial record keeping, from the PCV. I've requested that they submit a monthly income statement for the remainder of 2013. Great PCV and PL testimonials.
2013-04-05 | K-674 | http://www.worldconnect-us.org/discoverprojects/camp-lead/ | Hanna Chang | PH |  | X |  | X |  |  | This was a pretty classic, K2K leadership camp project. The original campers carried out two "echo" trainings in fall 2012 for other students at their school.
2013-04-05 | K-485 | http://www.worldconnect-us.org/discoverprojects/jovenes-en-accion/ | Annie Embertson/Kathleen Barrie | PE | X | [5 empty] | We need to edit the grant amount on the project page to $495.37; This project was incomplete when the original PCV (Annie) COSd, so we approved a handover to the replacment PCV (Kathleen). Unfortunately, Kathleen was transferred from the site shortly thereafter for security reasons, so the project wasn't quite completed. The excess funds were recently returned to us via an online donation. I've requested that the original PCV complete the Final Report to the best of her ability.
2013-04-07 | K-447 | http://www.worldconnect-us.org/discoverprojects/creating-future-artists-ereguayquin/ | Michelle Carpenter | ES |  | X |  | X |  | X | Good Testimonial from the beneficiary who was able to parlay participation in the art project to generating income for his family by painting signs for local businesses.
2013-04-08 | K-708 | project is not up on the website yet | Sarah Quinn | MA |  | X |  | X | X | X | PCV shared links to a Youtube news story (http://www.youtube.com/watch?v=g05lR_AGgDE&feature=youtube_gdata_player) and two excellent articles (in English) that were written by the PL and published in anticipation of the event. Article #1: (http://www.moroccoworldnews.com/2013/01/73522/interfaith-dialogue-conference-tameslouht-morocco/). Article #2: (http://moroccotimes.over-blog.com/article-it-s-amazing-what-can-happen-with-just-a-simple-idea-114831694.html). The goal was to have more than 100 youth participants; they ended up with more than 250. The PL (25 years old) for this project was an exceptional leader, see questions #6 and #7 on the first page of the Final Report for a description of his leadership and a good testimonial. There is good advice for planning future projects that are implementing an unprecedented idea revolving around a potentially challenging subject area in question #9 on the first page of the Final Report. The project succeeded in its goal to launch a post-forum inter-faith association, which is already planning its first events. Planning for the 2014 interfaith dialogue is also underway. Great Beneficiary #2 testimonial in the Final Report.
2013-04-09 | N/A | http://www.worldconnect-us.org/discoverprojects/haiti-2012/ | Bertin and Emilie Meance | HT |  | X |  |  |  | X | For the second year there were no reporeted cases of cholera in Lafond. The project succeeded in expanding the nurse's reach to two neighboring communities: Babeau and Dorcet. The're reporting a reduction in cases of cholera in these two communities and the community members following their training of rehydrating the infected persons quickly and taking them to the health center. Marie Renee Michel, the public health nurse, is still looking for steady employment. It's not clear if she is still in the Lafond area or not. There are some decent testimonials.
2013-04-09 | W-120 | http://www.worldconnect-us.org/discoverprojects/bio-sand-water-filters-provide-families-safe-drinking-water/ | Thomas Betts | DR | X |  |  | X |  | X | Progress Report #4: This progress report details the women's group's efforts to identify additional households to receive the bio-sand water filters. It also shares an interesting lesson learned that many families who originally signed onto the project did not truly commit until they saw the first seven, successfuly installed and functioning filters. Excellent Beneficiary #1 testimonial and a good breakdown of the project's impact in the notes section of this particular Progress Report.
2013-04-09 | W-136 | project is not up on the website yet | Lauralee Woods | PE | X |  |  | X |  | X | Progress Report #1: Community Health Worker (CHW) trainings (about diarrhea, Respiratory infections, Parasites, Nutrition, and Early Childhood Stimulation) and house visits (to monitor handwashing stations and prep for new cookstoves) are ongoing, with 51 households participating thus far. Great Beneficiary #1 testimonial from a mother discussing the importance of handwashing in her home.
2013-04-09 | W-128 | http://www.worldconnect-us.org/discoverprojects/young-womens-agricultural-cooperative/ | Bo Ghirardelli | MA | X |  |  | X |  |  | Progress Report #1: The project has thus far purchased 20 goats for the 20 young women participating and has led technical training in the feeding and milking of goats, increasing access to goat milk for related families and slightly increasing income. Income is increasing only slightly because the agreement with the local dairy farm, which was going to purchase the milk regularly, fell through. The women have instead been selling milk locally.
2013-04-10 | K-711 | http://www.worldconnect-us.org/discoverprojects/bonding-entrepreneurial-innovations-environmental-evolution-b-e-l-i-e-v-e/ | Hallie Davis | PE | X |  |  |  |  | X | Upon completing the summer workshops, three separate micro-businesses were started, one youth run and two women-run. The local municipality is starting to see the benefit of the workshops and is stepping up to provide funds to cover transportation/materials costs. Good Beneficiary #1 testimonial, from the youth who started a yogurt selling business after receiving training in dairy production, about now being able to generate income to pay for transportation to school.
2013-04-10 | K-457 | http://www.worldconnect-us.org/discoverprojects/world-30-days/ | Kristin Koo | ES |  | X |  | X |  |  | Another classic K2K project, painting of a world map mural on a school wall. Very nice pictures.
2013-04-11 | K-626 | http://www.worldconnect-us.org/discoverprojects/building-beauty/ | Anna Baker | CR |  | X |  |  |  | X | Great Project Leader testimonial about how the women's group's leadership on the project gave them legitimacy within the community.
2013-04-11 | K-701 | project is not up on the website yet | Koji Ukai | ES |  |  |  | X |  |  | This is the project that the Sage School is fundraising for. Project is complete. PCV submitted two final photos of the mural that was completed.
2013-04-11 | W-134 | project is not up on the website yet | Jessica Onsurez | PE | X |  |  | X |  | X | The project started on 2/13/13 and expects to complete on 7/1/13. The original PL has a serious illness so there is a new PL. I've sent a revised grant agreement for them to sign and return to us. PCV testimonia highlights the collaboration between various local groups to ensure this project is a success.
2013-04-12 | K-648 | http://www.worldconnect-us.org/discoverprojects/completion-high-school-science-laboratory/ | Mark Stratton | KE |  | X |  |  |  |  | The final report is focused on the extremely strong PL, who is also the school's director. The lab was constructed successfully and has been in use since fall 2012. I've asked the PCV to arrange for the PL to submit summary scores for the students performance on the KCSE in pre-lab years, which we can compare to their performance in the current school year.
2013-04-15 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X | [5 empty] | PCV submitted his fourth monthly indicator report. It's showing a trend of households dropping out of the project, so I've inquired for more details.
2013-04-15 | W-128 | http://www.worldconnect-us.org/discoverprojects/young-womens-agricultural-cooperative/ | Bo Ghirardelli | MA | X | [5 empty] | Progress report details why the agreement with the dairy farm fell through. Basically, the goats aren't yet producing enough milk for the farm to consider it cost-effective to pick up the milk. The women are having no trouble selling locally in the meantime, and hope to reengage the dairy farm once production increases.
2013-04-17 | W-125 | http://www.worldconnect-us.org/discoverprojects/singorwet-dispensary-maternity-ward-development/ | Andrea Flynn-Schneider | KE |  | X |  |  |  | X | This is the final report for the initial project at the Singorwet Dispensary, focused on the transfer of MCH equipment to the clinic. Fantastic testimonials. The PCV has been forced to interrupt her service for undisclosed personal reasons, but has left the project in the capable hands of the Project Leader. I'm following up with her to ensure we have a strong communication plan (between the PCV, PL and the PC office) in place to ensure the completion of the construction and to ensure that we have regular reporting of data from the clinic to show the project's impact.
2013-04-18 | K-251 | http://www.worldconnect-us.org/discoverprojects/children-jalacte/ | Sam Serpente | BZ |  | X |  |  |  |  | Not much detail in the final report, other than to state that they used their grant to buy soccer uniforms/equipment for the school and school supplies for the classrooms. The purchases were 100% decided by the students/teachers via a schoolwide vote. I've requested pictures from the project.
2013-04-18 | K-634 | http://www.worldconnect-us.org/discoverprojects/basketball-league-kids/ | Joshua Austin Slaughter | CR |  | X |  |  |  |  | PCV notes on Page 1, Question #10 of the final report that the delay in us disbursing the grant forced them to have to wait an extra two months to implement the project, after the rainy season. Otherwise, the project was an overall success, leading to the establishmen of a successful basketball league with locally trained coaches and four teams. I've requested photos and more thorough update on the sustainability of the league.
2013-04-21 | K-704 | http://www.worldconnect-us.org/discoverprojects/community-library-resource-room-ait-ayach/ | Joseph Donahue | MA | X | [5 empty] | We are going to be withdrawing this project because the community is waiting on approval to move and sell items in the garage that is to be converted into a community library and resource room and, while the PCV is reporting strong community support of the project, he is closing his service this month. The PC Morocco office is recommending the withdrawal and reimbursement based on their not being another PCV nearby to take over the project and ensure that it is completed successfully. None of the grant funds have been spent to date, so we can expect a full $5,000 reimbursement.
2013-04-23 | K-714 | http://www.worldconnect-us.org/discoverprojects/linking-tradition-21st-century-literacy-skills/ | Amy DeCola | PH |  |  |  | X | X |  | PCV submitted many photos of the completed library and Bahay Kubo, and one low res video of the students playing flutes at the grand opening.
2013-04-23 | K-634 | http://www.worldconnect-us.org/discoverprojects/basketball-league-kids/ | Joshua Austin Slaughter | CR |  |  | X | X |  |  | Just a quick update to share photos and let us know that the four local coaches who were trained as part of our project will be in charge of the next season, scheduled to start in December 2013. They are expanding the age groups of kids involved as well.
2013-04-25 | K-721 | http://www.worldconnect-us.org/discoverprojects/koldas-talent/ | Jordan Levinson | SG | X | [5 empty] | They have held 4/6 planned contests/shows thus far with great success. Interestingly, another local youth group unaffiliated with this project started its own weekly dance/music competition at the city's youth center. Also, local professional musicians have gotten greatly involved, volunteering to perform at the events and contributing to the success of the shows. This has established the sustainability of the project idea and activities, even if in an unanticipated way. Our project leaders are now proposing to shift their focus (from ongoing performances) and their remaining funds to organizing one large, regional music festival and final competition, scheduled for mid-September. I've approved a budget ammendment for them to do so. The narrative here is "a small grant from World Connect ignites the artistic community in Kolda."
2013-04-25 | K-708 | http://www.worldconnect-us.org/discoverprojects/common-threads-interfaith-forum/ | Sarah Quinn | MA |  |  | X |  |  |  | PCV confirmed the name of the interfaith association (The Association of Interfaith Friendship) and that they will be leading the 2013 forum alongside the CBO (Tameslouht's Association Al Anwar).
2013-04-26 | K-687 | http://www.worldconnect-us.org/discoverprojects/sustainable-organic-educational-gardening-project/ | Melinda Lanning | CR |  | X |  | X | X |  | This is a comprehensive, successful schoolyard garden project, including gardening, composting, nutrition workshops, incorporating the harvest into the school lunches to increase consumption of healthy foods and decrease costs. Project leaders documented strong leadership of "non-traditional student leaders," or students who struggle in the traditional classroom settings and are deemed at-risk, but excelled in the "open-air garden environment." Most of these non-traditional student leaders come from the poorest households and were able to parlay their experience working in agriculture to support their families to the school gardening project. Also, many students are regularly giving up their recreation time before/after school to assist the project. Page 1, Question #7 has a great profile of a 13 year old at-risk student who took a leadership role in the project. The first harvest was performed on 4/8/2013 and included cilantro and mustard, both of which were incorporated into school lunches.
2013-04-26 | W-134 | http://www.worldconnect-us.org/discoverprojects/community-hydroponic-garden/ | Jessica Onsurez | PE |  |  |  | X | X | X | PCV submitted photos, a video and translations for the testimonials in the first progress report. I added the translations to the progress report. The video is pretty shaky and needs editing/translating, but it shows a community agr. workshop being done on site, led by the PCV.
2013-05-06 | K-714 | http://www.worldconnect-us.org/discoverprojects/linking-tradition-21st-century-literacy-skills/ | Amy DeCola | PH |  | X |  |  |  | X | 539 books checked out from the library in approximately 45 day period (2/1 - 3/15). Project Leader was very strong and speaks excellent English. Tons of great pictures in the shared file. Great discussion in the capacity assessment about the way this project increased the capacity of local leaders to create sustainable linkages in their community. Fantastic data on the increases in reading levels pre/post project.
2013-05-07 | W-119 | http://www.worldconnect-us.org/discoverprojects/womens-group-greenhouse/ | Adriana Lopera | CR |  | X |  | X |  | X | The group is receiving continuing support from the Ministry of Agriculture. The women are beggining their second harvest this month (May) to coincide with the start of the rainy season, to maximize available water. The first harvest, which had a number of problems that are detailed in an earlier progress report, still produced 12 USD and funded the seeds purchase for the second harvest. The PCV is closing her service this week (May 10, 2013), so I'm going to be establishing a longer term contact associated with the women's group who can keep us updated on the impact of the second harvest. The post-project CBO capacity assessment has good detail on how the women's group has increased their capacity as an organization through this project.
2013-05-13 | K-653 | http://www.worldconnect-us.org/discoverprojects/mothers-preschool/ | Jenifer McEnery | MA |  | X |  | X |  | X | This project is credited with fundamentally altering people's perceptions about community associations and community development in Touama. It's also interesting that (mid-project) the CBO elected new members and leadership who were not involved in the design of the project, yet saw it through to completion. This change explains why there is such a large reported decrease in organizational capacity from the pre-project to the post-project phase (from 16 to 6 on our scale). Great story about how mothers and the presechool teacher are now socializing over tea as a result of this project, and the cultural importance of that act. I'm documenting this as behavior change, even though it's not formally measured. Also, interesting how the school discovered it owned more land than it had previously thought and was thus able to expand the schoolyard play area. Sidi Ahmed Toumi is now the only presechool in Touama that has its own storybook library/reading station, sports field, zoo, health station and designated play area. It's also the only preschool to offer workshops for mothers. The goal to create a mother's committee was shelved because a) most of the mothers could not read, and b) the mothers begain participating in a separate literacy and crafts workshop. Instead, the school is planning to continue voluntary workshops for mothers focused on nutritional cooking, income generation and health. The project also resulted in two new bathrooms and two renovated bathrooms at the school.
2013-05-13 | K-653 | http://www.worldconnect-us.org/discoverprojects/mothers-preschool/ | Jenifer McEnery | MA |  |  | X | X |  |  | Post project report describes why there was a decrease in organizational capacity during the project, due to the organization electing completely new membership and leadership mid-project. Fantastic photos. PCV has extended and plans to apply for another grant in September to extend the impact/sustainability of the Mothers' Preschool.
2013-05-13 | K-648 | http://www.worldconnect-us.org/discoverprojects/completion-high-school-science-laboratory/ | Mark Stratton | KE |  |  | X |  |  |  | PCV was able to collect the aggregate KCSE scores for the school from 2010-2012, showing an increase in chemistry scores in 2012, the first year the students had access to the lab.
2013-05-14 | W-127 | http://www.worldconnect-us.org/discoverprojects/sex-fish-nyamware/ | Samantha Slater | KE |  | X |  |  |  |  | The women that received boats are making between 12,000 and 15,000 Kenya Shillings per month (144-180 USD), which is 3-4 times the minimum wage in Kenya. As a result of the business trainings in the project, there are now two community savings groups, one for the women and one for the men. Collecting more stories/data per Carmen's feedback.
2013-05-15 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X | [5 empty] | Project submitted its May indicators report, noting the beginning of handwashing workshops at the six participating schools, the completion of family workshops focused on balanced diets, successful families, family communication and well-being. Home visits confirm that the majority of the 27 participating families have now prepared their latrine pits. Changing Project Leader from Leily Mendoza, who no longer works at the Health Center, to Felicia Florida Latorre. I've sent a revised Grant Agreement.
2013-05-15 | K-700 | http://www.worldconnect-us.org/discoverprojects/bringing-fun-jutiapa/ | Edward Piersa | ES |  | X |  |  |  |  | This is a pretty straightforward court construction, increase in access to sports project. The photos of the completed court should be integrated into the slideshow on the project page.
2013-05-17 | W-129 | http://www.worldconnect-us.org/discoverprojects/crochet-embroidery-training-craftswomen-el-makhzen/ | Alexandra Naegele | MA |  | X |  | X |  |  | Interesting story of how severe drought in the region forced many older women to travel far away to collect food for their livestock making them unavailable to participate in the trainings, which were instead filled by younger women and girls. Some of the younger girls have been successful in selling their work to local community members and in nearby villages. I've inquired about about the status of their original plan to sell to hotels/guesthouses in the region. Parts of Page 2/3 of the Final Report were incomplete. I've asked the PCV to revise and resubmit.
2013-05-20 | W-106 | http://www.worldconnect-us.org/discoverprojects/azalagh-womens-center/ | Leigh Anne Schmidt | MA |  | X |  |  |  | X | After some delays due to legal paper work for the land, the center is now complete and 670 women have participated in literacy, Arabic, French, English, cooking and sewing classes to date. The PCV COS'd in May 2013 and has left the center in the hands of Rashida Abaough, a local pre-school teacher. The president of the center (who?) will be meeting with a regional representative for women's associations to learn about opportunities and resources available to women in Morocco.
2013-05-20 | W-135 | http://www.worldconnect-us.org/discoverprojects/la-cocina-sana/ | Sue Song | PE | X |  |  | X |  |  | PCVs camera was stolen so she has limited photos. 12/24 workshops have now been completed. There was some difficulty initially with attendance, but there are now more than 15 women who attend the nutrition classes regularly.
2013-05-20 | W-118 | http://www.worldconnect-us.org/discoverprojects/madres-emprendedoras-hacia-futuro-prometedor-enterprising-mothers-promising-future/ | Emily Deer | CR |  | X |  |  |  | X | They measured a 33% increase in applied knowledge related to vulnerabilities and benefits in small business administration, price-setting and basic accounting practices. EAch woman perfomred a SWAT analysis on her own small business idea and developed a business plan, with oversight by PCV and PL. Question #6 and #7 feature a 19 year old participant who developed a strong business plan for a bakery, but would need seed funding to make it happen. We should consider collecting the business plan and a budget and seed funding the project. In fact, we should consider seed funding a number of these business via a second grant. Interesting health education occured here as well. For example, each participant identified a preferred method of birth control after participating in a workshop to learn about the differing methods, how to use/access them, and to dispel common myths. Great PL testimonial.
2013-05-21 | K-645 | http://www.worldconnect-us.org/discoverprojects/project-zenith-2/ | Daniel Nierengarten | EC |  | X |  |  |  | X | The project features in large part eight students from the Deaf Institute of Chimborazo (ISCH), who are the "linguistic models" in the videos. The end result is a curriculum to go along with two DVDs, each DVD containing four stories. The sign language consultants were so excited by the project that they refused compensation. PCV submitted a list of the 49 institutions, located in all but three of Ecuador's provinces, that have received the curriculum/DVDs to date (5/21/13). 100 copies were distributed to these 49 institutions. I've requested that the ISCH notify us any time the curriculum is requested/distributed, and I've also asked the PCV about the possibility of us making the curriculum available to project leaders working with deaf and hard of hearing populations in other spanish-speaking countries.
2013-05-26 | CDF | http://www.worldconnect-us.org/discoverprojects/singorwet-dispensary-maternity-ward-development/ | Andrea Flynn-Schneider | KE |  |  |  | X |  |  | The Project Leader, Samwel Koech, sent us four photos of the nearly completed construction of the materntity ward.
2013-05-26 | W-082 | Project is not up on website yet | Grace Buezis | MA |  | X |  |  |  |  | This project was a PCV handoff, completed by Grace Buezis over the course of the last two years. It revolved around a series of trainings for women focused on literacy, maternal health issues, first aid, growing and harvesting saffron as an IGA, and two camps for children focused on health (toothbrushing, handwashing, littering, etc.) and soccer.
2013-05-28 | 13-019 | http://www.worldconnect-us.org/discoverprojects/renovation-mawingu-nursery-women-center/ | Shailah Bevan | KE | X | [5 empty] | Progress report details the land tenure issue that the project is facing, along with the plan for moving forward.
2013-05-31 | W-127 | http://www.worldconnect-us.org/discoverprojects/sex-fish-nyamware/ | Samantha Slater | KE |  |  | X |  |  | X | Report details the Village Savings and Loan Association, provides fantastic testimonials from the three women who own the boats we funded as well as the men who are involved in the project, clarifies the distinction between our project and the original pilot project, and reports on the increases in income for the three women.
2013-06-02 | W-120 | http://www.worldconnect-us.org/discoverprojects/bio-sand-water-filters-provide-families-safe-drinking-water/ | Thomas Betts | DR | X |  |  | X |  |  | They installed 7 more bio-sand water filters on 5/11/13, bringing total to date installed at 13. They're expecting to expand soon to a neighboring community in partnership with the community's women's group. 82,225 DOP remaining in grant funds, approximately 2000 DOP of grant funds required per filter installation = approximately 41 more filters that can be installed.
2013-06-09 | W-136 | http://www.worldconnect-us.org/discoverprojects/parents-healthy-tomorrow/ | Lauralee Woods | PE |  |  |  | X | X |  | Good video of kids delivering a handwashing presentation in Spanish.
2013-06-11 | 13-003 | http://www.worldconnect-us.org/discoverprojects/rebuilding-environment/ | Nicole Phillips | DR | X |  |  |  |  | X | They have completed two community-wide trash cleanups to date and four educational workshops. They've also received 300 trees, which are being cared for by the youth group and will be planted in the next month. Also, some households have started using trash bags and storing trash for weekly pickups. Project has developed a strong partnership with the Ministry of Environment, which is donating the majority of trees for the project. They're going to be submitting a revised budget to account for the unexpected donation of trees.
2013-06-13 | K-645 | http://www.worldconnect-us.org/discoverprojects/project-zenith-2/ | Daniel Nierengarten | EC |  |  | X | X |  |  | PCV shared the plan for evaluating the curriculum's impact in the 2013-2014 school year at the ISCH, and also noted that the curriculum uses Ecuadoran sign language, therefore would not be transferable to other Spanish-speaking countries. I've inquired to find out a good time to check back in with the project to collect data/results from the evaluation at the ISCH.
2013-06-14 | K-357 | http://www.worldconnect-us.org/discoverprojects/ecological-youth-house/ | Michelle Jolie Wieland | MA |  | X |  |  |  | X | Long overdue Final Report. The project resulted in the following projects being completed by/for youth at the Dar Chebab (youth house): creating a compost pile, planting fruit trees, evergreen trees and flowers, adding books and posters concerning environmental awareness and protection to the library, building birdhouses and a fountain, environmental education workshops. Great Beneficiary #1 and #2 Testimonials.
2013-06-18 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X | [5 empty] | PCV submitted his June Indicators Report (covering 5/6-6/18). The main noteworthy activity in this report is that the concrete toilet basins arrived and were distributed to 24/27 participating families and one school (PRONOEI Ishpingo). The three remaining families still need to dig their latrine pits before receiving their concrete toilet basins. Also, the District Municipality of Leymebamba financed the purchase of additional needed materials. 6/6 participating schools now have restroom latrine facilities, with only the Ishpingo school needing to complete improvements to its latrine. There was a slight decrease in the % of school days where students are attending school with the necessary handwashing materials (soap and towel), from 84.18% to 82.65%, but the number is still well over the goal of 70%.
2013-06-21 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X |  |  | X |  | X | PCV submitted his second official Progress Report. 26/27 families have received their latrine building materials. 12/27 have improved, functioning latrines, while 7/27 are in the process of construction. They're seeing an across the board postive improvement in hygiene indicators for the 27 families from the pre-project measures (see various indicators reports). Overall, there is just fantastic data being collected for this project relative to most of our projects. 7/8 participating teachers report giving at least one hygiene lesson with students each week. Great detail in question #2 on the strong support of the District Municipality of Leymebamba. Project expects to complete in October 2013. Great Beneficiary #1 testimonial, 7 year old kid talking about handwashing. Great Beneficiary #4 testimonial, talking about the latrine's long-lasting impact.
2013-06-23 | 13-001 | project is not up on the website yet | Sean DeBuck | DR |  | X |  | X |  | X | 22 people graduated the documenatation promotor course, each assisting at least one individual through the documentation process. The project collaborated with a local NGO, CEDESO, which is interested in possibly taking the program over in the future, and is already covering transportation costs for monthly meetings.They completed a census to discover the number of undocumented children within each participating community as part of a collaboration with CEDESO. We've requested summary census data. Facebook page is called Declaro Mis Derechos.
2013-06-27 | 13-015 | http://www.worldconnect-us.org/discoverprojects/hearth-healthier-home-smoke-reducing-cook-stoves-culinary-classes/ | Stanley Greidinger | DR |  |  |  | X |  |  | We received one photo of the stove mason installing the first stove.
2013-06-30 | 13-038 | http://www.worldconnect-us.org/discoverprojects/leaders-development/ | Jennifer Conner | SG | X | [5 empty] | PCV has decided to terminate her service, but has put in place a transfer of responsibility for the project to another PCV, Janet Smith. I've requested the official TOR form from PC and have sent them a revised grant agreement. They have identified 7/10 placements for interns and are collecting letters of support now. They invited 170 applications and received 130 from interested students. The internship program wil take place in September 2013, before the start of school in October.
2013-07-01 | 13-007 | http://www.worldconnect-us.org/discoverprojects/brasilia-hair-stylists/ | Farid Mozafari | CR | [6 empty] | See Supplemental Application Document #2 in the Applications folder; we received the Project Leader's personal testimonial. We should be receiving a video testimonial shortly as well.
2013-07-01 | 13-003 | http://www.worldconnect-us.org/discoverprojects/rebuilding-environment/ | Nicole Phillips | DR | [6 empty] | We received and authorized the revised budget and finance report, you can find the document in the "Funding" folder.
2013-07-01 | K-607 | http://www.worldconnect-us.org/discoverprojects/planting-future-jangass-sustainable-agriculture-educational-center/ | John Meyer | PE |  |  | X |  |  |  | PCV submitted a brief report stating that the garden at the primary school has been taken over by a local professor, it continues to produce vegetables for sale, and the most recent sale netted 1500 soles (576 USD), which is being used to support families in need. I've requested the PCV develop a basic, income-generated summary report to be submitted to us monthly for the remainder of 2013.
2013-07-02 | K-712 | http://www.worldconnect-us.org/discoverprojects/improving-quality-life-productive/ | Amanda Slack | PE |  | X |  | X |  | X | Good PCV testimonial about working with WC in Question #11 on page 1 of the Final Report. In June 2013, they had the grand opening of the juice store in the central market. The shop is open every day from 7AM to 1PM and is run by the kids and their parents on a rotating schedule, as well as one local woman who is paid 10 soles (3.5 USD) to help out every day. They save 30% of the income generated in a bank account for the business and distribute the other 70% to those who work the shop. There is a replacement PCV being placed in Guadalupe in August 2013, so we could continue to work with this group if we so choose. Families are buying medicines and daily needs with their increased income. Changes in behavior reported are anecdotal. I've requested the PCV develop a basic, income-generated summary report to be submitted to us monthly for the remainder of 2013.
2013-07-05 | W-105 | http://www.worldconnect-us.org/discoverprojects/ouled-ali-youssef-medical-caravan-workshop/ | Jonathan Pleban | MA |  |  | X |  |  |  | PCV submitted an unsolicited post-project report to inform us that since the project completed, more than one year ago, a doctor has been placed in Ouled Ali and construction has begun on a health clinic in Timitar, one of the sites of the medical caravan. Both are in direct response to the success of the medical caravan. This is a major success for our project, as the intent of the project was to use the caravan data to demonstrate the need for increased access to medical care in the region to the Ministry of Health. We should update the project page and post about this on social media.
2013-07-06 | 13-001 | project is not up on the website yet | Sean DeBuck | DR |  |  | X |  |  |  | Census data on undocmented population is not yet processed, but PCV surveys indicate 20-35% undocumented rates in the surveyed communities. 30 individuals were guided through the documentation process during this project, 15 of whom are on their way to gaining documentation.
2013-07-07 | 13-029 | http://www.worldconnect-us.org/discoverprojects/souss-girls-soccer-camp/ | John DeBellis | MA | X |  |  | X |  | X | Progress report was submitted mid-camp. 48 girls were able to attend the camp and they'd completed all of the health workshops as of 7/4/13. The girls are in awe of the women's pro soccer team that is acting as coaches for the camp. There have been some administrative/logistics problems, particularly in that their volunteer camp director backed out, but the PCV and PL have worked through all problems and it hasn't impacted the girls in any way. Great testimonials, I'm trying to track down the videos now.
2013-07-09 | 13-007 | http://www.worldconnect-us.org/discoverprojects/brasilia-hair-stylists/ | Farid Mozafari | CR |  |  |  |  | X |  | Project Leader video testimonial is in the photo folder.
2013-07-09 | W-115 | http://www.worldconnect-us.org/discoverprojects/ejo-hazaza-recycled-glass-bead-project/ | Kim Baskin | RW |  |  | X |  |  |  | The former replacement PCV, Chinelo Nwosi, was medically evacuated. The new site replacement PCV is Suzanne Enoch, but the original PCV (Kim Baskin) should remain the primary point of contact. Kim is still in regular contact with Nonci, the Ejo Hazaza manager. They were not able to meet their goal of selling eggs by June 2013 because there was a problem with the land where they intended to build their chiken coop. In sum, the health center, which originally agreed to donate land for the chicken coop, backed out, as there was a sentiment that the women were making too much progress and didn't need handouts. The women are instead working to purchase their own plot of land in the cooperative's name, using funds raised from their various jewelry/beading activities. In addition to raising chickens, they plan to build a small house for their glass bead IGA.
2013-07-14 | K-678 | http://www.worldconnect-us.org/discoverprojects/salemata-students-fight-stay-school/ | Jessica Frye | SG |  | X |  | X | X | X | At a total cost of $53,000, this is the largest completed PCPP project ever. We contributed $5,000 for the construction of one of the high school's classrooms. It will serve more than 25 villages and 750 students per year. There is a great video on youtube (http://www.youtube.com/watch?v=07VBlJfbAtM). As one might expect with such a large project, there were a lot of locoal political problems, detailed in Question #3 on the Final Report.
2013-07-16 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X | [5 empty] | PCV submitted his July Indicators Report (covering 6/19-7/15). 27/27 families now have their latrine materials, and they project that the majority of the 27 families should have their latrines by the end of July. Specifically, 12/27 families have improved, functioning latrines, while 12/27 are in the process of construction.
2013-07-16 | K-625 | http://www.worldconnect-us.org/discoverprojects/bringing-google-guaitil/ | Jennifer Amores | CR |  | X |  | X |  |  | The computer lab is up and running and we have great pictures. It's not quite functioning at its designed capacity in two ways: 1) the teachers are not using it for teaching directly; rather, they're using it for completing their paperwork and for printing materials for their classes; 2) the school board decided it wasn't feasible to open the lab to community members twice per week, as originally envisaged; instead, they're only opening it up to community members who sign up to take classes led by the PCV. 80 students and 36 community members have completed at least one 30 hour computer course to date.
2013-07-18 | W-134 | http://www.worldconnect-us.org/discoverprojects/community-hydroponic-garden/ | Jessica Onsurez | PE |  | X |  |  |  | X | The project resulted in education and skill building for thirty community members related to community and home gardening. They adapted their goal mid-project from one single, community garden and hydroponic system to several smaller gardens in separate locations. This decision was made because of time and location constraints amongst the participants. Great Beneficiary #1 Testimonial. I'm inquiring for more details/specifics on the # and type of gardens (community v. household) and for more photos.
2013-07-18 | 13-029 | http://www.worldconnect-us.org/discoverprojects/souss-girls-soccer-camp/ | John DeBellis | MA |  |  |  | X | X |  | PCV shared more photos and videos via DropBox. Good PCV video testimonial, and there is a transcript to go with the three beneficiary videos. The video entitled "World Connect Mid 1" is fantastic. It has some technical glitches in the first 15 seconds, but they almost make it better as the camera comes into focus on the girl. I think it should go up on our website and social media just as it is.
2013-07-22 | K-651 | http://www.worldconnect-us.org/discoverprojects/project-green-clean-zween-beautiful/ | Marc Gimbel | MA |  | X |  |  |  | X | The bathroom was successfully constructed, and school gardens were setup in all three of the primary schools in Talmest, as opposed to just the original one school. Reports that the community is very impressed with the CBO's (women's association) ability to implement such a successful project. They have added new members and are now working on a school wall project at Sidi Abdel Jalil. There is a good story of increased CBO capacity in this project. The school composting componenet has led to a prospective town composting project. Good PCV and PL testimonials.
2013-07-22 | 13-026 | http://www.worldconnect-us.org/discoverprojects/kalou-educational-compound/ | Brett Werkheiser | KE |  |  |  | X |  |  | PCV submitted three photos of the greenhouse excavation in progress.
2013-07-25 | 13-019 | http://www.worldconnect-us.org/discoverprojects/renovation-mawingu-nursery-women-center/ | Shailah Bevan | KE | [6 empty] | The PCV still has not received her funding, as her revised budget is still under review by Peace Corps; however, she submitted a hand drawn site map of the Mawingu property and a blueprint for the building that will be constructed. Also, we should probably change the title of this project, as it's no longer a renovation project, but a new construction project.
2013-07-30 | K-651 | http://www.worldconnect-us.org/discoverprojects/project-green-clean-zween-beautiful/ | Marc Gimbel | MA |  |  | X |  |  |  | PCV sent along names of the three schools that implemented school gardens, and detailed some of the successes/challenges. He expects one school in particular, the one that was originally the focus of the project, to keep a sustainable schoolyard garden.
2013-08-05 | K-717 | http://www.worldconnect-us.org/discoverprojects/imigongo-art-co-op/ | Sara Gaul | RW | [6 empty] | PCV submitted copies of the documents showing the Imigongo Coop as officially registered with the Rwandan goverment.
2013-08-06 | K-706 | http://www.worldconnect-us.org/discoverprojects/bathroom-hygiene-project-girls/ | Molly Green | MA |  |  | X |  |  |  | PCV passed along the attendance report for the 2012-2013 school year that shows no girls dropped out of school.
2013-08-09 | K-717 | http://www.worldconnect-us.org/discoverprojects/imigongo-art-co-op/ | Sara Gaul | RW |  |  | X |  |  |  | PCV submitted a paragraph explaining the benefits of getting the cooperative officially registered with the Rwandan government.
2013-08-11 | 13-020 | http://www.worldconnect-us.org/discoverprojects/drilling-water-kithyululu-community/ | Julia Cheng | KE | X | [5 empty] | The Hydrogeological survey was completed and drilling was scheduled to begin on August 12. They have run into an unanticipated increase in costs, related to the need to drill 50+ meters more than expected. The project, which we granted at $8,411.76, will require approximately $8,000 in additional funding. The local community is exploring how to fund these additional costs, and the drilling company has agreed to a long term payment plan. It's clear that an important lesson for us to consider with boreholes projects moving forward is to have the pre-project scientific surveys and assessments completed before agreeing to move forward. In this particular case, we noted this in our review process as a risk, but elected to move forward nonetheless.
2013-08-14 | K-717 | http://www.worldconnect-us.org/discoverprojects/imigongo-art-co-op/ | Sara Gaul | RW |  | X |  | X | X | X | Really nice pics of young people doing Imigongo. Cooperative members have increased their income from 40,000 RWF (60 USD) per month to 50,000 RWF (75 USD) per month. They are selling in a number of markets. There is a company called Azizi Life (http://azizilife.com/), based in Gitarama, that continues to buy from the cooperative on a monthly basis, and they have a couple of loyal buyers in different Kigali markets (Mu Mujyi, Kaparachi, Atrake). PCV is teaching English lessons to facilitate their continued pursuit of international markets. There is a strong local leader at the center of the project, profiled in the final report, Zacharie Ngenzi. He is also the official Project Leader on our grant agreement. Interesting to learn that the coop had actually existed for 13 years before the PCV arrived in site. What World Connect's support permitted was an opportunity to formalize their work (open a bank account, open a local shop, etc), get officially registered, learn English and expand their market. This is a fantastic success story. The PCV's COS is November 7, 2013, but the site has requested a replacement PCV. They will know if the request was approved in October. I think we should at least explore the idea of providing a second round of funding to grow the cooperative further.
2013-08-15 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X | [5 empty] | August Indicators Report (7/16-8/15): 17/27 improved household latrines are now complete, 9/27 are in process of construction, 1/27 has materials but has not yet begun construction. Some interesting data points based on home visit #2: 27/27 families are now separating organic and inorganic trash; 18/27 families are treating their water; 19/27 households have functional handwashing facilities, 14 of which are at least 10 paces from the bathroom/latrine.
2013-08-16 | K-721 | http://www.worldconnect-us.org/discoverprojects/koldas-talent/ | Jordan Levinson | SG |  |  |  | X |  |  | Decent quality photos.
2013-08-16 | 13-029 | http://www.worldconnect-us.org/discoverprojects/souss-girls-soccer-camp/ | John DeBellis | MA |  | X |  |  |  | X | The camp was a great success, particularly in peaking the interest of the professional women's soccer team, who wants to run the camp next year with its players as both coaches and counselors. 94.71% of girls know much more about soccer than they did before the camp; 92.98% of girls are very much or much more likely to participate in their town's soccer team and trainings; 100% of girls found the soccer coaching good or excellent; 87% rated the health and nurition workshop good or excellent; 85% rated the HIV/AIDS workshop good or excellent. There was some infighting within the CBO, but the PL, who is President of the CBO, stepped up in a big way to ensure the project's success. The overarching success story here is the connection between the pro women's soccer team and these girls and their towns' soccer teams. This is an example of how our projects can spark collaboration and local leadership.
2013-08-24 | 13-004 | Project is not up on website yet | Rodolfo Torres | DR |  | X |  | X |  | X | In sum, there is a spring box that they installed to protect a natural water source. They installed a pipe that runs nearly 2 km to a water tank that was built in the community. The plan is for each of the 30 homes in the community to connect directly to the tank. The story of this project is, in addition to increased water access, the community's water management. Six individuals were elected to a water committee, where they will govern access and care for the system, and collect dues to pay a local plumber to provide ongoing maintenance. The original plan called for five communal tap stands that would receive water from a tank, which received it's water from an elevated water source (hence the name of the project, "gravity forced water system"); however, the elevated source was not providing adequate volume of water, so the plan was changed. The water source that was eventually identified is actually lower in elevation than the community, making the name of the project a bit of a misnomer. To date, 10/30 home connections have been completed. The other twenty households are either in the process of digging their trenches or have not yet come up with their financial contribution. PCV had to ET because his mother is sick back home. I've inquired as to who in the community can report back on the completion of the final 20 connections.
2013-08-24 | 13-003 | http://www.worldconnect-us.org/discoverprojects/rebuilding-environment/ | Nicole Phillips | DR | X |  |  | X |  |  | At this point, they've completed 10 workshops, each with more than 30 youth participants. Youth who missed no more than three of the workshops were taken on field trips to the national botanical gardens and aquarium in Santo Domingo. They've planted 50 of the 300 trees they were donated, and sent four truckloads of trash to the local trash dump with the support of the local governor. Families of youth have been collecting trash using bags and waiting for trash pickups throughout the course of the project, demonstrating behavior change at least in the short term. I love the story of how the community's motoconchistas (motorcycle taxis) are providing security for the trees while they wait for clients. Also an intersting story of how a professional from the provincial environmental ministry drove by the community, saw the projects, stopped and offered more trees, which they will be collecting when they finish planting their first 300 trees. There is a flicker of interest in replicating the project coming from youth in neighboring bateyes. The Batey 5 group is going to be inviting youth from other communities to their next workdays (trash clean ups, tree plantings, workshops, etc.).
2013-08-27 | W-120 | http://www.worldconnect-us.org/discoverprojects/bio-sand-water-filters-provide-families-safe-drinking-water/ | Thomas Betts | DR | X | [5 empty] | Update was via a phone call in preparation for our site visit to the Loma Atravesada on 9/8. Thomas informed me that there are 15 families ready (with their community contribution and having completed the filter workshops) to receive filters in the neighboring community of El Manatial. The women's group who is leading the project in Loma Atravesada actually approached the community of El Manatial initially about the project and was able to secure the commitment and leadership of a local woman, who has organized everything in El Manatial. They are tentatively expecting to do the installation on 9/7, the day before our site visit. Whether they do or not, we will be visiting the community, meeting with families and the local leader.
2013-09-02 | 13-040 | http://www.worldconnect-us.org/discoverprojects/gueoul-sport/ | Marsha Hedrick | SG | X | [5 empty] | PCV submitted an unofficial progress report while requesting use of our logo. The grand opening of the dojo will be this weekend (9/7-9/9). Most of the equipment has been procured, there is strong community support, and the doctor from the local health center has already referred four patients with health issues that can be improved by regular exercise.
2013-08-31 | 13-038 | http://www.worldconnect-us.org/discoverprojects/leaders-development/ | Janet Smith | SG | X |  |  | X |  |  | Nine student interns began their internships on Friday, August 30, 2013, and will continue throughout the month of September. This particular progress report shows a list of the nine host institutions. We should update the project page with photos.
2013-09-04 | 13-026 | http://www.worldconnect-us.org/discoverprojects/kalou-educational-compound/ | Brett Werkheiser | KE | X |  |  | X |  | X | The greenhouse is almost complete. Soil testing and prep is complete, the structure is up (see pictures), and drip line has been connected to the water tank. There is quite a bit of community interest, which has already allowed the greenhouse leadership team to hold informal trainings on topics such as drip irrigation, crop diversity and composting. Great PL testimonial.
2013-09-04 | 13-027 | http://www.worldconnect-us.org/discoverprojects/maternal-child-health-project/ | Brittany Werkheiser | KE |  | X |  |  |  | X | The project was completed successfully. The placed the order for the maternity ward equipment as soon as grant funds were received, and two days later there was a maintenance team in place to set the equipment up. Two trainings were helf for staff on how to properly use the equipment. As there has yet to be any reporting on the actual use of the new equipment, I'm requesting that the PCV put together a basic, monthly report that will indicate the impact of the new equipment on the MCH care provided by the Hospital and its staff. It's interesting to read that this project (improved maternity ward equipment to improve care) was something that the Hospital initially pitched to the Kenya MoH, but was denied because the government was not distributing funds for new equipment to medical facilities at the time and gave no indication as to when it would be resuming distribution of funds. World Connect filled the gap. Great testimonials. I've also requested more pictures.
2013-09-14 | CDF2012 | http://www.worldconnect-us.org/discoverprojects/singorwet-dispensary-maternity-ward-development/ | Andrea Flynn-Schneider | KE |  |  |  | X |  |  | Photos submitted of the completed Singorwet Dispensary maternity ward clinic.
2013-09-20 | 13-037 | http://www.worldconnect-us.org/discoverprojects/youth-action/ | Kelly Blodgett | SG | X |  |  | X | X | X | Fantastic video, with subtitles, that mentions World Connect by name. To date, they've held three trainings, one in business, one in waste management, one in health. They also held the soccer tournament to great success and participation. There is a lot of dialogue and brainstorming happening before and after the trainings with regards to community projects that could be launched by the youth (in their varying communities) without additional funding, such as monthly trash pickups. The re-trainings in local communities is a little slow to take off but is gaining some momentum. PCV also submitted a summary of answers to survey questions that were asked after the trainings. Great photos.
2013-09-24 | K-711 | http://www.worldconnect-us.org/discoverprojects/bonding-entrepreneurial-innovations-environmental-evolution-b-e-l-i-e-v-e/ | Hallie Davis | PE |  | X |  | X |  | X | Project ended up targeting three groups: two high schools, and one mothers group. High School #1 was wildly successful, their main products being nectars and yogurt, though they also harvested beets, radishes, lettuce and alfalfa, raised guinea pigs and ducks, and harvested honey for sale. High School #2 was much less organized and transportation was an issue, so they focused on just one product: yogurt. The mothers' group focused on ecological and lactose products that provide nutritional benefit. They're continuing workshops and the IGAs as they're sustainable through sales. Overall, the project led to the creation of four small businesses focused on selling vegetables, juice, nectar, cheese, yogurt and honey, and one small guinea pig association. 20% of the total participants are involved in IGAs related to selling products learned during the workshops. Increases in knowledge documented through 90% participants being able to replicate activities post-workshops. Good Beneficiary #1 testimonial.
2013-09-24 | K-046 | http://www.worldconnect-us.org/discoverprojects/elementary-school-improvements/ | Marcela Guachamin | CR |  | X |  | X |  |  | I've added one photo to the project page, as there were none before. I'd like to have CyberNY walk me through the photo upload process. PCV revisited her site in November 2012 and her daughter played on the playground equipment with children from the community. She also noted that the dresses and supplies related to the music/dance component of the project are still being used and have been used by many students since the project.
2013-09-19 | 13-005 |  | Jennifer Krottinger | BZ | X | [5 empty] | PCV submitted an unofficial progress report. The group was able to secure the pro-bono services of a local, professional graphic designer, with experience selling handicrafts. They have developed a logo and decided to do business as Las Sartenejeñas. There is already a waiting list of women wishing to join the group.
2013-09-18 | W-136 | http://www.worldconnect-us.org/discoverprojects/parents-healthy-tomorrow/ | Lauralee Woods | PE | X | [5 empty] | To date, 35 cookstoves/handwashing stations have been installed, while 8 individuals in the community have been trained in the construction process. They're anticipating 14 more cookstoves being installed this fall before the project will complete. The link to the blog is here (http://lauraleeinjorasayabaca.blogspot.com/search?updated-min=2013-01-01T00:00:00-08:00&updated-max=2014-01-01T00:00:00-08:00&max-results=8). Great story of women in the mother's group emerging as leaders in the community.
2013-09-25 | K-625 | http://www.worldconnect-us.org/discoverprojects/bringing-google-guaitil/ | Jennifer Amores | CR |  |  |  | X |  |  | A lot of great photos submitted.
2013-09-18 | 13-038 | http://www.worldconnect-us.org/discoverprojects/leaders-development/ | Janet Smith | SG | X |  |  | X |  | X | I added a photo to the project page, as it did not have one before. This particular progress report details how a PCV accompanied each intern on her/his first day and conducted regular check ups on the interns. It also details how the participants requested a mid project program discussion, where they could present to the other interns and ask questions to each other about their experiences. Great beneficiary testimonials.
2013-09-16 | W-132 | http://www.worldconnect-us.org/discoverprojects/caring-mothers-healthy-students/ | Joseph Luedecke | PE | X |  |  | X |  | X | PCV submitted an Indicators Report (8/16-9/16). Of the 22 families monitored for this particular report, 20 have functioning improved latrines as a result of this project, and the data on their proper care for and use of the latrines is good. 20/22 households are storing water in a secure manner, 22/22 are properly washing food prior to cooking, and 22/22 are separating their trash between organic/inorganic. He also submitted his 3rd official Progress Report: Overall, there are 23/27 participating families with improved, functioning latrines, with the remaining 4/27 in process. Documenting significant positive trends in data related to hygience, health conditions, habits and behaviors of participating families, overall 76% compliance with all measured indicators relating to the household component of the project. As for the schools component, they've witnessed an average of 20-25% increase in students handwashing at critical moments, as a result of the three handwashing workshops and the weekly handwashing lessons being given by teachers at each school. 80% of students are bringing in their own hand-washing materials regularly. Question #2 documents the strong support of the municipal government for this project, great story of collaboration.
2013-09-13 | 13-032 | http://www.worldconnect-us.org/discoverprojects/creation-camp-introduction-traditional-moroccan-artisanal-skills-girls/ | Sarah Quinn | MA | X |  |  |  |  | X | We received a progress report, which was originally written in late July, for this project. At the time, they were reporing having secured a location for the camp and having identified 20/40 young girls to participate. The women of Creation Tameslouht went door to door to identify participants. Great Beneficiary #1 testimonial.
2013-09-16 | W-120 | http://www.worldconnect-us.org/discoverprojects/bio-sand-water-filters-provide-families-safe-drinking-water/ | Thomas Betts | DR | X | [5 empty] | Tommy submitted a finance report detailing costs after the third filter installation, which took place in El Manatial the day before we visited. They're currently working to identify households for one final installation, which will complete the project and exhaust the grant funds.
2013-09-05 | 13-029 | http://www.worldconnect-us.org/discoverprojects/souss-girls-soccer-camp/ | John DeBellis | MA |  |  | X |  |  |  | PCV discusses some of the challenges they had with data collection as well as the role of AMJAD moving forward. While AMJAD will likely run the camp next year, PCVs will still be involved as they are the ones who coordinate the girls' teams in the villages.
2013-09-13 | 13-015 | http://www.worldconnect-us.org/discoverprojects/hearth-healthier-home-smoke-reducing-cook-stoves-culinary-classes/ | Stanley Greidinger | DR | X | [5 empty] | PCV submitted his second informal progress report, noting that they've identified 33 houses to receive the stoves with grant funding, and an additional three houses will be paying for their own stoves, bringing the project's reach to 36 households. To date, they've held two health cooking classes, focused on using low cost food items that are readily available in the campo.
2013-09-26 | 13-041 | http://www.worldconnect-us.org/discoverprojects/play-area-recycled-materials/ | Chelsea Krema | CR | X |  |  | X |  |  | The tables and tires have been setup and painted by the students at the school. They are not going to be able to get the donation of trees as the government program that was to provide the donation has ceased to exist. All that remains is the inauguration of the park.