## Sheet1
Activities | Completed? | Date To Be Completed
Section 1: Under Review
Task 1- announce and Shephard applications
Circulate RFP | X | 2013-03-11
Circulate reminders to Posts | X | 2013-03-27
Provide application/project design support | X | 2013-04-10
Task 2- Prepare applications for Review
Check applications email for new applications | X | 2013-04-10
Download and save application content and attachments to shared files | X | 2013-04-10
Download and save photos to shared files | X | 2013-04-10
Edit and merge application content/attachments | X | 2013-04-10
Print, label and organize complete grant applications | X | 2013-04-10
Task 3- Project Review
Screen grant applications for completion and circulation |  | 2013-04-12
Notify PC HQ/Posts with list of applications received |  | 2013-04-12
Circulate grant applications for review to Youth Advisory Board |  | 2013-04-15
Review grant applications |  | 2013-05-03
Collect/Save grant review forms |  | 2013-05-06
Create grant review data summary spreadsheet |  | 2013-05-07
Make first round of funding decisions |  | 2013-05-08
Communicate first round of approvals to PCHQ, Posts |  | 2013-05-09
Task 4- Grant Agreement Managment
Assign project numbers to newly approved projects |  | 2013-05-09
Add to Master Project Spreadsheet
Reassign approved project materials to In Progress Projects folder
Create Grant Agreements for approved projects |  | 2013-05-10
Distribution of Grant Agreements to PCVS |  | 2013-05-10
Add Project to Internal Tracking System
Task 5- Project Application Revisions
Communicate application revisions request/deadline |  | 2013-05-10
Re-Review grant applications |  | 2013-05-31
Make second round of funding decisions |  | 2013-06-05
Communicate second round of approvals to PCHQ, Posts |  | 2013-06-06
Repeat Task 4- Grant Agreement Managment
Task 6- Application rejection
Communicate project denied notifications |  | 2013-06-10
Reassign denied project materials to Denied Projects folder