## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
At least 50 households will attend classes on health-related impact of smoke inhalation and cookstove use. | Host classes providing education on helath benefits of stoves and their proper maintenance. | Oct, Nov, Dec of 2013 | At least 50 women over 25 yrs old | 1. # individuals attending classes on improved cookstoves. 2. # of individuals able to demonstrate health benefits and proper use of using improved cookstove. | A tally will be kept recording the number and frequency of individuals attending classes for cookstoves, along with observation of their progress. Person responsible: PCV Grossman
50 households will adopt efficient low fuel emission cookstoves to safeguard the health of the mothers and their families. | Construction of improved cookstoves | Jan-June 2014 | At least 50 women over 25 yrs old and their families | 1. # of cookstoves constructed for households or institutions. 2. # of indivifuals able to demonstrate correct use and maintenance of improved cookstove. | 1. PCV Grossman will attend all stove builds, ensuring participation of recipient family and reviewing maintenance of stove. 2. Immediately after last stove is built, follow up visits will commence to each beneficiary family to see how stove usage is going. 3. One week after last stove is built, a meeting will be held to review knowledge gained by beneficiaries and to field questions for any issues or concerns they may have.
At least 50 households will measure and improve health relating to smoke inhalation, according to the questionnaire developed by PCV Elzey. | Complete survey two times, once before stove construction, and again after. | Oct, Nov, Dec of 2013 | At least 50 women over 25 yrs old and their families | 1. # individuals that took the health survey developed by PCV Elzey. 2. # individuals showing improved health. | Before the day of construction, each beneficiary will complete the health survey, then one month after last stove is completed, follow up visits will be made to each beneficiary where they will complete the survey a second time. Responsible: PCV Grossman and Stove Committee
At least 50 households will attend 2 or more classes on human impact on natural environment and ways improve it. | Host classes providing education on friendly environmental practices, e.g. separating waste, making fertilizer. | Oct, Nov, Dec of 2013 | At least 50 women over 25 yrs old and their families | 1. # individuals that attended classes. 2. # individuals showing increased learning in friendly environmental practices. | The volunteer will keep a paricipant log at stove/environment meetings, noting progress.
BEHAVIOR: At least 15 households will adopt improved waste management practices. | Beneficaries will attend classes, participate in motivational activities such as painting the waste bins and community cleanup, and receive help in how to change their waste management. Creating organic fertilizer. | Change by June, 2014 | At least 15 men and women over 25 years old, and potentially entire community. | 1. # individuals separating organic from inorganic waste. 2. # individuals creating fertilizer from organic waste. 3. # individuals responsibly disposing of inorganic waste. | During activities, PCV Grossman will note attendance and progress of participants. Immediately after last stove is built, follow up visits led by PCV Grossman and Vigilance Committee will commence to each beneficiary that attended class to note how waste management practices changed.
ACCESS: Community will develop and implement action plan to improve waste management in community. | At Junta de Vecinos every Saturday, we will develop plan, motivating community members, involving local government. Involving youth in trash collection and painting of garbage bins. | Duration of entire project and beyond - Sept - June, 2014 | 68 women over 25, 38 women under 24, 78 men over 25, 50 men un 24 | 1. If plan has been formulated. 2. If plan has been submitted to ayuntamiento. 3. If waste bins have been purchased and placed in community. 4. If ayuntamiento plans to contribute to waste collection. 5. # individuals using waste bins and no longer burning or littering garbage. | Every Saturday throughout project, PCV Grossman will meet with community group to discuss and work on proposal until completed. PCV Grossman will survey how many people have changed waste management behavior (I already have a baseline).
BEHAVIOR: At least 50 households will no longer use gas or plastic to ignite cookstoves. | Classes on proper methods of igniting stove. Follow up visits. | Oct, Nov, Dec 2013. May, June, 2014 | At least 50 women over 25 yrs old and their families | 1. # individuals using environmentally and stove-friendly methods to ignite stove. | Immediately after last stove is built, follow up visits will commence to each beneficiary to note how stove is being ignited. A log will be kept for class attendance and visit date and results.
INCOME: At least 1 youth will receive education in masonry. | Identified youth will be invited to participate in stove builds and later on in pouring cement floors. | Jan-June 2014 | At least 1 male under 24 years old. | 1. # youth participating in # of stove builds. 2. Number of youth motivated to participate in future cement floors project. | PCV Grossman will keep log of youth attendance at builds, and along with masons, test youth on stove builds, hopefully leading to the full installation of one stove by youth.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)