## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Goal: Parents of our school community will increase participation in effective parental engagement in order to enhance and support student educational opportunities. Objective: For the second semester of the school year 2013-2014, 30 parents, from each school (60 parents in total), will be selected to have the opportunity to receive a participation certificate on the Activity Conference for Parents, with the purpose of exchanging ideas for the improvement of their children’s development. | Selection of 30 parents. The teachers select the parents that will participate, and didn’t participate before. | January, 2014 | 50 women 25 or older, 10 men 25 or older | Measure attendance and motivation of participants Number of parents who completed the healthy parental engagement in the school community, training | 1. List with name of parent, name of their children studying at school, students grade and contact information
| The project team has planning meetings to coordinate the time, dates (two meeting per three months), topics (if not the same as before), and materials needed. This includes getting hold of all the needed resources and materials acquiring. | January, 2014 | 50 women 25 or older, 10 men 25 or older | Monitor project planning process Monitor financial expenses of the project | 1. Simple checklist of all steps and assignments to be achieved/ 2. Explicit data table with materials, dates, expenses and other related information
| The project team should have everything prepared for each meeting with parents. | January, 2014 | 50 women 25 or older, 10 men 25 or older | Monitor project planning process | 1. Simple checklist of all steps and assignments to be achieved
| The Secretaries, the Director and the Teachers will make notifications for all the parents. The teachers will help send with the students the notifications and take their contact information. | January, 2014 | 50 women 25 or older, 10 men 25 or older | Monitor project planning process | 1. Simple checklist of all steps and assignments to be achieved
| Start the Activity Conference with Parents. Each meeting will be dynamic, using the knowledge parents already have and bringing new things to the table. At the start will facilitate knowledge evaluation and will be given again at the end of the Conference to measure each participant’s progress. All meetings should motivate every single parent to participate actively. Every meeting should have a fun activity review for that past meetings topic, and evaluations. The facilitators will have SWOT (Strengths, Weaknesses, Opportunities y Threats) evaluations after each meeting. | January, February, March, 2014 | 50 women 25 or older, 10 men 25 or older | Number of parents who completed the healthy parental engagement in the school community, training/ Increase healthy parental engagement in the school community skill in 60 Parents/ Monitor project planning and implementation process | 1. Simple checklist of all steps and assignments to be achieved/ 2. Pre-post evaluations to measure acquired knowledge/ 3. Group tests to review and evaluate each meeting's acquired knowledge (monitors the meetings effectiveness and the overall progress)/ 4. Checklist for teacher and students observation of the parent specific engagement in the school community attitudes, of each student/ 5. Attendance and participation sheet
| Graduation: By the last meeting, and graduation we will present each parent, who attended to four or more meetings, with a participation certificate. We will ask interested parents to facilitate the next selection of parents, and make sure they attend in the planning meetings for the 1st semester of the school year 2014-2015. They will meet with the PCV before the summer to plan in general aspects. The school psychologist and the academic coordinator will make sure the planning with the new facilitators and implementation is done effectively. | March, 2014 | 50 women 25 or older, 10 men 25 or older | Monitor the Parent facilitator’s knowledge and progress/ Number of trained parents multipliers in healthy parental engagement in the school community | 1. Checklist for capacities the parent facilitator demonstrates.
| Review project monitored data and collect the last data | March, 2014 | 50 women 25 or older, 10 men 25 or older | Number of parents who completed the healthy parental engagement in the school community, training/ Increase healthy parental engagement in the school community skill in 60 Parents/ Monitor project planning and implementation process/ Monitor financial expenses of the project | 1. Simple checklist of all steps and assignments to be achieved/ 2. Pre-post evaluations to measure acquired knowledge/ 3. Group tests to review and evaluate each meeting's acquired knowledge (monitors the meetings effectiveness and the overall progress)/ 4. Checklist for teacher and students observation of the parent specific engagement in the school community attitudes, of each student/ 5. Checklist for capacities the parent facilitator demonstrates.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
These are the monitoring and measuring tools for our project with the primary people in charge of the data collection Attendance and participation sheet-The teacher available in the meeting and the facilitators. Checklist for teacher and students observation of the parent specific engagement in the school community attitudes, of each student- Facilitators List with name of parent, name of their children studying at school, student’s grade and contact information- Teachers Simple checklist of all steps and assignments to be achieved- Facilitators Pre-post evaluations to measure participants acquired knowledge- Facilitators Group tests to review and evaluate each meeting's acquired knowledge (monitors the meetings effectiveness and the overall progress) - Facilitators Checklist for capacities the parent facilitator demonstrates- Team Leader and Peace Corps Volunteer Buying materials and use: Explicit data table with materials, dates, expenses and other related information- Peace Corps Volunteer
prgmform: last updated, 06/26/2012 (pjh)