## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Goal 1: Expand Mothers' Preschool by increasing collaboration among 11association members and 5 preschool teachers and providing information regarding preschool education and how to improve preschooler learning by February 2014. | Meet with project leader, preschool teacher, and original leaders who planned/implemented Mothers' Preschool to plan workshop. | 2014-01-01 | 11 association leaders representing 10 communities | At the beginning and end of this workshop, participants will be asked to answer questions regarding their knowledge and experience with preschool education. Follow-up with the associations and preschool teachers will occur one month following the workshop to determine if any plans or next steps have been taken. | attendance sheet/project leader
| Invite preschool teachers & associations to workshop. | 2014-01-01 | 5 preschool teachers |  | pre-test/post-test/PC volunteer
| Work with preschool teacher and leaders to create presentation for Mothers' Preschool Project. | 2014-01-01 |  |  | evaluation/PC volunteer
| Meet with Ministry of Education to discuss status of preschool education in Morocco; invite to workshop. | 2014-01-01 |  |  | Follow-up/project leader
| Coordinate food, facilities, and materials | 2014-02-01
| Set-up facility. | 2014-02-01
| Hold Workshop. | 2014-02-01 |  | # of participants; # of plans to create preschool following workshop; positive or negative response to workshop evaluations.
| Tour Mothers' Preschool with Group | 2013-02-14
| Assemble toy boxes for preschools & distribute. | 2014-02-01 | 150 preschool children
| Meet with plumber, builders, and schools re: bathroom repairs | 2014-01-01 | 5 teachers
| Schedule Repairs. | 2014-01-01
| Repairs Completed | 2014-04-01 | 250 children; 12 teachers | 1 improved bathroom facilities. | observation/project leader
Goal 2: Host Mothers and Future Mothers Workshops to increase knowledge among 30 mothers and future mothers about health, child development, and income generation by March 2014. (Mothers and Future Mothers Workshops) | Meet with project leader and preschool teachers to plan workshops. | 2014-01-01 | 30 mothers and future mothers | At the beginning and end of each workshop, participants will be asked to answer questions regarding their knowledge and experience with health, child development, or income generation. | attendance sheet/project leader pre-test/post-test/PC volunteer evaluation/PC volunteer
| Meet with mothers to announce project. | 2014-01-01 | 150 preschool children
| Meet with high school students to share opportunity. | 2014-01-01 | 5 teachers | # of participants; # of participants planning to share information; we will also be observing skills demonstrated through group work in the workshops as women make budgets, practice first aid, and so forth.
| Meet with workshop facilitators to plan workshops. | 2014-02-01
| Set dates for workshops. | 2014-02-01
| Prepare materials and mothers' toolkits for workshops. | 2014-02-01
| Coordinate food, facilities, and materials | 2014-02-01
| Hold Workshops. | Feb-April 2014
Goal 3: Establish Mothers' Toy Store to increase income potential of 30 mothers and 27 members of association Tatamatin from $0 to $50 by April 2014 thereby improving access to preschool edcuation for children in Touama. | Meet with project leader and association to plan committee. | 2014-01-01 | 27 association members | $ amount of sales made at grand opening; amount of product; # of customers; customer feedback; and participation in committee by mothers and preschools. | cash flow/association & project leader
| Invite preschool teachers, mothers and other women to join committee. | 2014-01-01 | 30 mothers and future mothers |  | interviews/association & project leader
| Create committee. | 2014-02-01 | 5 preschool teachers |  | attendance sheet/project leader
| Meet to create business plan for store and identify roles/responsibilities. | 2014-02-01
| Determine products, pricing, and financial management. | 2014-03-01
| Create signage, marketing materials & marketing plan. | 2014-03-01
| Begin making or collecting products/inventory. | 2014-03-01
| Set-up store space. | 2014-03-01
| Begin promoting store. | 2014-03-01
| Begin selling | 2014-03-01
| Evaluate program | 2014-04-01
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
We will use a combination of informal interviews, evaluations, pre and post tests to evaluate this project. Throughout the project, the project leader will be asking participants in the project for feedback and monitoring the project deadlines to ensure we are meeting our deadlines and workplan objectives. However, throughout the project participants will be asked a simple "how is it working so far" question; at the end of the project participants will meet to discuss what went right, what went wrong, and what next. Each workshop will include evaluations and pre and post tests to determine any changes in knowledge or attitudes. Participation is often a good indication of a project's success and will be monitored through attendance sheets.
prgmform: last updated, 06/26/2012 (pjh)