## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To prepare 40 rising high schoolers (sixth graders) from rural communities for success in high school English courses by the start of the 2014 school year (February 2014) through intensive, remedial instruction in the language during the summer break from school. | Facilitate a month-long English camp (JumpStart) covering topics from the Ministry of Education´s (MEP´s) English curricula for elementary school and the first years of high school, with 40 student participants and 2 Ministry of Education (MEP) co-teachers | January-February, 2014 | DIRECT: 40 local youths (approx. 20 boys and 20 girls) ages 11-13 | KNOWLEDGE: Increase in knowledge related to English topics covered during elementary school and first years of high school among at least 70% of camp participants (28 students) between start and finish of camp | An oral assessment to be administered to camp participants both before and after JumpStart to measure improvement in students´ English conversation skills over the course of camp. PCV responsability.
|  |  |  | BEHAVIOR: Improved confidence in personal aptitude for learning English among at least 70% of camp participants (28 students) between start and finish of camp. | A survey to be administered to students both before and after JumpStart. PCV responsability.
To improve the quality of English instruction received by at least 250 students during the 2014 school year (February - December, 2014) as a result of improving the teaching and conversational skills of 2 public school English teachers during the preceding summer break from school. |  |  | DIRECT: 2 public school English teachers (1 male and 1 female) over the age of 24 | KNOWLEDGE: Improved English conversation skills among both camp co-teachers. | A grade of 0-20 to be assigned to each co-teacher during month after camp based on overall improvement throughout JumpStart, with 15+ representing adequate progress. PCV responsability.
|  |  |  | BEHAVIOR: Increase in confidence and skill when implementing communicative JumpStart activities among both camp co-teachers. | A grade of 0-20 to be assigned to each co-teacher during month after camp based on overall improvement throughout JumpStart in the area of teaching strategies, with 15+ representing adequate progress. PCV responsability.
|  |  | INDIRECT: 250 local youths (approx. 125 boys and 125 girls) between the ages of 6 and 18 | ACCESS: Increase in exposure to dynamic, communicative methodologies for learning English among at least 250 local public school students in JumpStart-trained co-teachers´ classrooms. | Post-camp report to be filled out by each co-teacher and turned in to CRML during month after JumpStart (includes question about current number of students).
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
JumpStart participants´ growth in English will be measured using an interview to be administered twice with each student, once prior to JumpStart for establishing a baseline and a second time at the end of camp. As the interview is oral, it focuses on coversational skills in English, specifically in regards to English topics that students are supposed to have mastered by the end of elementary school, as well as additional topics that are covered during the first years of high school. During the JumpStart pre-camp training, Peace Corps Volunteers and their camp co-teachers will be trained on how to implement and evaluate the interview, though administering this assessment tool is primarily the responsability of PCVs. Participating elementary school principals have committed to allowing PCVs to administer pre-camp interviews during the first weeks of September so that as much camp time as possible can be devoted to JumpStart lessons. Post-camp interviews will be administered during the last days of JumpStart. In addition to the interview, a student survey will be used to help evaluate success in achieving Goal 1. Students will complete pre- and post- camp surveys with similar multiple choice questions for gauging student perspectives on English and high school in general, such as "How useful do you feel Englsh is for your future?" "How prepared do you feel for high school?" and "How do you feel about learning English?" Within a month of JumpStart´s completion, PCVs will provide CRML with a score between 0 and 100 for each of their co-teacher´s performance. These scores will be submitted to the "Instituto de Desarrollo Professional," which requires a score of at least 70 to approve a teacher for training credits as a result of JumpStart. The overall score consists of scores between 0-20 in 5 different areas, including active participation during JumpStart; improvement in English skills; improvement in classroom management techniques; and improvement in teaching strategies. PCVs will grade teachers based on their observations during JumpStart, and co-teachers have been made aware of this assessment strategy. Like PCVs, co-teachers will also complete post-camp forms to aid in project assessment within one month to six weeks of JumpStart´s completion. In addition to questions for learning co-teachers´ thoughts on JumpStart methodology, which lessons were most useful/replicable, etc, the report will include a space for co-teachers to indicate the number of students in their classrooms during the 2014 school year. This number will be used to determine the number of indirect beneficiaries for JumpStart.
prgmform: last updated, 06/26/2012 (pjh)