## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Through the 4P’s Parent Leader Livelihood Training, 50 Parent Leaders will learn new skills in any of the following topics: food processing/ preservation, meat processing, accessory-making in July/August 2014. | Talk to TESDA, DTI, Dept. of Tourism about pricing for training, resource speakers, and possible supplies needed for starter kits | 2014-04-11 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon
| Make contact with resource speaker(s), inquire as to availability and reserve for training; | 2014-04-30 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon
| Determine how the Parent Leaders will be divided for the training | 2014-05-09 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Inform Parent Leaders which training they will be attending | 2014-05-16 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Meet with LGU representatives; ask for monetary or in-kind support for training | 2014-05-16 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Distribute letters to local businesses soliciting donations for training | 2014-05-23 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Arrange food for training (including snacks and lunch, drinks) | 2014-05-23 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Arrange venue; determining the number of days needed for training | 2014-05-31 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Collect materials for starter kits | 2014-06-06 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon
| Collect materials for training | 2014-06-06 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon
| Conduct training | 2014-07-01 | 50 Parent Leaders | Increase in knowledge related to basic livelihood training among 50 Parent Leaders. | Pre- and Post-Test to be given prior to the start of training; Ms. Dillon / Ms. Lisaba
| Invite Barangay and LGU officials to attend training | 2014-06-27 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Assemble starter kits and materials for training | 2-weeks prior to training | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Collect any donated items, give thank you letters | 1-week prior to training | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Following livelihood training, give thank you letters to those who offered support | 2-weeks post training | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Follow up with Parent Leaders about training; monitoring and assessment | 2-weeks, 1-month & 2-months post training | 50 Parent Leaders | Increase in creation of product and skill familiarization among 50 Parent Leaders / Increase in income by 5% of total monthly income in 2 months by 25 Parent Leaders. | Home visits & interviews; ask for demonstrations of acquired knowledge; Ms. Dillon & Ms. Lisaba
For 50 Parent Leaders to conduct (and re-echo) the Livelihood Training from July 2014 for a total of 1,376 beneficiaries during the Family Development Sessions from October to November 2014 | Check-in with 50 Parent Leaders; assess their status and comfortability with subject matter | 2014-09-01 | 1376 Beneficiaries |  | Ms. Lisaba / Ms. Dillon
| Determine which Parent Leaders will be facilitating certain topics for member beneficiaries | 2014-09-12 | 1376 Beneficiaries |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Schedule Parent Leaders; inform them of schedule | 2014-09-19 | 1376 Beneficiaries |  | Ms. Lisaba / Ms. Dillon / 5 Parent Leaders
| Conduct mini-training on facilitation skills utilizing CSWDO venue | 2014-09-19 | 50 Parent Leaders |  | Ms. Lisaba / Ms. Dillon
| Conduct re-echoing of training for member beneficiaries | 2014-10-01 | 1376 Beneficiaries | Increase in facilitation skills and livelihood skills among 50 Parent Leaders | Observation; Ms. Lisaba / Ms. Dillon / 50 Parent Leaders
| Follow up with beneficiaries and Parent Leaders; assess effectiveness | 11/1/2014; 2-weeks, 1-month & 2-months post training | 1376 Beneficiaries | Increase in income by 5% of total monthly income in 2 months by 344 beneficiaries. | Home visits & interviews; ask for demonstrations of acquired knowledge; Ms. Lisaba / Ms. Dillon
As mentioned previously, this project intends to utilize the existing infrastructure of monitoring and evaluation that are already imployed by the 4P's program. That being said, the two City Links involved in the project will follow-up and monitor both Parent Leaders and member beneficiaries through: pre- and post-test surveys, observation, home visits, parent leader meetings and interterviews. Ms. Lisaba will be the primary collector of data since this is in her current job description and she is the most qualified person to do so.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)