## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Goal 1: Community members will use improved cook stoves to reduce upper respiratory infections and be environment friendly. | Objectives below | Objectives below | Objectives below | Objectives below | Objectives below
Objective 1.1: By August 2013, 50 households will adopt new and improved cook stoves to safeguard the health of their children and family. | 1.) Construction of 50 cook stoves. 2.) Mandatory meeting/lecture on health benefits for all benficiaries. | Constructin will start in June. One cookstove will be built a day/5 a week. Considering rain and other factors by August 2013 all 50 cookstoves will be built. | 50 households: At least 50 women and men ages 24 and up. Averaging 3 (infants, children,youth) per household -150 total. | 1.) 50 cook stoves constructed amongst the two communities Maguana Arriba and Maguana Medio - one per households (50 household totals). 2.) 50 individuals trained on the health benefits of using improved cook stoves. | 1.)Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Attendance will be taken at all mandatory meetings/lecture.Responsible:Project committee (including PCV).
Objective 1.2: By August 2013, 50 mothers will adopt healthy behaviors/lifestyles from the benefit of smoke free kitchens | 1.) 3 Mandatory meetings/lectures on the following: 1. Introduction to the project and why it is important (including health and environmental benefits). 2. How to cook with your stove. 3. How to maintain and repain your stove. | 1st meeting will be held at the very beginning of project. 2nd will be held after the beneficiaries have been selected. 3rd a week after the 2nd meeting. Construction will not begin until after all meetings have been held. | 1.) 50 mothers 2.)50 men 3.) Averaging 3 children per household - about 150 children. | 1. At least 50 mothers trained on the health risk of smoke and benefits of smoke free kitchens. 2. 150 children from the households benefit from smoke free households. | 1. Mandatory lectures on health and environmental benefits. Attendance will be taken. 2.) Survey taken before the second meeting on knowlwdge and practices women are currently doing. 3.) Same Survey taken at the end of the 3rd meeting. 4.) Observation and note changes seen after a month of using stove. Responsible: Organization and project committee.
Objective 1.3: By August 2013, 50 households will adopt behaviors and practices in reducing contamination of the environment. | 1.) 3 Mandatory meetings/lectures on the following: 1. Introduction to the project and why it is important (including health and environmental benefits). 2. How to cook with your stove. 3. How to maintain and repain your stove. | 1st meeting will be held at the very beginning of project. 2nd will be held after the beneficiaries have been selected. 3rd a week after the 2nd meeting. Construction will not begin until after all meetings have b | 1. 50 mothers 2. 50 men 3.) Averaging 3 children per household - about 150 children. | 1. At least 50 mothers and husbands trained on the health risk of smoke and benefits of smoke free kitchens. 2. 150 children benefit from smoke free households | 1. Mandatory lectures on health and environmental benefits. Attendance will be taken. 2.) Survey taken before the second meeting on knowlwdge and practices women are currently doing. 3.) Same Survey taken at the end of the 3rd meeting. 4.) Observation and note changes seen after a month of using stove. Responsible: Organization and project committee.
Goal 2: Increase job creation and employability via education, value added practices, and skills. | Objectives below | Objectives below | Objectives below | Objectives below | Objectives below
Objective 2.1: By August 2013, one community member will be certified as a mason in building this new stove model and will be able to transfer these skills to other community members. | 1.) Community Mason attended a two-day training of the construction and benefits of the stoves. | 1.) Training was held March 8-10, 2013 | 1.) Community mason 2.) At least 50 community members (one household member required to help mason). | 1.) One community member will be trained on the construction of the stove model. 2.) At least 50 community members will benefit from trained masons skills on the construction of the stove 3.) Mason will have the education, practices, and skills necessary to make this a source of income generation. | 1.) Certificate of masons participation in the training of stove construction 2.) Each household is required to provide at least one household member to help with the construction of stove (Part of beneficiary contract) 3.) Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Responsible: Mason, Hogares Saludables, project committee
Objective 2.2: By August 2013, 50 community members will have the education, practices, and skills to build the new stove model. | 1.) Construction of 50 stoves | By August 2013 | 1.) At least 50 community members (one household member required to help mason). | 1.) At least 50 community members will have the skills to build a stove. 2.) At least 50 community members will adopt new practices and skills for possible income generation. | 1.) Each household is required to provide at least one household member to help with the construction of stove (Part of beneficiary contract) 2.) Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Responsible: Mason
Goal 3: Community organizations will strengthen their capacity to develop and implement sustainable projects, manage their resources, and collaborate with others to achieve their missions. | Objectives below | Objectives below | Objectives below | Objectives below | Objectives below
Objective 3.1: By August 2013, 3 community organizations will implement participatory project assessment and planning practices. | 1.) Hogares Saludables groups in community sectors Maguana Arriba (2 groups) and Maguana Medio participated in project planning and will participate in all project meetings/activities throughout project 2.) Weekly meetings at the end of the week with organizations and project committee | 1.) Project planning: March - April 2.)Weekly meetings (end of the week) throughout project | 1.) 3 Hogares Saludables group members (total of 38 women) 2.) Project committee: mason and 5 group leaders of Hogares Saludables. | 1.) 3 community organizations will be trained on project assessment. 2.) 38 women of Hogares Saludables will participate/ trained on project planning practices. 3.) Committee project will be trained on project assesment and planning practices. | 1.) Organizaton and Project committee participated in Project planning meeting. 2.) Weekely meetings throughout project with organization and committee -Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Responsible: PCV, Hogares Saludable groups and project committee.
Objective 3.2: By August 2013, 3 community organizations will improve project management | 1.) Hogares Saludables groups in community sectors Maguana Arriba (2 groups) and Maguana Medio participated in project planning and will participate in all project meetings/activities throughout project 2.) Weekly meetings at the end of the week with organizations and project committee | 1.) Project planning: March - April 2.)Weekly meetings (end of the week) throughout project | 1.) 3 Hogares Saludables group members (total of 38 women) 2.) Project committee: mason and 5 group leaders of Hogares Saludables. | 1. 3 community organizations will be trained in project management through their active participation of this project. | 1.) Organizaton and Project committee participated in Project planning meeting. 2.) Weekely meetings throughout project with organization and committee -Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Responsible: PCV, Hogares Saludable groups and project committee.
Objective 3.3: By August 2013, 3 community organizations will improve their capacity to develop and implement sustainable projects. | 1.) Hogares Saludables groups in community sectors Maguana Arriba (2 groups) and Maguana Medio participated in project planning and will participate in all project meetings/activities throughout project 2.) Weekly meetings at the end of the week with organizations and project committee | 1.) Project planning: March - April 2.)Weekly meetings (end of the week) throughout project | 1.) 3 Hogares Saludables group members (total of 38 women) 2.) Project committee: mason and 5 group leaders of Hogares Saludables. | 1. 3 community organizations will be trained on developing and implementung sustainable projects through their participation in this project. | 1.) Organizaton and Project committee participated in Project planning meeting. 2.) Weekely meetings throughout project with organization and committee -Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Responsible: PCV, Hogares Saludable groups and project committee.
Objective 3.4: By August 2013, 3 community organizations will adopt new practices to collaborate with others to achieve their missions. | 1.) Hogares Saludables groups in community sectors Maguana Arriba (2 groups) and Maguana Medio participated in project planning and will participate in all project meetings/activities throughout project 2.) Weekly meetings at the end of the week with organizations and project committee | 1.) Project planning: March - April 2.)Weekly meetings (end of the week) throughout project | 1.) 3 Hogares Saludables group members (total of 38 women) 2.) Project committee: mason and 5 group leaders of Hogares Saludables. | 1. 3 community organizations will be trained in new practices to collaborate with others to achieve their missions as a group through their participation in this project | 1.) Organizaton and Project committee participated in Project planning meeting. 2.) Weekely meetings throughout project with organization and committee -Weekly assessments of progress will be documented by observation and noting progress on a schedule/calendar. Responsible: PCV, Hogares Saludable groups and project committee.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
A questionnaire with questions on behaviors and knowledge (questions on women’s time spent in kitchen, women’s and children’s health, etc.) will be given before the start of the second mandatory meeting/lecture “How to cook with your stove”. Every beneficiary must attend these meetings and participate in the questionnaire. Same questionnaire will be given after the beneficiary has been using their new cook stove for at least two weeks. A contract has been developed for all the required beneficiary contributions; family must contribute all requirements before the start of construction. Weekly meetings will be held for the project organization (Hogares Saludables) and the Project committee throughout project (Discuss how project is going, necessary action plan, changes, or follow ups). All projects monitoring and evaluation will be the responsibility of the projects organization and committee.
prgmform: last updated, 06/26/2012 (pjh)