## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
| Project Goals: To increase household income, farm yield, reduce malnutrition in children and increase the living conditions of 100 women and Girls in five women organisations in the Meluf community through the provision of vocational training in income generating activities and agricultural loans. | Advance to Project Plan Template --->
How we intend to achieve this: Strengthening the evidence and knowledge base to address gender/Women's issues in agriculture. Empowering them to improve and have control over their own produce as a means of strengthening their financial background. (b) Providing them with managerial and technical capacity building to enable them to run a business. This should improve their financial viability and thus act as a bridge to the solution to many of the problems they encounter. (c) The provision of vocational training/support in activities like marketing, tailoring and market gardening. (d)Also help in activation of value chains in the transformation of primary less expensive products to more valuable products. Such include the processing of crops like cassava other valuable products like Garri, meyondo etc all of which have high demand in the market. (e) To provide women with basic equipment to start a job and support them to become organised in community-based working units to effectively manage and run their businesses (f) To establish women’s associations in marketing (business units) to exploit collective bargaining power as well as build strong coalitions with like groups elsewhere. (g)Provide them with technical, administrative and logistical support and promote their products in the formal market through the provision of publicity tools on the various media. (h) Promoting collective action and leadership of these women in order to take advantage of opportunities and address discrimination (i)Promoting women’s ownership and access to productive resources (j) Making women/gender aspects in agriculture more visible and recognized
Time frame: This project is to start in September 2014. It is to start with the communal cultivation of irish potatoes the highest income generating crop here. The advantage is that it will help raise the finances to three times the initial amount requested making the project stronger in terms of finances. A microfinance scheme will then be set up in preparation for the upcoming farming season which starts in March 2015. Other activities will also be carried and include trainings, capacity building measures. A Women's cooperative will be created immediately after the sale of the irish potatoes to take control over the micro finance scheme. This should be Done in January in preparation for planting which should start in March. |  |  | take at most three months to mature
Total Expected Beneficiaries: The project is designed for 100 direct beneciaries but it will benefit some 550 women and girls including direct beneficiaries. A total of 60 women with ages of 24 and above with their entire families will benefit from the project. This will be in the area of provision of agricultural loans to enable them increase farm yield much needed to improve the living standards. 25 girls of less than 24 years will be trained in other vocational activities including income generation and in the activation of value chains which should enable them raise enough incomes from the conversion of primary less expensive to more valuable products. 8 young girls shall equally benefit from this in that, we shall be able to send them to vocational schools to take up academic course in these fields. Others enlisted and younger than 17 will benefit from regular academic courses.
The first indicator will be measured after the first three months of the start of the project. The results of the cultivation of irish potatoes. Proceeds should be greater than or equal to three times the amount initially requested. We equally shall look at the number of women and girls applying to join the cooperative and the enthusiasm with which current members are participating in project implementation. This should be seen in how they come out to work on the communal farm during moulding and harvesting. The next indicator will be measured late in April during harvesting. Given that women will be able to cultivate larger pieces of land will be evidence that their level of income has increased. Expenditure styles and immediate reation to health demands. We shall measure too the success of the project during the first 9-10months for those who will recieve vocational training in marketing, tailoring and other activities.
Data collection method shall be done by the project management committee under the surpervision of the project leader. Questionnaires shall be distributed from time to time to beneficiaries to fill. Interviews shall also be conducted and results used to see where adjustments to the project can be made. The project committee shall be charge with close follow up of all activities relating to the project and every individual shall be expected to give an account of how she is running her own activities.

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)