## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To improve the health of women and children in the 40 participating households in La Loma de La Gallina and La Guardia Arriba within the six month project time-frame. | 1. Form an improved cook stove committee from local community members. | 1. Within first week of project start (most of the committee has already been selected). | 1. 4 men and 4 women above the ages of 24. | Increase in access to improved cook stoves among forty households in the two communities, La Loma de La Gallina and La Guardia Arriba. | Survey, Community Organization (Improved Cook Stove Committee)
To improve the environment in La Loma de la Gallina and La Guardia Arriba by reducing the amount of wood needed to fuel 40 traditional cook stoves within the six month project time-frame. | 2. Improved cook stove committee helps select 40 households to partake in the improved cook stove project by surveying the 500 households in the two communities and determining who uses the traditional cook stoves the most (versus gas stoves) and what households have the highest number of people exposed to the cook stoves (women and children). | 2. Within first month of project start. | 2. 40 women above the ages of 24. | Decrease in deforestation (behavior) among forty households in the two communities. | Survey, Community Organization (Improved Cook Stove Committee)
To train a local mason and educate 40 households on the use and maintenance of the improved cook stoves to ensure the longevity and sustainability of the project. | 3. Construct an example of the improved cook stove in the local primary school to allow the potential 40 households to decide whether or not they like the improved cook stoves and want to participate in the project. The primary school wants a stove because they currently do not have a method of cooking snacks or a lunch for the school children. | 2. Within first month of project start. | 3. Indirectly 40 women above the age of 24 participating in the project will benefit and directly 31 children under the age of 12 attending school will benefit. | Increase in knowledge related to the use of the improved cook stoves among forty households and one local mason in the two communities. | Three educational classes offered on the (1) need for improved cook stoves and their (2) use and (3) maintenance, done by Project Leader and PCV
| 4. Require 40 households participating in the project to attend three educational classes on the improved cook stoves. These classes are facilitated by PCV and Project Leader and will cover the purpose of the improved cook stoves, how to use the improved cook stoves, and the maintenance of the cook stoves. | 4. Finish three educational classes within three months of project start. | 4. 40 women above the age of 24
| 5. The locally trained mason, PCV, and members of the 40 participating households construct the 40 cook stoves over the course of four months. | 5. Construct all improved cook stoves within three month time frame, finishing five months from project start. | 5. 40 women above the age of 24, 15 females between the ages 18-23, 15 females 6-17, 20 females ages 0-5, males ages 6-17, males ages 0-5
| 6. A month after the cook stove is constructed, members of the improved cook stove committee will check in on the 40 households to make sure they are using the cook stoves correctly. | 6. Check on households one month after their stove has been constructed. A majority of the housing checks should be done by the end of six months after project start. | 6. 40 women above the age of 24, 15 females between the ages 18-23, 15 females 6-17, 20 females ages 0-5, males ages 6-17, males ages 0-5
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Baseline: Improved cook stove committee surveys 500 hundred households to identify 40 households that primarily rely on traditional cook stoves to feed their families. Carried out by community organization (improved cook stove committee). Midline: Require 40 participating families to attend educational classes on the improved cook stoves to ensure dedication to project and readiness to use the new stoves. Carried out by Project Leader and PCV. Final: Improved cook stove committee visits and interviews the forty households to ensure they are using the new cook stoves correctly and understand the benefits of the improved cook stoves. Carried out the community organization (improved cook stove committee).
prgmform: last updated, 06/26/2012 (pjh)