## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To provide 3000 adolescents with a safe after-school center that offers programs to advance and reinforce their knowledge base through healthy activities. | The after school center will allow adolescents to interact and grow as leaders in healthy learning activities and awareness programs emphasizing: study clubs, adolescent development, gender difference, hygiene, self esteem, importance of education, knitting, cooking , nutrition, farming, literacy programs, and HIV/AIDS awareness. | The activities are on going all year round. They will start promptly on July the 15th and be held everyday after school. | 3000 adolescent school students will benefit from this project. | 1. Increase in knowledge related to proper study methods among 3000 adolescent students. 2. Increase in access to local nutritious food sources among 3000 adolescent students. 3. Increase in school attendance from the importance of education programs among 1000 secondary school students. 4 Increase in knowledge related to adolescent chages among 3000 males and females. | Weekly surveys will be taken by adolescents to ensure optimal honest feedback about the study sessions and activites. They will then be reviewed by the Project Leader and teachers. Also the primary and secondary school exam scores will be monitored by Project Leader and PCV to watch grade flucuations.
To provide 150 nursery school students in the community with a clean, healthy learning environment to grow and flourish during these important years of their lives. | In order to provide a safe environment for 150 children to develop healthy learning styles. The facility should have real floors, windows, and a safe ceiling that isn't about to cave in. It is also extremely important to have tools to aid in optimal knowledge absorption like desks, chairs, chalkboards, chalk , and number boards. Children will learn how to count, write, wash hands, general hygiene, and cultural norms. The new environment will give children a healthy advantage to boost learning in their delicate first years of life. | The Nursery School will be open all 12 months of the year. | 56 nursery school students will benefit from this project. | 1. Increase in knowledge related to hygienic practices among 150 nursery school students. 2. Increase in access to a healthy environment among 150 nursery school students. 3. Decrease in overall ringworm and roundworm contractions due to hygienic awareness and sanitary facilities. | The project leader and nursery school teachers will monitor children's spike in knowledge absorption by having Friday share days with the students. Children will also be checked weekly for decreases in roundworm and ringworm contraction due to the new facility standards.
To provide 1075 women in the community access to an area where they can congregate in private and discuss important matters related to the community itself, mainly group meetings. | 1075 women will have an where they will be able to address health issues around the community through group meetings. Women will plan and teach classes pertaining to the specific needs in the community like sanitary cooking, empowerment of women, at-risk adolescents behavior, farming tips, income generating projects, sanitary pad project healthy breast feeding, and literacy programs. Women with specific knowledge in different sectors will schedule to teach different classes each week. There will be sign up sheets each week in order to give everyone a chance to be involved. | Starting on July 15th 2013, the first women's group will meet with the topic of early child birth and the adverse effects surrounding it. Three classes will be scheduled each week taught by a community member. There will also be four women's group meetings scheduled each week on different days. The classes and group meetings will take place between 1:00 and 4:00, after nursery school gets out and before students arrive. These activities will go on 12 months out of the year. | 1075 women will benefit from this project. | 1. Increase in knowledge related to the indigenous views of women in kenya among 1075 women. 2. Increase in sanitary practices in the kitchen to decrease diseases among 1075 women. 3. Increase in access to new knowledge from friends and neighbors among 1075 women. 4. Increase in knowledge related to healthy breastfeeding among 200 expecting mothers. | Surveys will be taken weekly after every session asking how the classes went and positive or negative feedback they can offer. The project leader and chief will be collecting this data for weekly reviewing each Saturday.
To provide a place for weekly HIV/AIDS women's support and couseling group meetings. | This multi-functional center will also be utilized as a woman's HIV/AIDS group counseling and support center.Counseling sessions will be offered along with HIV/AIDS awareness, support groups, stimga reduction, and at-risk women awareness sessions. All of these sessions will be taught by a local volunteer public health officer. | The first HIV/AIDS couseling session will be held Wednesday July 17th at 2:00 p.m. The sessions will then take place every Wednesday at the same time. | These couseling sessions will be group sessions only offered to women. Approximately 26 women have signed up for the July 17th group counseling session in advance. | 1. Increase in knowledge related to HIV/AIDS prevention among 1075 women. 2. Increase knowledge related to HIV/AIDS transmission from mother to child among 1075 women. 3. Increase in access to counseling sessions for HIV/AIDS positive women. | The Public Health Officer(PHO) will take notes and offer recommendations after each session. The PHO and the Project Leader will discuss any positive or negative feedback and work to create the most comfortable environment for the groups.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Usafi women's group has set up monthly meetings to receive feedback about the classes, activities or anything pertaining to the events that occur in the center. Meeting will be held on 30th of every month. The monthly meetings will also include personal one on one interviews with the women who have taught the classes each month. They will be able to accurately give feedback about how the women perceive the classes. These meetings will help the women monitor the class progression and let them know if they need to make any alterations. After each woman’s group meeting the ladies will fill out a survey rating the improvement of the gathering due to the new facilities. The headmasters of each school will meet separately every two weeks with the project leader and PCV to discuss how study group sessions are affecting student’s exam scores, parents of the students will also be present during this meeting. The nursery school will have weekly ringworm and roundworm checks from the public health officer. They foresee a 90% decrease due to the new sanitary facilities of the renovated school. The Project leader, Peris Mwangi, will be present at all the meetings to consolidate all the information received from the interviews, surveys, and observation. This information will be shared with the Peace Corps Volunteer every two months. With these tools the community will be able to monitor and measure their project’s successful progress independently in these next years.
prgmform: last updated, 06/26/2012 (pjh)