## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Dates are subject to change depending on if and when funding is received
Obtain quotations of material costs at local hardware stores and other material vendors | Visit vendors, compare pricing, negotiate | 2014-04-01 |  | Baseline | Volunteer and Project Partner
Community meeting to layout project specifics and timeline | Organize meeting and delegate tasks | 2014-04-01 |  | Baseline | Volunteer, Project Partner and Community Organization
Recruit donated labor | Motivate the community, set work schedule and dates | 2014-04-01 |  | Baseline | Direct observation/Volunteer, Project Partner and Community Organization
Draw up contract for land | Meet with land owner, lawyer and obtain signatures for official documents of ownership | May, 2014 |  | Baseline | Volunteer and Peace Corps
Purchase store and install materials | Find a secure location to store raw materials | June , 2014 |  | Baseline | Volunteer and Project Partner
Adjust land gradient for drainage with gravel fill | Pour and spread gravel | June, 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Complete cement floor | Put in gravel baed subfloor, install corrigated rebar, pour cement | June, 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Modify drainage and columns | Apply stucco to the tops of the columns | June , 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Install pvc water tubing and spigot | Connect tubing to mail outflow, install spigot | June, 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Install electrical materials, electrical interver and fixtures | Run electrical wire through condunit, install and connect breaker box, run wiring to street pole, install and configure invertor and batteries, install fixtures and light bulbs and plugs | July, 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Paint interior of the building | Apply paint | July, 2014 |  | Midline | Direct observation/Volunteer, Project Partner, Community Organization and community members
Metal security bars | Fabricate and install security bars on existing windows | August, 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Paint exterior of the building | Apply paint | August, 2014 |  | Midline | Community member, Malu
Sanitation/Community center bathroom facility | Dig hole and install floor, build surrounding walls for bathroom facility | September, 2014 |  | Midline | Direct observation/Volunteer, Project Partner and Community Organization
Fill the center's interior | Buy furniture | September, 2014 |  | Midline | Direct observation/Volunteer, Project Partner, Community Organization and community members
Build and install bookshelves | Mount shelving and fill with donated books | September, 2014 |  | Midline | Direct observation/Volunteer, Project Partner, Community Organization and community members
Innagurarte center! | Invite distinguished guests, present possible clas schedule and hours of operation, arrange food, set date, organize youth activities for entertainment etc. | October, 2014 |  | Final | Direct observation/Volunteer, Project Partner, Community Organization and community members
Commence learning | Orient community educators and students, begin to collaborate with INFOTEP, administer pretests for each course | October, 2014 | 150 females >24, 100 females 18-23, 125 females 6-17, 75 females 0-5. 100 males >24, 75 males 18-23, 70 males 6-17, 45 males 0-5 | Final | Pre test/Post test/Direct observation/ Volunteer
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The success of this project is two-fold. The first success is the completion of the Youth Community Center. The second success is that programs can now be held in a safe environment and benefit the maximum number of community members and willing participants (youth as well as interested women and adults). Progress building the center will be monitored and evaluated bimonthly to ensure that we are maintaining a proper schedule. The Junta de Vecinos, with the help of the Porject Parter, Jovanny and Volunteer, Corinne, will speed up progress depending on whether or not tasks are not being completed in a timely manner. We will plan for a small amount of flexibility in the schedule for unforeseen events such as bad weather or a shortage of laborers. We plan to use direct observation to evaluate the progress of the communty center. Once it is built, every program that is run out of the community center will have a pre test and post test that will allow for evaluation of the effectiveness of each program and the volunteers ability to deliver information. The volunteer will use the results of the pre test and post test to monitor and alter subsequent classes and programs to different groups of youth and adults. The volunteer will collect and analyze this data using descriptive statistics and the evaluating tools available through Microsoft excel to determine effectivness and necessity to change or alter certain methods of deliver. The knowledge of the participants is expected to increase over the course of the program and subsequently, behaviors of participants are expected to change. For example, with the newfound knowledge of sexually transmitted diseases, it is expected in post tests that the majority of participants report that if they had not already been using a condom, they are now practicing safe safe by wearing a condom and only having one sexual partner at a time. Or to say that the participants of the groups will have changed risky behaviors due to the new knowledge they are equipped with. Both the knowledge and behavior changes will be determined by the differences between pre and post testing as well as reported differences in behavior. The volunteer will share findings with the Project Partner and the Junta de Vecinos and investors as data becomes available.
prgmform: last updated, 06/26/2012 (pjh)