## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To provide music education to 30 students (40% of C.E. Buenos Aires) by September 15 through marching band. | 1. Purchase 21 instruments. 2. Maintain proper care and repair the 9 instruments that are currently in school. 3. Hire music instructor. 4. Have music class twice a week for two months leading to September 15 | June 30 to September 15 | 30 students of C.E. Buenos Aires, 15 boys (15 years and younger), and 15 girls (15 years and younger) | 1. Increased knowledge related to musical performance among 30 students in C.E. Buenos Aires. 2. Increase in access to music classes among 30 students in C.E. Buenos Aires. 3. Receipt of purchase of the instruments. 4. # of instruments in use at beginning, middle, and end of project. 5. # of students that attend music classes through project and on September 15. | The Music Instructor. Project Leader. and School staff
To promote gender equality by having at least half (50%) of the students in the marching band be girls. | 1. Promote music education to girls, by allowing them to tryout the instruments. 2. During tryout of the marching band strive to include half girls, half guys. | June 30 to September 15 | 15 girls (15 years and younger) | 1. Increase in access to music classes among 15 female students in C.E. Buenos Aires. 2. # of girls in attendance at music classes and march on September 15. | The Music Instructor and the Project Leader.
By September 15 the project leader will be prepared to lead the band next year, as recommended by the school and music instructor. | 1. The Project Leader will attend at least 80% of music classes to observe, assist, and learn teaching methods. 2. Project leader will obtain music modules from the music instructor. 3. Project leader will be evaluated after September 15 by music instructor and school staff. | June 30 to September 15 | 1 man (25 years and younger) | 1. Increase in knowledge of teaching marching band among the Project Leader. 2. Recommendation letter written and approved by school staff and music instructor. | The Music Instructor and School Staff.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
For Goal #1: An attendance sheet will be used each class by the music instructor and Project Leader to collect data on # of students in music classes. A proof of purchase of the # of instruments purchased will be obtained by the school staff. An inventory list of # of instruments in C.E. Buenos Aires will be kept and updated by the Project Leader. For Goal #2: The attendance sheet will include gender. For Goal #3: A recommendation letter with observation from both music instructor and staff on the Project leader's behavior will be used as readiness for Project leader to become music instructor next year.
prgmform: last updated, 06/26/2012 (pjh)