## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To provide 40 students of C.E. San Juan with music classes which last the duration of the school year. | 1. Purchase keyboard, stringed and percussion instruments. 2. Hire music instructor as a volunteer position. 3. Audition students in school. 4. Offer classes on each instrument, twice weekly for 5 months. 5. Finish the project with a final exam. | June 2, 2014 to November 10, 2014 | 40 students of C.E. San Juan. | 1. Increase access to music classes for 40 students of C.E. San Juan. 2. Increase in knowledge related to music performance and theory in 40 students of C.E. San Juan. 3. Use of attendance sheet for each class and performance. 4. Final examination on student’s ability to properly perform chromatic scale, rhythms and notes on chosen instrument. 5. Receipts from purchase of instruments. | 1. Increase in knowledge will be shown in comparison of abilities at beginning, middle and end of project. This will be measured by guitar instructor, PCV and music instructor. 2. Attendance to show increase in access taken by project leader, Julio Hernandez. 3. Receipts held and organized by CDE treasurer.
To provide one music instructor with sufficient abilities in teaching the clarinet. | 1. Test abilities of school teacher to play clarinet. 2. Provide regular clarinet lessons twice weekly for five months. 3. Provide final examination on ability to not only play but teach clarinet skills. 4. Suggest to project leader, Julio Hernandez, that the teacher shows sufficient ability to play clarinet. | June 2014 to November 2014 | One teacher of C.E. Canton San Juan. | 1. Increase access to clarinet lessons for one teacher of C.E. San Juan. 2. Increase knowledge related to clarinet theory and performance. 3. Increase in ability of teacher to perform proper chromatic scale, rhythms and notes on clarinet. 4. Increase in ability of teacher to articulate lessons on the clarinet in notes, rhythms and scales. | 1. Increase in access to clarinet lessons for the teacher will be shown by an attendance sheet and practice hours signed by teacher and PCV. 2. The teacher will show increased skills by successfully performing the chromatic scale, basic rhythms and notes during a final examination. 3. A letter of recommendation will be provided to the project leader from the PCV upon completion of lessons.
Prepare the 40 music students of C.E. San Juan for the performances in the music festival and Independence Day parades. | 1. Provide music lessons twice weekly for 3 months prior to Independence Day parade and two months prior to music festival. 2. Provide students with opportunity for practice during recess and before and after school with open instrument use time. | June 2014to September 15, 2014. September 16, 2014 to November 2014. | 40 Students of C.E. San Juan. | 1. Increase in knowledge related to instrument of choice in 40 students of C.E. San Juan. 2. Increase in access to practice hours for 40 students of C.E. Canton San Juan. 3. Increase in hours of practice among 40 students of C.E. Canton San Juan. | 1. Increase in knowledge will be shown by the student’s ability to perform in the music festival and the Independence Day parade this will be measured by a test on the songs by music instructors and PCV. 2. Attendance will be taken during each class by project leader. 3. Practice hours will be written down by each student, signed by student and parent and turned into the project leader.
To prepare funds in order to hire one full time music instructor for percussion and keyboard classes twice weekly for the duration of the following school year. | 1. Movie night fundraiser. 2. Music festival food sales. 3. Raffel. 4. Soccer tournament. | July, September, October, November 2014. | One music instructor for C.E. San Juan. 40 students of C.E. San Juan. | 1. Increase in income from $0/month to $100/month among one music instructor. 2. Increase access to fulltime music instructor among 40 students in C.E. Canton San Juan. 3. Raise enough money to fund the full time music instructor for the following school year through four fund raising events. | 4. The Project leader and treasurer of the C.D.E. will keep receipts and information on funds raised. 2. The C.D.E., teachers, students and PCV will keep a thermometer showing how much money has been raised for new teacher in school allowing transparency in the project’s fund raising. 3. The student government will pick the movies for movie night. 4. The C.D.E. will release funds as stimulus money for fund raising events. 5. Project leader will organize roster for soccer tournament. 6. Music instructors and PCV will organize performances for music festival. 7. Project leader will organize raffle tickets; C.D.E. will authorize release of funds for raffle purchase. 8. Students, parents and community members will provide labor at these fund raising events.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
For goal #1 receipts will be kept by the treasurer of the C.D.E. on the instruments that were purchased for the school’s band. An attendance sheet will be kept on each practice and performance by the project leader. Examinations on the skill level of the students will be carried out by the two music instructors and the PCV at the beginning and end of classes. This test will include information on the chromatic scale, rhythms and notes of each instrument. For goal #2 the practice sheet will be filled out by the teacher and signed by the PCV. The letter of recommendation will be written by the PCV and given to the project leader. The test will be carried out at the beginning, middle and end of classes by the PCV. It will include information on the teacher’s ability to perform the chromatic scale, notes and rhythms on the clarinet. It will also cover the instructor’s ability to teach the instrument to the students. For goal #3 the level of preparedness will be measured by a song test given by the instructors and the PCV for each student on each instrument. The practice logs will be filled out by each student and signed by their parent or the teacher in charge of open practice times. Attendance will be taken by the project leader for the performances and classes. Finally, goal #4 will include many different parties. The movie night will be run by the PCV, project leader and student government. The student government will pick movies shown and aid in preparing drinks and snacks. Finances will be documented by the project leader and C.D.E. For the raffle, the project leader and treasurer will purchase the items for raffle. The project leader will prepare the raffle tickets. The children will sell them. The C.D.E. will document the finances for this fund raiser. The soccer tournament roster will be covered by the project leader. The venue is provided by the community. Food and drinks will be prepared by the students, C.D.E. and parents. Financial gain will be documented by the C.D.E. The music festival performances will be prepared by the music instructors, students and PCV. The food sales will be prepared by the school teachers, project leader, parents and students. Finances will be documented by C.D.E. The thermometer showing progress in fundraising will be prepared my PCV and project leader.
prgmform: last updated, 06/26/2012 (pjh)