## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Solar ovens -- 12 youth will have built low-cost solar ovens made of locally available materials, and have demonstrated the use of solar ovens to the wider community | Organize Brigada Verde solar oven building day and demonstration day | 2013-07-01 | 12 Brigada Verde youth and their families | Knowledge -- Increase in knowledge related to solar ovens among 12 Brigada Verde youth and their families. Behavior -- 12 Brigada Verde youth and their families will use solar ovens to prepare food, decreasing dependency on wood-burning stoves and expensive natural gas. | Pre- and post- test and survey. PCVs and Brigada Verde leadership.
Environmental Art -- 12 Brigada Verde youth will complete recycled-materials art projects to educate themselves and their community about reducing, reusing and recycling inorganic waste. | During normal meeting times Brigada Verde youth will create art pieces focusing on the importance of the three Rs. | May - Dec / 2013 | 12 Brigada Verde youth, their families and community members who view art pieces | Access -- Increase in access of art resources and art education for 12 Brigada Verde youth. Knowledge -- Increase in knowledge of environmental themes, especially the three Rs, among 12 Brigada Verde youth, the student body of the local school (186 students), and the wider community (560 people). | Observation/evaluation of both art-making process and resulting art pieces. PCVs, school officials, and neighborhood association president.
Map Mural --Brigada Verde and other youth will paint a world map mural with environmental themes at local K-12 school | Organize and produce a map mural at local school with 12 Brigada Verde youth plus 10 other interested youth | 2013-08-01 | 12 Brigada Verde youth, Student body, community at large | Completion of Map Mural by Brigada Verde and other interested youth. Access -- increase in access to geographical and environmental knowledge among student body | Pre- and post- test for Brigada Verde youth. PCVs. Informal geography quizzes for student body. PCVs.
School and home gardens -- 15 Brigada Verde and other youth will participate in the expansion of the school garden to 1,800 square feet. Fifteen youth will create home gardens on family plots | Hold 2 garden participation activities per week to develop school garden. Provide tools and education to support development of home gardens. | By December / 2013 | 15 Brigada Verde and other youth and their families, the student body. | Development of productive, well maintained 1,800 square foot school garden. Creation of fifteen home gardens. Access -- at least 15 families will have increased access to nutritious, organic produce. | Measurement of square footage of productive space, yield and quality of produce. PCVs and Brigada Verde leadership. Home visits to evaluate home gardens. PCV and Brigada Verde leadership.
Garden income generation -- the Brigada Verde will raise $10 per week selling basil to the Cabarete Coffee Company. | Sow, cultivate, protect and harvest successive plantings of basil | June-Dec / 2013 | 15 Brigada Verde and other youth | Income -- Increase the Brigada Verde youth group's income from $0/week to $10/week. The youth will decide how to spend the money. | Recording of sales each week. PCV and Brigada Verde treasurer.
Bioregional field trips -- Through day-long field trips to key local ecosystems, 12 Brigada Verde youth will increase their knowledge of their bioregion and their awareness of environmental issues, focusing on connections between mountain and marine ecosystems on the north coast of the Dominican Republic. | Organize 3 field trips to area nature reserves (Loma Guaconejo Scientific Reserve, Laguna Dudu, and El Choco National Park). Discuss environmental issues and ecosystem connectivity in each setting. | May-Sept / 2013 | 12 Brigada Verde youth | Access -- Increase access to local sites of environmental interest and trained Dominican nature guides among 12 BV youth. Knowledge -- Increase bioregional awareness among BV youth, their friends and families. Increased environmental sensitivity and stewardship among BV youth and those influenced by them. | Pre- and post- test to check for knowledge. PCVs.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The principal tool to measure the success of the project will be a pre- and post- test that will record changes in knowledge over time. The test will include topics such as the three Rs, energy-saving cooking methods, environmental geography, and bioregional information pertaining to the areas where we plan to make field trips. It will also check for knowledge related to organic gardening. In addition, elected Brigada Verde leaders and the PCVs will make home visits and survey both home gardens (size of garden, quantity and quality of produce) and the solar ovens (frequency of use, user satisfaction, what kinds of food cooked). The completion of actual tangible products will be measured in quantity and evaluated in quality by the PCVs, the Brigada Verde youth, and community leaders. This includes the number and quality of art pieces created and solar ovens produced; the quality and effect on knowledge of the environmentally-themed world map mural; the size of the school garden and the quantity and quality of produce yielded; and the sales of produce. Each BV member will be required to present three lectures before their gradution from "level two" of Brigada Verde education. We will note changes in the BV youth's confidence, public speaking skills and leadership ability -- because fostering environmental multipliers is the ultimate goal of this project and that of the Brigada Verde.
prgmform: last updated, 06/26/2012 (pjh)