## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Empower women and hire male youth and generate income for self support | Constuct four boats to be owned in a joint partnership of three people. 3 boats for women and one for male youth. | 2014-08-14 | 9 women- age 24 + 15 male youth age 5 20-24, | Increase in Income from 0 ksh to to a minimum of 1,000 ksh per week. Measured through weekly meetings and construction monitoring | Through record keeping taught by PCV
Reduction of HIV AIDS throughout the Lake Victoria Region | Selecting 3 male youth to take part in boat ownership and hiring 12 male youth as fisherman for the No Sex For Fish boats | 2014-06-14 | 15 male youth 10 age 24+ and 5 age 20-24 | Increase knowledge and behavior change among the male population within this beach community. Changing mindsets of young men throughout the lake | Meeting with newly appointed youth with PCV and VIRED, with minutes taken . Documented within new VRF( Volunteer Reporting Form) reporting with Peace Corps
Reduction of HIV AIDS throughout the Lake Victoria Region | Meeting with selected male youth boat owners and other fisherman within Kusa Beach area | 2014-07-01 | 25 male youth 15 age 24-35, and 10 age 20-24, | Increase knowledge of HIV/AIDS prevention around the Lake and explaining the problems with "Jaboya" as related to HIV/AIDS | Suvey at the start for knowledge before meeting and at the end for gained insight. PCV, health partner and Counterpart and VIRED. Also documented in the Peace Corps VRF reporting
Reduction of HIV AIDS throughout the Lake Victoria Region | VCT setups four times annually at Kusa Beach | 2014-08-14 | 50 to 100 people from Kusa Beach and surrounding beach areas. 60-65% of men and 35-40% of women will be the ration | Increased knowledge of HIV/AIDS prevention due to VCT consultations and continuous visits 4 times annually | Record keeping by VCT professionals. Utilizing such organizations such as WOFAK( Women Fighting Aids in Kenya)
Ensure more of a food supply for families | Construction of four boats in Kusa Beach | 2014-08-14 | 9 women- age 24 and older, 15 male youth age 5 20-24, and 10 24 and older, along with fish traders who buy at Kusa will have more fish available | Increased Access to local nutritious fish because of added boats to the beach | Bookkeeping previously taught by PCV and revenues collected by the BMU treasury as to the fish that is brought in.
Communicate with Community Members about the No Sex For Fish Expansion to Kusa Beach. Which would include the nomination and selection process of vulnerable women and upstanding youth | Local Barazas( meetings) with fisherman, Beach Management Unit, local Chief and fish traders | 2014-06-14 | 4 BMU members, 2 Chief council, approx 50 fishtraders and 25 fisherman which includes male youth | Increased knowledge of the No Sex For Fish Expansion Project | To be held by PCV and counterpart and include a sign-in sheet. Also documented in the Peace Corps VRF reporting
To increase knowledge in basic business skills. To happen 3 x annually. | To teach bookkeeping, budgeting, money mangement, Effective Communication and managing employees | July2014 thru Dec 2014 | No Sex For Fish beneficiaries- 9 women and 3 male youth | Increase knowledge with money matters and how to budget money using a record keeping system. Meetings to happen three times a year with follow-up at weekly meetings. | PCV will set up each member with a book of record and instruction. PC/VRF reporting
To bring together all members of No Sex For Fish to meet, to discuss successes, challenges and looking ahead to the future | To host a workshop for all current No Sex For Fish members and the newly appointed members from Kusa Beach. To include BMUs ( Beach Management) representatives and their local respective Chiefs | 2014-07-01 | 28 women and 20 men | To continue a sense of team work, encourage open communication and to learn from others mistakes and successes | PCV, counterpart, VIRED Director General and staff will facilitate and plan. Monitor through Registration and feedback survey. Also to include Peace Corps VRF reporting
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The Peace Corps Volunteer, her Counterpart and completely overseen by Director General of VIRED International, Professor J.B. Okeyo, the No Sex For Fish Expansion will be monitored from start to finish. From the nomination of the potential boat owners, to the final selection of the No Sex For Fish beneficiaries, to the monitoring of the boat building and to meeting with community members and the NSFF members, the project will be completed on time. The Scope ( what you need to get done and within what timeframe) is the driving force of any project. Planning out your work within that time frame is key and can only be met with a schedule. An agreed upon weekly meeting with NSFF memebers, day and time, will ensure open and constant communication between all parties.This weekly meeting will occur even after the project has ended to make sure it is being sustained. All meetings and workshops will be documented through minutes, surveys and questionaires. Another day will be dedicated to the boat builder to access his progress and survey any needs. A budget for staying within your financial means will also be necessary to ensure completion with our means. Lastly, and sometimes overlooked will be team satisfaction and teamwork within the organization and among all No Sex For Fish members. The Peace Corps Volunteer and her Counterpart will be available to all team members to resolve conflicts, address any issues or problems and be a means of support throughout the project to make sure the project is completed successfully.
prgmform: last updated, 06/26/2012 (pjh)