## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Establish a physical presence in the Brasilito community with an office and Resident Staff by July 1, 2014. | 1. Contract volunteer teaching staff and have them live in the community by or before July 1, 2014. 2. Search community for a viable office to rent by June 15, 2014 and move into office on July 1,2014. 3. | 2014-07-01 | 6 staff members/volunteers as well as members of the community. 30 Females 14 and younger, 20 females between the ages of 15-24, 30 females over the age of 25, 35 males 14 and younger, 20 males between the ages of 15 - 24, and 20 males over the age of 25 | Increase access to more educational opportunities among community of 800 people | Peace Corps Volunteer and Community Project leader will both be in charge of finding a permanent office in the community, while the Community project leader will be in charge of hiring and training all staff and volunteers and securing accomodations.
By August 1, 2014 offer three hours of English education per day, doubling the current offering, and add computer classes to the Casa Brasilito program. | 1. Train staff to execute English and computer classes 2. Publicize classes to the community | 2014-08-01 | 30 Females 14 and younger, 20 females between the ages of 15-24, 30 females over the age of 25, 35 males 14 and younger, 20 males between the ages of 15 - 24, and 20 males over the age of 25 | Increase access to English and computer education to a minimum of 150 community residents, so that there is an increase in knowledge amongst the marganilized at-risk population, current baseline is 75 participants where students receive 45 minutes of ESL education 3 times per week. | The Project Leader and Abriendo Mentes' team will track classroom hours each month, as well as monthly attendance. These metrics will be compared to 2013 data in order to illustrate a growth in program hours as well as attendance.
By August 1, 2014 extend the programming to increase weekly extracurricular activities related to sports and the arts so that the community has access to a more well-rounded educational and youth development program. | 1. Staff must be contracted 2. Programming must be established by July 20, 2014 and publicized to the community. | 2014-08-01 | 30 Females 14 and younger, 20 females between the ages of 15-24, 30 females over the age of 25, 35 males 14 and younger, 20 males between the ages of 15 - 24, and 20 males over the age of 25 | Increase access to extracurricular activities related to sports and the arts to a minimum of 90 youth students. Current baseline is 50 students who participate in 1 hour per week of extracurricular programming. | The Project Leader and Abriendo Mentes' team will track program hours each month, as well as monthly attendance. These metrics will be compared to 2013 data in order to illustrate a growth in program hours as well as attendance.
To increase knowledge of Abriendo Mentes as an organization in the community of Brasilito | 1. Create marketing materials and post them throughout town 2. Connect with local leaders 3. Strengthen partnship with local school 4. Network in local community | 2014-10-01 | 800 community members | Increased knowledge of Abriendo Mentes programming amongst 800 residents of Brasilito | The Project Leader and staff will do random community surveying in September of 2014 to assess the community's knowledge and awareness of Abriendo Mentes
To provide a high-quality educational program to a minimum of 150 community members, helping them gain necessary life skills and improving their chances of pursuing higher education and/or employment. | 1. On a consistent basis, grassroots marketing must take place in order to fully imform the community of the available educational opportunities. 2 Assessments tests will be administered in order to track improvement | 2014-10-01 | 30 Females 14 and younger, 20 females between the ages of 15-24, 30 females over the age of 25, 35 males 14 and younger, 20 males between the ages of 15 - 24, and 20 males over the age of 25 | Increase Knowledge related to English language and computer skills amongst a minimum of 150 community members and an increased interest in pursuing higher/more education and/or employment involving the two skills. | The Abriendo Mentes staff members will be in charge of documenting attendance, which will be analyzed each month with other important program metrics. Assessment tests will be administered to establish a basline for each student and tests will be administered every 6 months to track progress and improvement. Follow up with students will also be completed by the Director of Casa Brasilito by interviewing random students and administering surveys.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
We will be monitoring our success based off attendance, student performance, and community feed-back --- Before every class, attendance will be taken so that we can keep track of who is attending the classes. This attendance list can also help us see if only a certain part of the community population is attending classes so as to give us possible guidance on which marginalized populations still need to be reached.--- Student performance will also be a huge indicator of success since the entire project is focused on education. Via tests and keeping in contact with members, we will be able to evaluate our program and determine if what we are teaching is useful to the community.--- Probably the most important analyzing tool that will measure project success will be the community feed-back. By talking with the community and interviewing them on how the feel about the program and hearing what was useful or not, the Casa Brasilito will be able to have an ever-evolving educational program fulfilling the needs of the community.--- For all of these monitoring efforts, the entire Casa Brasilito staff will be involved, with the Director of Casa Brasilito eventually compiling all the feedback for the current project leader in order to be fully evaluated.
prgmform: last updated, 06/26/2012 (pjh)