## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Low-income women will adopt healthy behaviors and practices that contribute to improved family health outcomes | Promote the health benefits of using improved cook stoves through building of sample stoves in El Carmen and Mateo Pico, Formation of a Stove Committee in each of the Two Communities, Water Boiling Test on Improved Cook Stove to show the efficiency of the Cook Stove compared to wooden cookstove | Formation of Stove Committee and building of the sample stove with water boiling test- June 2014 | 45 women over the age of 24 | Knowledge: The number of individuals trained on the health benefits of using improved cook stoves | Peace Corps Volunteer, Project Leader, Attendance Sheets, Pre and Post Tests
| Beneficiaries will be required to sign a contract showing their commitment to education (Stove Committee meetings-- around 3-4 workshops) and in-kind donations of materials and services in order to begin construction of Improved Cook Stove. Once beneficiaries have completed all the requirements on the contract, construction of stoves will begin. | 3-4 Workshop on how benefits and maintenance of Cookstove July 2014; Time frame of construction will span 4 months depending on mason schedule and beneficiares' abilities to complete its commitments- July 2014-November 2014 | 40 households, 123 expected total direct beneficiaries: 45 women over the age of 24, 2 women between ages of 18-24, 50 youth between ages of 6-18, 26 children under the age of 5 | Access: Number of cookstoves (new or rehabilitated) purchased or constructed for households or institutions (health clinics, schools) with assistance of Volunteers or partners | Peace Corps Volunteer, Completed Contracts of Beneficiaries
| Continual Assistance of all Stove Workshops and Healthy Homes meetings of all Beneficiaries; During Health Promoter or Peace Corps Volunteer home visits, beneficiaries will demonstrate their knowledge and proper use of the Improved Cook Stove and will fill out a survey about their Improved Cookstove Usage | Once beneficiares have received their stoves, Health Promoters and Peace Corps Volunteer may visit to assess behavior change of beneficiaries from October 2014- December 2014 | 45 women over the age of 24, | Behavior: Households using a properly maintained improved cookstoves and number of households having a properly maintained cookstove that is a being used for at least 90% of the time | Peace Corps Volunteer/ Health Promoters, Attendance Sheets, Home Visits with Survey filled out by promoter/PCV and the beneficiaries
| Beneficiaries will be required to take a test on best practices of Improved Cookstove at the beginning to Stove Committee training. The same test will be given after the training to assess on beneficiares' improvement of knowledge | However the pre-test will be given before the first stove committee workshop in July 2014. Once beneficiares have attended all the trainings, beneficiaries will be tested again on the benefits of the improved cook stoves- August 2014. Health Promoters and Peace Corps Volunteer may visit to assess behavior change of beneficiaries after receiving the stoves: October 2014- December 2014. | 45 women over the age of 24 | Knowledge: Showed Improvement in Knowledge of Benefits of Using improved cookstoves-- number of individuals able to identify at least 2 benefits of an improved cookstove | Peace Corps Volunteer, Pre and Post Test of Beneficiaries
| During Peace Corps Volunteer or Health Promoter home visits, beneficiaries will fill out a survey about satisfaction and usage of the improved cookstove. | By November 2014, all construction of stoves should be completed and from November 2014-December 2014, beneficiares will complete the survey on the benefits of using the improved cook stove. | 40 households, 123 expected total direct beneficiaries: 45 women over the age of 24, 2 women between ages of 18-24, 50 youth between ages of 6-18, 26 children under the age of 5 | Access: Individuals benefitting from a new or rehabilitated cookstove- number of individuals living in households benefitting from new or rehabilitated cookstoves | Peace Corps Volunteer/ Health Promoters-- Survey of Beneficiaries on Usage and Satisfaction Level of Improved Cook Stove (in comparison to their old wooden cookstoves), Home Visits
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Baseline: Peace Corps volunteer, Community Health Promoters, and Project Leader analyzes data from Community Diagnostic of 131 households in El Carmen and Mateo Pico to identify 40 households that primarily rely on traditional cook stoves to feed their families and have children under the age of 5. The Community Diagnostic for El Carmen and Mateo Pico which included a census of both communities and an in depth interview on issues regarding health was done and completed by the Peace Corps Volunteer from November 2013-January 2014. The Peace Corps Volunteer and Community Organizations' health promoters also live in a the community and are aware of the most vulnerable families in their community. Midline: Invite the 40 participating families to attend educational classes on the improved cook stoves and propose the project in a manner that makes clear that the Improved Cook Stove project is a community project and commitment. The Project Leader and Peace Corps volunteer will make clear that without completing all the aspects of the contract, construction of the Improved Cookstove will not begin. This is to ensure dedication to the project and allow for participating families to take more ownership of their stove. Peace Corps Volunteer and Health Promoters will be responsible for keeping track of attendance of participating families. Peace Corps Volunteer will be responsible for conducting the Pre-Test regarding the benefits and proper usage of an Improved Cook Stove. Final: Improved cook stove committee composed of the most enthusiastic improved cookstove recipients, health promoters or the Peace Corps volunteers will visit, observe, and conduct a survey and post-test of the forty recipient households to ensure they are using the new cook stoves correctly and understand the benefits of the improved cook stoves. The first couple visits will be done by the Peace Corps Volunteer to collect data but also to train certain Stove Committee members of how to conduct a final visit to monitor the correct usage of an Improved Cookstove. After the Peace Corps Volunteer has trained Stove Committee members and Health Promoters as to how to conduct home visits on the stoves, they will be able to report all the data from the surveys back to the Peace Corps Volunteer who will be able to compile all the data electronically from all the home visits surveys, and post-test.
prgmform: last updated, 06/26/2012 (pjh)