## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
By September 2014, 10 households will corrently and consistently use and maintain the bathrooms constructed in their houses | 1. Hold a training on correct use and maintenance of the bathrooms. 2. Have a skilled mason construct the bathroom 3. A minimum of 4 house visits after bathroom construction is complete. | June-September of 2014 | The 10 selected families who will receive bathrooms | 1. # of individuals with increased knowledge of the maintenance of the basic bathrooms installed 2. # of families with increased access to bathrooms 3. # of individuals properly using and mai\ntaining their bathrooms | 1. Attendance sheets and pre and post-assessment test given at the beginning and end of the trainings. Secretary of Development Committee will be responsible. 2. Evaluation sheet filled out at house visits. PCV will be responsible.
By September 2014, 40 household members will correctly and consistently wash their hands with soap at a hand washing stationg at the critical times. | 1. Hold a training on proper handwashing technique, critical handwashing times, and how to construct a handwashing station. 2. Requirement of the installation of a handwashing station in the house before bathroom construction. 3. Check for behavior change and retained knowledge during post-construction house visits. | May-September of 2014 | The 10 selected families who participate in the trainings, especially the children who are most susceptible to diarrheal diseases. | 1. # of individuals with increased knowledge in the critical times for hand washing 2. # of households with increased access to soap, safe water, and a handwashing station for proper hand washing 3. # of individuals with increased frequency of washing their hands with soap | 1. Attendance sheets and pre and post-assessment test given at the beginning and end of the trainings. Secretary of Development Committee will be responsible. 2. Evaluation sheet filled out at house visits. PCV will be responsible.
By September 2014, 10 household members will possess the skills and knowledge to safely treat and store water for household use | 1. Hold a training on water treatment options and safe water storage practices. 2. Requirement of proper storage containers in the house and a chosen method of treatment before bathroom construction. 3. Check for behavior change and retained knowledge during post-construction house visits. | May-September of 2014 | The 10 selected families who participate in the trainings, especially the children who are most susceptible to diarrheal diseases. | 1. # of mothers with increased knowledge in using treated and properly stored drinking/cooking water 2. # of mothers with increased knowledge of the characteristics of a safe water storage vessel and at least 3 ways to purify water 3. # of mothers with increased practice of safe water treatment and storage | 1. Attendance sheets and pre and post-assessment test given at the beginning and end of the trainings. Secretary of Development Committee will be responsible. 2. Evaluation sheet filled out at house visits. PCV will be responsible.
By September 2014, 10 households will properly store and dispose of trash | 1. Hold a training on how to properly dispose of trash and recycling options. 2. Requirement of proof of proper trash disposal before bathroom construction. 3. Check for behavior change and retained knowledge during post-construction house visits. | May-September of 2014 | The 10 selected families who participate in the trainings as well as the rest of the community, who also inhales the toxins released by burning trash. | 1. # of mothers with increased knowledge of the imprtance of proper trash disposal 2. # of families with increased access to proper storage and disposal of trash through municipal collection and/or mini landfill | 1. Attendance sheets and pre and post-assessment test given at the beginning and end of the trainings. Secretary of Development Committee will be responsible. 2. Evaluation sheet filled out at house visits. PCV will be responsible.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
There will be a minimum of 4 monitoring visits to ensure that the bathrooms are operating correctly and that the families are properly using and maintaining them. During these visits, the families will be asked to demonstrate how they have applied what they have learned in the trainings; for example, they will show the handwashing stationg that they have constructed and the proper storage and treatment of water. Peace Corps provides volunteers with tools to monitor this progress. These evaluation forms will be filled out by the PCV at each visit to track progress and continued proof of behavior change. In addition, the local project leader will be charged with enforcing these bahaviors when the PCV is not there and once she has left Peru.
prgmform: last updated, 06/26/2012 (pjh)