## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
By April 2014, 50 low income mothers will adopt evidence based practices to safeguard the health of their children in the form of the adoption of improved efficiency cookstoves. | 1. To construct 50 improved cook stoves to families. 2. Provide 3 mandatory educational workshops on the care and importance of the improved cook stoves. | May 2013-November 2013 | 50 low income mothers living in La Lometa/Las Canitas. 100 children living in these housholds | 1. Increased access to the improved cook stoves among 50 low income women. 2. Increased skill on the maintenance of improved cookstoves among 50 low income women. | Assessments of progress will be made through observation before, during, and after the community presentations. House visits will be made before, during, and after the improved cookstove construction. Progress will be noted weekly. Healthy Homes Group and Volunteer will be responsible
By April 2014, 50 women will be able to demonstrate increased knowledge of the environmental effects of deforestation in the Dominican Republic | 1. To provide 50 women with an educational workshop on the deforestation in the Dominican Republic | May 2013-August 2013 | 50 low income mothers living in La Lometa/Las Canitas | 1. Increased knowledge on the environmental effects of deforestation in the Dominican Republic among 50 community members. 2. Decrease in the use of logs in their cook stoves among 50 women. | Pre/Post test before and after the community presentations. An oral exam will be the data collection tool. Healthy Homes Group and Volunteer will be responsible
By April 2014, 50 women will demonstrate increased knowledge of the damage of inhaled smoke. | 1. To provide 50 women with an educational workshop on the risk of inhaled smoke. | May 2013-August 2013 | 50 low income mothers living in La Lometa/Las Canitas. 50 children living in these housholds | 1. Individuals trained on the risk of inhaled smoke among 50 women 2. Decreased respiratory illnessess among 50 children. | Pre/Post test before and after the community presentations. An oral exam will be the data collection tool. Healthy Homes Group and Volunteer will be responsible
By April 2014, 5 women will be trained to give presentations on the care of and benefits of the improved cook stove model. | 1. To provide 5 women a workshop on how to give presentations. | 2013-05-01 | 5 low income women 24 and older living in La Lometa/Las Canitas. 100 community members they will give presentations to. | Increased knowledge on how to give presentations in the community on the care benefits of improved cook stoves among 5 women. | Assessments of progress will be made through observation before, during, and after the training. An oral exam will be given. Volunteer will be responsible.
By April 2015, 5 masons will be competent in the construction of the improved cook stoves. | 1. To provide hands on workshops to 5 masons in the construction of the improved cook stoves. | May 2013-November 2013 | 5 low-income masons in La Lometa/Las Canitas. 50 low income families who will receive the improved cook stoves. | Increased knowledge of the construction of the improved cook stoves among 5 masons. | Assessment of progress weekly through observation and written in a notebook. Volunteer will be responsible.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
To monitor and measure the project's success, we are going to create a baseline during the first encounters. The Healthy Homes Group and the volunteer will do home visits and interviews at the project start. This information will be kept in a notebook. At the 3 mandatory workshops, attendance will be taken and progress noted with each participant. An oral exam will be given before and after each workshop to each participant and progress noted. The masons and community presenters will be monitored through observation, demonstration, and oral exam by the volunteer with each workshop and stove construction. After construction is complete, the Healthy Homes Group and the volunteer will make home visits to assess use of the improved cook stoves as well as provide follow up teaching. The respiratory illnesses in children will be assessed in a survey at the project start interview and at the follow up visit.
prgmform: last updated, 06/26/2012 (pjh)