## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Raise funds in order to fix up one room designated for use as the computer lab during the first three months of the project. | 1. Soccer tournaments | November 2014, December 2014, January 2015 | 69 youth of Santa Inés | 1. Increase in access to funds in order to fix up room designated for use as the computer lab among 12 members of the CDE. | 1. Increase in access to funds will be shown by comparing the amount of funds available during the beginning, middle, and end of time fundraising. 2. The Project Leader and treasurer of the CDE will keep receipts and records of information on funds raised toward the project. 3. Information regarding the fundraising and progress made will be publicized and discussed at CDE meetings and with parents in the community at general meetings at the school, making sure that the fundraising process is transparent. 4. Teachers at the school will invite teams from other communities and organize soccer tournaments. 5. Teachers, students, parents, and community members will provide labor at tournaments (setting up and preparing the field, selling drinks, cooking and selling hamburgers and pupusas, refereeing games and keeping score, clean up, etc.).
Prepare and set up one room designated for use as the computer lab during the first three months of the project. | 1. Repair ceiling 2. Clean out and organize room 3. Purchase six tables and 25 chairs 4. Purchase 25 computers 5. Set up tables, chairs, and computers 6. Install antivirus and additional programs | November 2014, December 2014, January 2015 | 69 youth of Santa Inés | 1. Increase in access to a space that can be utilized for computer education among 69 youth and children in Santa Inés. | 1. CDE will be in charge of distributing funds for use in setting up the room. 2. Project Leader and CDE treasurer will keep receipts and records of all purchases. 3. Records of purchases will be publicized at CDE meetings and at general meetings at the school for parents in the community. 4. Progress will be monitored during beginning, middle, and end of room setup by CDE, Project Leader, and PCV. 5. A check list will be kept with various materials and tasks by Project Leader. 6. Teachers, students, and PCV will provide labor in room set-up.
Provide 69 youth of Santa Inés with computer classes throughout the school year, beginning in January. | 1. Offer computer classes one hour daily (Monday-Friday) starting at the beginning of the school year. | January 2015, February 2015, March 2015 | 69 youth of Santa Inés | 1. Increase in knowledge related to computer use among 69 youth and children in Santa Inés. 2. Increase in access to computer education among 69 youth of Santa Inés. | 1. Increase in knowledge will be shown by comparing computer abilities at the beginning, middle, and end of the project. This will be measured by the computer instructor and PCV. 2. Increase in access will be measured through attendance being taken by the computer instructor. 3. A questionnaire and pre-test will be given by the computer instructor at the start of classes to assess current knowledge and abilities. 4. Opportunities to demonstrate learned abilities and exams will be given by the computer instructor during the duration and at the end of classes to display knowledge gained.
Provide one qualified computer instructor able to teach computer classes throughout the school year. | 1. School director is taking a weekly computer course, and will continue to do so for three years, in order to be competent to teach computer classes. 2. Jointly teach and model computer classes for the first three months of the school year. | January 2015, February 2015, March 2015 | One teacher from the school in Santa Inés, 69 youth of Santa Inés | 1. Increase in knowledge related to computer usage and various programs for one teacher in Santa Inés. 2. Increase in access to computer lessons for one teacher in Santa Inés. 3. Increase in ability to utilize the computer and its various programs among one teacher in Santa Inés. 4. Increase in ability and confidence to articulate lessons on the computer and various computer programs among one teacher in Santa Inés. | 1. Increase in knowledge will be shown by comparing computer abilities at the beginning, middle, and end of classes. 2. Increase in access will be shown by the school director's enrollment in and attendance of the computer classes. 3. Increase in ability and confidence to articulate computer lessons will be assessed through observation by the PCV and constant communication between director and PCV.
Capacitate four teachers with basic computer skills and knowledge of basic computer maintenance during the first three months of the school year. | 1. Have teachers demonstrate what they already know about the computer and computer maintenance. 2. Based on what they already know, provide regular lessons once a week and demonstrate computer maintenance during the first three months of the school year. 3. Have teachers demonstrate their acquired computer skills and computer maintenance abilities. | January 2015, February 2015, March 2015 | Four teachers from the school in Santa Inés, 69 youth of Santa Inés | 1. Increase in knowledge related to the computer and computer maintenance among four teachers in Santa Inés. 2. Increase in access to basic computer and computer maintenance lessons among four teaches in Santa Inés. 3. Increase in ability and confidence to utilize and to take care of and maintain computers among four teachers in Santa Inés. | 1. Increase in knowledge will be shown by comparing what teachers know about computer use and computer maintenance at the beginning, middle, and end of computer and computer maintenance lessons. 2. PCV will give questionnaires at the beginning , during, and at the end of lessons to measure knowledge gained. 3. Increase in access will be shown by the PCV keeping an attendance sheet of teachers participating in each lesson. 4. Increase in ability and confidence to use and take care of and maintain computers will be measured through observation by PCV, teachers demonstrating what they have learned, and constant communication between teachers and PCV.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
For the first goal soccer tournaments will be held to raise funds for use in fixing up and setting up the room that has been designated for use as a computer lab. Teachers from the school will organize the tournament and invite teams from other communities. Tasks for the tournament will be divided amongst teachers, students, parents, and community members who will all work together, whether it be preparing and setting up the field, refereeing and keeping score, cooking and selling hamburgers and pupusas, selling drinks, selling other snacks, or clean up. The Project Leader and CDE treasurer will keep all receipts and records of information on the funds raised for the project. They will oversee a monthly budget. Information on the fundraising and progress being made will be publicized at CDE meetings and at general meetings for parents in the community held at the school and open to anyone who would wish to attend. Progress will be measured through comparing the amount of funds available at the beginning, during, and at the end of the time fundraising. For the second goal of preparing and setting up the room for the computer lab the CDE will be in charge of distributing funds. All receipts and records of purchases will be kept by the CDE treasurer and project leader whom will also be keeping a monthly budget. Records of these purchases will be publicized at CDE meetings and general meetings held at the school for parents in the community. The project leader will keep a checklist of the various tasks and materials determined necessary for the setup of the room which will be consulted throughout the process. The teachers, students, and PCV will provide labor in room setup and progress will be monitored during the beginning, middle, and end of room setup by the CDE, Project Leader, and PCV. Once computer classes are offered for goal three, increase in knowledge will be monitored by the computer instructor and PCV whom will compare computer abilities at the beginning, during, and at the end of the project. A questionnaire and a pre-test will be given by the computer instructor at the beginning of the classes to assess current knowledge and abilities. Opportunities to demonstrate learned abilities and exams will be given by the computer instructor during the duration and at the end of the classes to display knowledge gained. The computer instructor will also measure increase in access through an attendance sheet. The fourth goal of providing a qualified computer instructor able to teach computer classes will involve the school director/Project Leader taking a computer course so that he will be competent in computers in order to give classes at the school. Professor Edwin Aguilar began this course on August 23, 2014. The increase in access to computer lessons will be shown by his enrollment in and attendance of these classes. Comparing computer abilities at the beginning, middle, and end of classes will demonstrate increase in knowledge. The PCV will model and jointly teach computer classes with the instructor for the first three months of the school year. Through observation by the PCV and constant communication between the computer instructor and PCV, ability and confidence to articulate computer lessons will be assessed. Finally, the fifth goal of capacitating four teachers with basic computer skills and knowledge of basic computer maintenance will comprise of providing regular lessons for the first three months of the school year. Knowledge gains will be measured by comparing what the teachers know about computer use and computer maintenance at the beginning, middle, and end of computer and computer maintenance lessons. The PCV will keep an attendance sheet of teachers participating in each lesson in order to measure increase in access. At the beginning, during, and at the end of the lessons the PCV will give questionnaires in order to gauge the increase in knowledge. The PCV, who will also be in consultation with the school director, will monitor the ability and confidence of the teachers to use and take care of and maintain computers through observation, teachers demonstrating what they have learned, and through constant communication between the teachers and PCV.
prgmform: last updated, 06/26/2012 (pjh)