## Project Plan Guidance - Table 1
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template - Table 1
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To create a small, sustainable sewing business as a source of income for 16 women in Caserío La Zuncuya by April 2015 | Consolidate group: train women in leadership and teamwork skills | Dec. 2015 | 9 women, 7 youth (female) | 100% of women trained will have acquired new knowledge and skills in teamwork, managing conflicts, and visioning for the future by January 2015 80% of women trained will be able to demonstrate at least one strategy learned through training by February 2015 | PCV: pre- & post-test, PC-ES leadership observational tool
| Acquire legal standing for women's group | Apr. 2015 |  | Group will acquire legal standing by April 2015 | PCV & Women’s group leadership: Legalization paperwork signed
| Train women in sewing women’s clothing | Mar. 2015 |  | 100% of women trained will acquire new technical skills (women's clothing) by April 2015 | Sewing Teacher: Progress reports and final grades
| Complete a business plan | Dec. 2015 |  | 80% of women will participate actively in the creation of a business plan for the group | PCV: observation
To strengthen the internal management capacities of 16 women in Caserío La Zuncuya in the first year of the project | Train women in business management | Jan. 2015 | 9 women, 7 youth (female) | 100% of women will have acquired new knowledge and skills in planning and managing a small business by January 2015 16 women provided quality business management and technical training in the first six months of project 80% of those trained will be able to identify and utilize at least one assessment and planning technique in order to create a new income-generating activity or enhance an existing one after training | PCV: interviews, observation, pre- & post- test, PC-ES Business tool
| Train women in managing finances | Feb. 2015 |  | 100% of participants will acquire knowledge in business best practices to increase efficiency by February 2015 | PCV: interviews, observation, pre- & post- test, PC-ES Business tool
| Complete cost analyses for products | Mar. 2015 |  | 100% of women will successfully complete a cost analysis for one product by February 2015 | PCV & women’s group: submission of checked cost analysis
To reduce economic vulnerability of 14 families in Caserío La Zuncuya during the first year of the project | Train women on how/why to save money | Jan. 2015 | 14 families, 73 people (32 women, 13 men, 14 boys, and 14 girls) | 100% of women will learn money saving skills after training 100% of women will learn new knowledge about the importance of saving money after training 100% of families will experience an increase in monthly income and/or savings in the first year of project 100% of participating families will express improvement in their quality of life after first year of project | PCV: interviews, surveys, observation, pre- & post- test
| Identify sources of credit in the region | Jan. 2015 |  | 100% of women will acquire new knowledge regarding financial services available to them after training | PCV: pre- & post-test
To facilitate linkages between women's small business and other businesses in El Salvador | Identify distributors and potential employers | Feb. 2015 | 9 women, 7 youth (female) | 100% of participating women will gain skills in establishing and maintaining business relationships after visits At least 2 distributors identified in the first year of project | PCV: PC-ES networking & advocacy tool, observation,interview
| Network with women’s groups in Morazan and/or San Miguel that sew uniforms and run small businesses | Apr./May 2015 |  | 80% of participating women will successfully identify successful business practices of other groups 80% of participating women will apply best practices to their own business | PCV: PC-ES networking & advocacy tool, observation
To facilitate networking between women’s group and governmental organizations/NGOs that support women | Have women complete and submit a workshop request to Ciudad Mujer or INSAFORP | Nov. 2015 | 9 women, 7 youth (female) | 2 women will successfully complete and submit an application by January 2015 to demonstrate knowledge of advocacy tools | PCV: PC-ES Networking & Advocacy tool Women’s group leadership: paperwork submitted
| Register women with Ciudad Mujer | Dec. 2014 |  | 100% of participants will visit and register with Ciudad Mujer, learning the opportunities available to them in working with the organization | PCV & Ciudad Mujer Representative: paperwork signed
| Identify sources of assistance nationally and internationally | Feb. 2015 |  | 100% of participants will be able to identify at least two sources of assistance to women they can utilize by April 2015 | PCV: interviews, observations, presentations
To strengthen marketing practices among entrepreneurs involved in sewing in Caserío La Zuncuya in the first year of the project | Train women in marketing/branding | Apr. 2015 | 9 women, 7 youth (female) | 100% of women who attended charlas will acquire new knowledge on marketing and branding | PCV: pre- & post-test
| Perform a market analysis | Jan. 2015 |  | 100% of women will apply marketing skills learned from charla | PCV: interviews, observation, PC-ES Business tool
| Publicize sewing business in the community | Apr. 2015 |  | 50% of women will be making clothing for community members within the first six months. | PCV: interviews, observation, survey, PC-ES Business tool
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Monitoring, Recording and Evaluation (MRE) tools created by Peace Corps El Salvador will allow me, through attendance rosters, observation, surveys and short conversations with participants, to analyze change over the course of the project in the areas of business development, networking and advocacy, leadership, and entrepreneurship. Gender analysis will also be employed to ensure accurate appraisal of the project and to gauge the improvement rendered in the human condition. I also plan to use appreciative inquiry to monitor and evaluate the the success of the proposed project. Appreciative inquiry is participatory tool that identifies assets and allows participants to build upon strengths through visioning and dialogue. Participants acknowledge what is working, what resources are already available through the project or in the community, and what assets are present for creating change. Through dialogue project participants will identify success and best practices to develop a positive, practical approach to change and improvement. It is an empowering tool that is easy to implement, that gives everyone a voice and that encourages creativity and positivity while addressing the needs of a project.
prgmform: last updated, 06/26/2012 (pjh)