## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Students grades K-9 will learn the importance of separating and recycling waste, and how to properly sort and store recyclables. | Educational presentations for kids in local school | December 2014-February 2015 | All students and teachers | Behavior/Knowledge. By April 2015, 528 students will understand the importance of recycling, and properly dispose of recyclable goods in their designated space in the school recycling center. | Each classroom will have separate bins for recyclables and non-recyclables. At the end of the day a student from each class will be responsible for transferring the recyclables to the storage center, and the teacher responsible will oversee this each day.
Parents of students will learn the importance of properly separating recyclables in the home and the benefit of depositing their recyclables at the school recycling center | Educational presentations for parents in local school | December 2014-February 2015 | All parents | Behavior/Knowledge. By April 2015, 150 parents who regularly attend school meetings will understand the importance of recycling and properly separate recyclable materials in the home, and deposit them in the school recycling center. | The CDE will be responsible for making announcements at every parent-teacher meeting, and their efforts will be measured by the amount of recyclables students bring from home to be deposited
All community members will learn the importance of properly separating and recycling waste, and how to properly sort and store recyclables. | Educational presentations for community members in local school | December 2014-February 2015 | All community members | Behavior/Knowledge. By April 2015, 200 community members who are neither parents nor students, will understand the importance of recycling and utilize the recycling center to dispose of materials. | The CDE will be responsible for community awareness regarding the use of the recycling center, and communtiy deposits will be evident.
The CDE and primary counterpart will use grant funds to purchase all needed project materials. | Buy materials necessary for murals and construction of recycling center | 2014-12-01 | Members of the CDE, Counterpart | By December 2015, all 13 CDE members plus my counterpart will have properly used allocated grant funds for materials purchase. | Primary counterpart and CDE Treasurer will hand in all receipts from materials purchase
Students and members of the Ecological Committee will help prepare the school for painting murals. | Prepare the school walls for mural painting | 2014-12-01 | Ecological Committee, other students | By December 2014, 30 students will have helped fully prepare the school walls to move forward will mural painting. | Primary counterpart and Peace Corps Volunteer will oversee work shifts and ensure full participation of Ecological Committee members
Local masons will build the recycling center in the time allocated. | Build recycling center at the local school | January-February 2015 | All community members | Access. By February 2015, the recycling shed will be fully constructed and ready for use. | The CDE, counterpart and Peace Corps Volunteer will coordinate with masons to create work timeline and schedule to ensure timely termination
The Ecological Committee and students will help paint murals around the school under the theme "environmental awareness" to encourage the recycling effort and beautify the school | Paint the murals | January-February 2015 | Ecological Committee, Counterpart, other students, community members | Knowledge. By February 2015, 30 students will use their knowledge about environmental consciousness to design and realize murals around the school. | The Ecological Committee, counterpart, and Peace Corps Volunteer
The community and school will celebrate the completion of the recycling center and bring attention to its new funtion | Hold a recycling center inauguration | 2015-03-01 | All community members | Access. By March 2015, all community members will be aware of the school-based recycling center and begin utilizing it. | The CDE, counterpart, Ecological Committee and Peace Corps Volunteer
The school will generate funds from the selling of recyclable materials | The school will sell recyclable materials once a week to be taken to a recycling plant | March 2015-on | The school of Las Pilas | Income. By March 2015, we will have introduced a regular pick-up system to buy recyclable materials from the school. | The CDE Treasurer will be in charge of managing incoming funds, and will record all monetary activity.
The community and school will keep up with use of the recycling center, and reguarly make deposits | Follow-up with community members about use of recycling center at school and proper trash maintenance in their homes | February-April 2015 | All community members | Behavior. By April 2015, community members will be regularly making deposits into the recycling center and properly sorting waste in the home. | Peace Corps Volunteer, Counterpart will give survey to household regaring their regular use of the recycling center
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
From the start we will be working with three complimentary school-based entities: the Natural Sciences teacher for 7th-9th graders (Primary Counterpart), the Ecological Committee, and the Consejo Directivo Escolar (CDE). They will all be responsible, at various phases of project implementation, for date collection, monitoring and evaluation. The Ecological Committee will be responsible for giving talks to community members, parents, and other students regarding recycling and waste management. To measure the impact of the talks, they will give a short pre and post questionnaire to measure general understanding on the subject. Generally, we will be using visual observation as a primary monitoring tool after construction has finished. Once the recycling center has been built, it will be clear how well the classrooms are separating their waste, by their inputs to the recycling center at the end of each day. We will also be able to measure the amount of recyclables coming in by the amount sold each week. The CDE Treasurer will be responsible for recording the dollar amount earned weekly from recyclables, and this will be a clear measure of how much the community is making use of the recycling service. Once the recycling center has been in service for a month, we will conduct a survey regarding household waste management and personal use of the recycling center. These surveys will be given out and recorded by the Ecological Committee in the school, CDE members in parent-teacher meeting, and my counterpart and I in the community.
prgmform: last updated, 06/26/2012 (pjh)