## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals |  | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Build a tree nursery with marketable and environmentally beneficial trees, and by November 2013, have seedlings ready to be sold for profit. |  | Enlist assistance of the Rural Forester to gain insight on needs for a tree nursery and how to begin construction. Begin preparation and construction with available resources. Maintain nursery (watering, trimming, transplanting into potting tubes) | April-November 2013 | approximately 20 members of Beautify Aberdare group, age 30 and older male and female. This number is increasing as membership increases | Baseline at zero, profit, number of trees sold, number of seedlings will be recorded. After the first round of seedlings are sold, this will then become the new baseline for improvement and growth. | PCV Jennifer Navala and members of Beautify Aberdare
| By January 2014 begin transplanting trees into schools, around the community, and back into the forest. | Prepare all tools and create a schedule to begin planting. 11 primary schools and 7 secondary schools in the town will have trees planted. The Njabini Health Centre and Youth Centre will have trees planted, as well as all government buildings in the area and the forest. | January-February 2014 | 18 primary and secondary schools, community areas, forest | Number of schools, buildings, public areas will be recorded. Total number of trees will be recorded and where they were transplanted. | PCV Jennifer Navala and members of Beautify Aberdare, school children
Educate schools and community on environmental awareness and prevention of deforestation |  | By January 2014 have lessons for school children and community members/farmers prepared and ready to teach in congruence with transplanting trees | January 2013-ongoing until all schools have been attended | over 1600 school children age 10-18 | Baseline at zero, number of schools attended to teach, number of students taught, number of farmers/community members educated will be recorded. Increase in knowledge of envrironmental awareness in 1600 school children. Increase knowledge in over 5000 community members. | PCV Jennifer Navala and members of Beautify Aberdare
By February 2014, all ten villages in Njabini Town will have had instruction on how to construct energy saving jikos. |  | Ten households from each of the ten villages in Njabini will receive an energy saving jiko, and be the base of community training for that village to show residents how to construct energy saving jikos and educate them on its importance to their health and to their environment; households that are given jikos will be models to encourage other families to adopt the improved cooking method. | May/June 2013-February 2014 | Over 1000 members of the entire community all ages | Baseline of how many people have energy saving jikos will be surveyed. 6 months after education on jikos, villages will be surveyed again to measure number of households that installed them. Number of households where energy saving jikos have been installed, number of community members taught how to construct energy saving jikos will be measured. | PCV Jennifer Navala and members of Beautify Aberdare
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The project's success will be measured over a period of one year. First, we will measure the success of the tree nursery, which will be indicated by the number of surviving trees, number of trees sold, and profit. All records will be kept by the secretary and the treasurer. Records of these values will be ongoing, as we hope the tree nursery will continually generate income and trees outlasting the one year grant period. Data will be recorded on how many trees were planted in schools, around the community, and back into the forest. The number of schools, school children, and staff that are educated on envronmental awareness will be recorded. To measure efficacy and knowledge atttainment, school children will be given a pre and post interview in the form of a survey. Staff and teachers will be given a survey on their opinions of each lesson given. Data on numbers of farmers and community members that are educated will be recorded. In the long term, soil productivity and fertility will be a sign of improved soil nutrition benefitting from the trees planted. Increased number of households with energy efficient jikos will indicate the success of the time invested in teaching the construction of these jikos. Long term measurements of this success will be decreased number of respiratory illnesses reported in health centers, as well as overall reduction of deforestation and cutting down of trees for firewood. PCV Jennifer Navala and members of Beautify Aberdare Self-Help group will be responsble for collecting all data. PCV Jennifer Navala will be responsible for analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)

## TIMELINE
Activity | Person(s) Responsible
Create workplan and list of needed supplies to begin a tree nursery | PCV Jennifer Navala, members of Beautify Aberdare, and assistance from Rural Forester | x
Apply for PCPP Grant to help get supplies donated to be able to sustain nursery. | PCV Jennifer Navala and members of Beautify Aberdare | x
Begin to collect necessary supplies for tree nursery (collect soil, sand, timber) | PCV Jennifer Navala and members of Beautify Aberdare | x
Construct tree nursery and seed bed. | PCV Jennifer Navala and members of Beautify Aberdare | x
Move seedlings from seed bed to potting tubes. | PCV Jennifer Navala and members of Beautify Aberdare |  |  | x
Plan for other IGA projects as well as lesson plans for community education | PCV Jennifer Navala and members of Beautify Aberdare |  | x | x | x | x | x | x | x | x | x | x | x
Use time to teach weekly lessons on Life Skills to local primary and secondary schools | PCV Jennifer Navala, members of Beautify Aberdare, staff of Ministry of Public Health, staff of Njabini Health Centre |  | x | x | x | x | x | x | x | x | x | x | x
Begin selling tree seedlings locally. | PCV Jennifer Navala and members of Beautify Aberdare | [5 empty] | x
When tree seedlings are mature and hardened, begin planting trees in schools, around the community, and back in the forest | PCV Jennifer Navala and members of Beautify Aberdare | [7 empty] | x | x | x | x | x
For each place that trees are planted, tree planting will be supplemented with education | PCV Jennifer Navala and members of Beautify Aberdare, assistance of Rural Forester | [7 empty] | x | x | x | x | x
Teach community how to build energy saving jikos/educate on importance of conserving fuel for health and environment | PCV Jennifer Navala and members of Beautify Aberdare |  |  |  | x | x | x | x | x | x | x | x | x