## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To encourage technology usage in classroom lectures for 8 teachers by installing two projectors in two classrooms that currently do not have one within a time span of two months. | Training on maintenance and usage of projectors and how to effectively use technology in lessons for teachers will be required to achieve this goal. The project leader and I will have fundraisers in order to raise money for 25% of the project costs. One of the fundraisers will be an activity where students (and other people from the community) have to help paint a mural of the world map on one of the walls in the school. People from the community can purchase a country and write their names underneath the map. Another fundraiser is a bake sale where the teachers and the students bring in baked goods and raise money for the projectors. Once the rest of the donations are ready, the principal and the vice principal must go to the ministry of education to get the donation approved by the director. Once that is approved, the school’s accountant will handle the finances and will order the projectors. The projectors will then be installed by the school’s technology worker. | 01/2015-03/2015 | 6 female teachers who are above 24 years old and 2 male teachers who are above 24 years old | 1. Baseline: Classrooms do not have projectors; therefore, teachers in those classrooms teach without technology. 2. Midline: Teachers' knowledge on using projectors will increase due to the training sessions 3. Final: Teachers will use the projectors and provide effective lessons due to their access to the educational resource. | During the training sessions prior to the installation of projectors, there will be a pre-test on how to effectively use projectors in the classroom. The pre-test will be provided by the volunteer and the project leader. Then, there will be a post-test after about 2 weeks.
To encourage technology usage in the classroom by 54 students by installing two projectors in two classrooms that currently do not have one within a time span of two months. | Lessons on teaching students how use PowerPoint will be necessary to achieve this goal. Students will then have to make presentations using PowerPoint on a specific topic. | 01/2015-03/2015 | 24 females from ages 6-17 and 30 males from ages 6-17 | 1. Baseline: Classrooms do not have projectors; therefore, students in those classrooms cannot utilize technology in their presentations. 2. Midline: Students' knowledge will increase due to lessons on how to give PowerPoint presentations. 3. Final: Students will use the projectors and provide PowerPoint presentations. | During the lessons, my co-teacher and I will give a pre-test on presentation style and on using PowerPoint presentations. After students make their own presentations, a post-test will be provided that will assess their knowledge on how to use PowerPoint presentations and general information on giving presentations.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
I plan on providing the teachers a pre-test on how to use technology in the classroom. For example, one of the questions will ask, "What ways can you use the projector to improve quality of learning in the classroom?" Then they will be given an assignment where they have to create a lesson plan that requires technology in the classroom. After they have had their lessons, a post-test will be given and that will help determine whether teachers have learned how to effectively use technology in their classrooms. The students, however, will be given lessons on using PowerPoint presentations and on giving presentations. Before the lessons, they will be given pre-tests on presentations. For example, a question on the pre-test will ask, "What is your idea of a successful presentation?" Students will have to make PowerPoint presentations on a specific topic and then they will take a post-test.
prgmform: last updated, 06/26/2012 (pjh)