## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Youth camp participants will adopt behaviors and practices to increase healthy lifestyle choices and reduce risky sexual behaviors | Gender specific reproductive health talks with host-country national medical professionals, sessions on healthy nutrition, malaria prevention and treatment education | March-April 2015 | 13 boys and 13 girls between the ages of 14-19 | Increase in knowledge of safe-sex behaviors and family planning among 26 youth camp participants. Increasing in practicing positive, healthy behaviors among 26 youth camp participants | Pre- and post-assessments of reproductive health and nutrition knowledge, conducted by PCV Kimberly Boland
Youth camp participants will expand their knowledge of future planning, financial literacy, and goal setting | Host-country national career panel, sessions on future planning and financial literacy | March-April 2015 | 13 boys and 13 girls between the ages of 14-19 | Increase in knowledge of good business practices and financial planning. Increase in positive future planning behaviors | Pre- and post assessments of financial literacy, observation and evaluation of goals and future planning presentations
Former youth camp participants will expand their facilitation and leadership capacity | Former participants will aid in facilitation and delivery of sessions throughout the camp | March-April 2015 | 2 boys and 2 girls between the ages of 14-19 | Increase leadership and presentation skills and increase knowledge of facilitation and public-speaking | Assessments and evaluations with former participants
To provide high quality education and effective training in leadership skills | Execute team-building activities, practical application of creative outlets to relay messages of positive life choices and behavior, and execute practical exercise of public speaking | March-April 2016 | 13 boys and 13 girls between the ages of 14-19 | Increase knowledge and effective leadership and presentation skills among 26 youth camp participants. Increase in practicing effective leadership and presentation skills among 26 camp participants, increase in practicing effective teamwork among participants | PCV Kimberly Boland, pre- and post- assessment of effective presentation skills, assessment and observation of the execution and messaging of theater sketches, completion of team building activities, assessment and observation of individual presentations.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
We will utilize surveys and interviews with camp participants to measure the project's success. On day 1 of the camp, using a pre-assessment tool, We will obtain baseline data on participants knowledge of family planning, reproductive health, financial literacy, and life skills. The assessment will contain multiple-choice and open ended questions and will also ask each participant to evaluate his/herself in terms of ability, comfort, and attitudes towards public speaking, group work, and goal setting. Throughout the camp, there will be practical applications of lessons learned during sessions. For example, after receiving information on goal setting and future planning, participants will work on making their own 5 and 10-year plans for the future. Participants will also present their plans to the group and be assessed on their knowledge as well as presentation skills. Criteria will include, but are not limited to: clarity, body language, voice level, audience engagement, length of presentation, quality of content, and visual aids. During the final day of the camp, a post-assessment survey will be conducted with the same questions as the pre-assessment. Interviews will also be conducted on the last day of the camp to help assess each individual's level of comfort and attitude toward public speaking and also allow for participants to share information and feedback not included in the assessment surveys. Participant feedback on surveys and interviews will also be used to help improve organization and execution in upcoming years.
prgmform: last updated, 06/26/2012 (pjh)