## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
At least 20 youth (with 50% being young women) will complete a 16-20 week training and learn how to design, manage, and promote a business, and to create an association in charge of a sustainable cafe in the dar chabab. | 16-20 week training programed offered to the youth in the dar chabab. | November 2014 until March 2015 | 20 youth aged 15-24 and 4 youth 25 and above. | 1) By March 2015, 20 participants will receive a certificate indicating participation in at least 80% of the sessions. 2) By March 2015 the youth will demonstrate an increase in their knowledge and understanding of basic business skills. | 1) Weekly tracking of attendance; I will be responsible. 2) There will be a survey taken at the beginning of the training and the end of the training that tests their basic business skills; the project leader will be responsible for interrpreting the data.
Halfway through the training program, the youth will open and begin to operate the youth café in the dar chabab | Grand opening of the dar chabab in January 2015 | 2015-01-01 | 20 youth aged 15-24 and 4 youth 25 and above. | 1) By January 2015, there will be an opened café in the dar chabab available for use by the youth of the city. 2) By March 2015 the youth will demonstrate increased business knowledge by an increased business accumen shown through consistent good running of their cafe. | 1) Weekly check-ins with youth from the opening of the café until the end of the sessions about their comfort level with running the café; the project leader will be responsible for collecting and analyzing the discussions.
The youth will complete paperwork and have a functioning association for the café | All paperwork will be finalized and delivered to the municipality, with the approval process taking approximatey 30 days. | 2015-03-01 | 20 youth aged 15-24 and 4 youth 25 and above. | By March 2015, the youth will have the necessary paperwork filed with the municpality and the approval of their association. | Completed Association paperwork.
Through the creation of a cafe that is run and designed by at least 12 young women, the dar chabab will provide an ongoing service to young women in the community by providing them a safe, culturally appropriate cafe that gives them the opportunity to enjoy a cafe environment that is not currently found (though much desired) in their town. | Weekly or bi-weekly art, cultural, and reading events held at the dar chabab's café between it's opening and the end of the training program. | 2015-03-01 | 60 young women aged 15-25 | By March 2015, at least 50% of all participants of activities in the dar chabab will be young women. | Tracking of attendence for all café activities counting the number of young men and young women present.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
I plan on implementing continous monitoring of the number of women who are involved in all aspects of the project. We will also be noting the leadership roles of the women and working directly to ensure that the young women feel comfortable in the training atmosphere. We will be collecting raw data, and I will work with my counterpart to interview the young women during the training sessions to make sure that they feel comfortable. As needed, we will work with the young women to assist them in asserting themselves in all aspects of the project.
prgmform: last updated, 06/26/2012 (pjh)