## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
1. To increase access to tap water for 222 households in Uwakagano, Bururi, and Gasumo villages in Banda, reducing the use of contaminated stream water and the time burden of fetching water from remote locations which is borne by women and children | The community will dig a 2,757 meter long canal for the water pipeline through community work days. | 2014-11-01 | 977 (170 men, 222 women, 333 female children and youth, and 252 male children and youth) | 1. Meters of canal dug | Kageno's Community Mobilizer will be responsible for organizing and coordinating digging efforts and delegating responsibilities. The PCV, Project Leader, and Kageno Community Mobilizer will make weekly field visits to the pipeline site during the first month of the project to monitor the community's progress. Feedback will be given and progress assessments will be recorded.
| The technician, with community assistance, will install 2,757 meters of piping, two 5 m³ reservoirs, and six new and functioning water taps in the three villages. | 2014-12-01 | 977 (170 men, 222 women, 333 female children and youth, and 252 male children and youth) | 1.Number of taps completed 2. Number of taps in use | The PCV, Project Leader, and Kageno Community Mobilizer will make weekly field visits to the construction site during the second month of the project to monitor progress. Feedback will be given, problems addressed, and progress assessments recorded.
| The Ruganza Pentacostal Church (ADEPR) in Bururi will connect to the pipeline using its own funding, serving an additional 800 people from outside villages. | 2014-12-01 | 800 (150 men, 250 women, 264 female children and youth, 136 male children and youth) | 1. Completion of water source at ADEPR Ruganza 2. Number of people with access to the tap | Kageno's Community Mobilizer will assist with a survey conducted in the congregation of AEDPR Ruganza following the completion of the source. All beneficiaries using the water will be recorded.
| 1,777 individuals will benefit from the water infrastructure and 222 families will use the six new taps in Uwakagano, Bururi, and Gasumo. A survey will be conducted at each water source on the number of beneficiaries. | 2015-01-01 | 1,777 (320 men, 472 women, 388 female children and youth, and 597 male children and youth) | 1. Number of families with access to the tap 2. Number of men, women, and children with access to the tap 3. Number of households reporting a decrease in time needed to fetch water 4. Number of households that stopped using stream water | Following the completion of construction, six individuals will conduct a survey at each tap for a week, and they will record the following information from beneficiaries: the individuals' name, date of birth, family members, family members’ dates of birth, the location they got water before the project, how long it took them to collect water from the old source, and how long it takes from the new source.
2. To increase the beneficiaries' capacity to properly use and treat water and to maintain the new water infrastructure | A committee consisting of six volunteers who act as spokespeople and caretakers of the water source will be formed at each tap. | 2014-11-01 | 36 | 1. Number of committees formed | Kageno's Community Mobilizer will oversee the creation of the committees once the project begins.
| All 36 committee members will attend a three-day training at Kageno on the following: 1. The importance of clean water in preventing disease 2. Treating water 3. Basic hygienic practices 4. Properly caring for taps, pipes, and reservoirs 5. Monitoring community water use and security at taps 6. Repairing taps and pipes | 2014-12-01 | 36 | 1. Number of people trained 2. Increase in knowledge about safe water and water system maintenance among the 36 committee members 3. Percent improvement on pre and post tests | The PCV and project leader will take attendance during each day of the training. Each participant will take a written pre-test before the training begins, and will take a post-test with the same content after the training is complete. The PCV and project leader will correct the tests and calculate the percent improvement.
| 7. The committees will open an account at the local savings and credit cooperative (SACCO) for future repair and maintenance of water sources | 2015-01-01 | 1,777 (320 men, 472 women, 388 female children and youth, and 597 male children and youth) | 1. SACCO account opened | After the committee trainings are complete, Kageno's Community Mobilizer will assist committees with opening the SACCO account
3. To increase awareness in the community about the importance of safe drinking water and properly caring for and maintaining water infrastructure by training village leaders and Community Health Workers | 22 local leaders and 15 CHWs will attend a three-day training at Kageno on: 1. The importance of clean water in preventing disease 2. Treating water 3. Properly caring for taps, pipes, and reservoirs 4. Monitoring community water use and security at taps 5. Repairing taps and pipes | 2014-12-01 | 37 (17 women and 20 men) | 1. Number of individuals trained 2. Increase in knowledge about safe water and water system maintenance among the 37 participants 3. Percent improvement on pre and post tests | The PCV and project leader will take attendance during each day of the training. Each participant will take a written pre-test before the training begins, and will take a post-test with the same content after the training is complete. The PCV and project leader will correct the tests and calculate the percent improvement.
| All village leaders will hold village meetings on safe drinking water and caring for public water taps | 2014-01-01 | 500 | 1. Number of meetings held 2. Number of people attending each meeting | The PCV and Project Leader will collaborate with local leaders to schedule meetings and plan meeting content. Local leaders will be responsible for taking attendance at the meetings and submitting the information. The PCV and project leader will try to attend all meetings.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
In order to measure the success of the first goal—increasing access to tap water for 222 households in Uwakagano, Bururi, and Gasumo villages in Banda—the main data will be collected after the construction of the taps by six individuals working at each tap for a week to record data on the families using the taps. This has already been discussed by Kageno staff and agreed upon as the most feasible way to determine the number of beneficiaries. Each time an individual comes to collect water during this week of data collection, the following information will be recorded: the individuals' name, date of birth, names of the family members, their dates of birth, the location they got water before the project, how long it took them to collect water from the old source, and how long it takes from the new source. Afterwards, the data will be organized by family and a relatively accurate picture on the increase in water access will emerge. In order to determine the number of beneficiaries at the Ruganza Pentecostal Church in Bururi, a direct survey will be taken in the congregation, and the list of households accessing the water recorded. Kageno's Community Mobilizer, Project Leader, and PCV will be responsible for organizing and overseeing this research. Kageno's Community Mobilizer is also familiar with most of the families in these villages, and has already collected household data from them for the planning of the project. In order to measure increases in knowledge among individuals trained, including committee members, leaders, and Community Health Workers, a simple pre- and post-test will be used. Before the training, all individuals will take a pre-test to assess their baseline knowledge. At the end of the training, the individuals will take the same test to see if they gained knowledge. Tests will be graded and percent improvements will be calculated. The Project Leader and PCV will be responsible for delegating and correcting tests. This method was used during the latrine project with success. Many of the other indicators of success will be measured through site visits or direct observation, including the community contribution, construction progress, and committee formation. Village leaders will take attendance at their village meetings about sanitary water and caring for water sources, which is a common practice in official local meetings.
prgmform: last updated, 06/26/2012 (pjh)