## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Goal 1 (Access & Income): 80% of the current standard 6 participants will enrol in high school after graduating from primary school by July 2015 and report an increase in self-generated income by at least $300/year. | • Maintaining GLOW Clubs for the young girls and offer trainings on self-esteem and self-confidence building, leadership, and ways to become more self-reliant. • Youth education methodologies including role modeling, reinforcement, and mentoring. • Educate GLOW girls on alternative approaches to cultural norms for young Q’eqchi women. • Educate girls on available educational and vocational activities. • Collect data on GLOW Club girls’ pursuits as it relates to their individual interests. | • May 2014 - September 2017 • May 2014 – September 2017 • November 22, 2014 • November 22, 2014 | 27 GLOW Club girls | Objective 1.1 Within the first year of the project, 80% of standard 6 GLOW Club girls will report an increased access to educational opportunities. Indicators • Output 1.1.1: Number of girls who participate in the GLOW Clubs. • Output 1.1.2: Number of girls educated on alternative approaches to cultural norms as well as educational and vocational activities. • Output 1.1.3: Number of GLOW Club girls who complete surveys relating to their individual aspirations. • Outcome 1.1.4: Number of standard 6 girls who enroll in secondary school. • Outcome 1.1.5: Number of GLOW Club girls who report positive role modeling, reinforcement, and mentoring. | Data Collection Method: activity checklists and log forms and surveys Persons Responsible: Peace Corps Volunteers and work partners
Goal 1 (Access & Income): 80% of the current standard 6 participants will enrol in high school after graduating from primary school by July 2015 and report an increase in self-generated income by at least $300/year. | • Provide small group training and one-on-one mentoring. • Provide resources banks and strategies for networking purposes. | • November 15, 2014 | 8 work partners | Objective 1.2 Within the first year of the project, 60% of work partners will report an increase in access to other development resources and opportunities. Indicators Indicators • Output 1.2.1: Number of work partners given trainings on professional development and offered mentoring. • Outcome 1.2.2: Number of work partners reporting increased knowledge and confidence in how to access development resources. | Data Collection Method: activity checklists and log forms, surveys, and questionnaires Persons Responsible: Peace Corps Volunteers, work partners, and third party counterparts (Ms. Froyla Tzalam, Director, SATIIM & Mr. Samuel Choc, Agriculture Teacher and Chairman of Santa Ana Village, Corozan Creek Technical High School)
Goal 1 (Access & Income): 80% of the current standard 6 participants will enroll in high school after graduating from primary school by July 2015 and report an increase in self-generated income by at least $300/year. | • Distribute one sow to each of the 27 young girls in the two GLOW Clubs. • Conduct financial surveys on funds made from the sows. • Report number of girls who used monies made from the sale of pigs to further their education. | • December 15, 2014 • June 1, 2015 • July 4, 2015 | 27 GLOW Club girls | Objective 1.3 Within the first year of the project, 80% of GLOW Club girls will report an increase in self-generated income from $0/year to at least $300/year from the project. Indicators • Output 1.3.1: Number of GLOW Club girls who receive sows from the project. • Output 1.3.2: Number of GLOW Club girls who complete surveys reporting funds made from the sows. • Outcome: 1.3.4: Number of GLOW Club girls who report using monies made from the sale of pigs to pay for their educational expenses. | Data Collection Method: activity checklists and log forms, surveys, and questionnaires Persons Responsible: Peace Corps Volunteers and work partners
Goal 2 (Knowledge & Behaviour): All participants, beneficiaries, and work partners will be offered programmatic and financial training and will report a change in perception towards girls’ education within the first 6 months. | • Offer training on best practices in pig rearing. | • November 29, 2014 | 27 GLOW Club girls, 54 beneficiaries, 8 work partners | Objective 2.1 Within the first 3 months of the project, 27 girls, 54 beneficiaries, and 8 work partners will have knowledge of best practices in pig rearing. Indicators • Output 2.1.1: Number of girls, beneficiaries, and work partners trained in pig rearing especially in pig diseases, nutritional needs, growth monitoring and control, castration benefits, and pig pen benefits. • Outcome 2.1.2: Number of girls, beneficiaries, and work partners reporting increased knowledge in pig diseases, nutritional needs, growth monitoring and control, castration benefits, and pig pen benefits. | Data Collection Method: activity checklists and log forms, pre-tests and post-tests, surveys, and questionnaires Persons Responsible: Peace Corps Volunteers, work partners, and third party counterpart, Mr. Samuel Choc, Agriculture Teacher and Chairman of Santa Ana Village, Corozan Creek Technical High School
Goal 2 (Knowledge & Behaviour): All participants, beneficiaries, and work partners will be offered programmatic and financial training and will report a change in perception towards girls’ education within the first 6 months. | • Project design and financial management workshops for work partners. | • November 15, 2014 | 27 GLOW Club girls, 54 beneficiaries, 8 work partners | Objective 2.2 Within the first 3 months of project, 27 girls, 54 beneficiaries, and 8 work partners will be trained in financial management and accountability. Indicators • Output: 2.2.1: Number of girls, beneficiaries, and work partners trained in individual and small-scale project account keeping, saving and banking practices, financial record keeping, and financial reporting and accountability. • Outcome 2.2.2: Number of girls, beneficiaries, and work partners reporting increase in knowledge in individual and small-scale project account keeping, saving and banking practices, financial record keeping, and financial reporting and accountability. | DCM: activity checklists and log forms, pre-tests and post-tests, surveys, and questionnaires PR: Peace Corps Volunteers & work partners
Goal 2 (Knowledge & Behaviour): All participants, beneficiaries, and work partners will be offered programmatic and financial training and will report a change in perception towards girls’ education within the first 6 months. | • Offer formal training of trainers for local work partners. | • November 15, 2014 | 8 work partners | Objective 2.3 Within the first 3 months of the project, 80% of work partners will increase knowledge in project design and management. Indicators • Output 2.3.1: Number of work partners participating in a training-of-trainers workshop that demonstrates strategies and methodologies of designing small-scale projects, creating organisational structures, aligning administrational priorities, and effectively managing project implementation. • Outcome: 2.3.2: Number of work partners reporting an increase in knowledge on strategies and methodologies of designing small-scale projects, creating organisational structures, aligning administrational priorities, and effectively managing project implementation. | Data Collection Method: activity checklists and log forms, surveys, and questionnaires Persons Responsible: Peace Corps Volunteers, work partners, and third party counterpart, Ms. Froyla Tzalam, Director, SATIIM
Goal 2 (Knowledge & Behaviour): All participants, beneficiaries, and work partners will be offered programmatic and financial training and will report a change in perception towards girls’ education within the first 6 months. | • Individual and group surveys on girls’ education. • Small group education on benefits of investing in girls’ education. | • June 1, 2015 | 27 GLOW Club girls, 54 beneficiaries, 8 work partners | Objective 2.4 Within the first 6 months of the project, 80% of GLOW Club girls, 50% of beneficiaries, and 50% of work partners will improve their perception towards girls’ education and cultural roles. Indicators • Output: 2.4.1: Number of girls, beneficiaries, and work partners completing a survey on individual and community perception towards girls’ education and cultural roles. • Output 2.4.2: Number of girls, beneficiaries, and work partners able to identify three benefits of investing in girls’ education. • Outcome 2.4.3: Number of girls, beneficiaries, and work partners reporting a positive change in perception towards girls’ education and cultural roles. | Data Collection Method: activity checklists and log forms, pre-tests and post-tests, surveys, and questionnaires Persons Responsible: Peace Corps Volunteers & work partners
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Although GLOW Clubs have been present in many countries for over 19 years, the clubs targeted by this project have only been active for at least 4 years. However, through the process of revitalising these clubs, local capacity is being built and the mission and vision for the clubs is being strengthened. As such, host country work partners will be instrumental in carrying out many of the project activities as well as monitoring, reporting, and evaluating the progress and success of this project. They will be trained to do during PCVs’ service and will be expected to continue the MRE process after PCVs leave the villages. The project’s MRE plan outlines activities, outputs, and indicators. In order to monitor the project’s progress, data will be collected, measured, and reported through quantitative and qualitative data collection tools. Before and during every activity, baseline data will be collected from different actors, such as the GLOW Club girls, the beneficiaries, and the work partners. Some tools will measure the knowledge, skills, and attitudes of individuals while others will take into account an entire group. These tools will measure output, outcomes (results) or activity level. Both qualitative and quantitative data collected will demonstrate realities in program development that are often overlooked before the project is implemented. With this in mind, the following tools will be used: activity checklists, pre-tests, post-tests, surveys, questionnaires, and individual and group interviews. Interviews will especially be helpful in conveying cultural feedback that cannot be accommodated through written feedback. Collectively, these tools will measure outcomes and determine areas of improvements in knowledge, skills, and attitudes as a result of the project’s activities. With PCVs and their work partners living in the targeted communities, they will be cognisant of both structural and programmatic challenges that can inform data from participants. This will help frame the post-project analysis and offer best practice measures and safeguards for future PCVs and communities that would like to adopt or implement a similar program.
prgmform: last updated, 06/26/2012 (pjh)