## Project Plan Guidance - Table 1
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template - Table 1
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
24 families that presently have no functional latrine will use and properly maintain improved VIP latrines | Mari Perez, along with other leaders from Centro de Madres, and PCVs Cynthia and Richard Cowgill determine the list of participating families | 2013-06-01 | Leaders of Centro de Madres | list generated | Cynthia and Richard Cowgill
| Community leaders and hired masons with Richard Cowgill decide the order of construction |  | Masons, community leaders | list generated | Cynthia and Richard Cowgill
| Order materials for 5 latrines at a time | June-Oct.2013 | Masons, community leaders | supplies delivered, receipts collected | Mari Perez and PCVs will sign for deliveries and keep receipts
| Construct latrines | June-Oct.2013 | Participating families, and their neighbors | number of latrines constructed | photos and payroll records, latrine inspections. PCVs and leaders from Centro de Madres to observe.
24 families will adopt Improved hygiene habits | Leaders recruit 6 volunteers from the Centro de Madres to train as health facilitators |  | women volunteer trainees | number of participating trainees | notes, attendance roles
| Cynthia Cowgill trains health facilitators | June-July 2013 | women volunteer trainees | Pre and Post knowledge discussion | notes from discussion comments showing knowledge gained. Cynthia Cowgill responsible
| Facilitators make 2 visits to the families, delivering health and sanitation lesson | June-Oct.2013 | participating families, women volunteer trainees | Number of families participating in a health lesson with a health facilitators | participation reports from health facilitators
| Families build hand washing stations outside their new latrine | Sept.-Oct. 2013 | participating families, women volunteer trainees | Number of hand washing stations constructed and regularly used. | observation reports, health facilitators, photos taken by PCVs
| Families are trained on proper latrine maintenance | Sept.-Oct. 2013 | participating families, women volunteer trainees | Number of families educated on the functionality and maintenance of the new latrines. | participation reports from health facilitators
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The first important thing to do is to accurately determine the needy families. This will require that someone (PCVs and Community leader) follow up on the list of needy families generated by the Centro de Madres. Also, we will consult with some of the leaders of the Haitians in the community, because the Haitians are often overlooked, and they do not participate with the Centro de Madres. We want to find all the extreme need situations. Many people will report that they need a new latrine and it is very important that the need be verified. We plan to visit each possible home, and photograph the situation. Later, we can use the photographs to correctly prioritize the needs. Once the list is generated the supplies will be ordered. They will be closely monitored after delivery, with Centro de Madres supplying a secure place for sand, gravel and block deliveries, and other individual supplies will be inventoried and collected by the participating families to protect until their turn for construction. When construction begins Richard Cowgill will monitor the building of the latrines by visiting the sites and talking to the masons daily. Richard will inspect each latrine for quality before the payment is made to the mason. Finished latrines and hand washing stations will be verified with photographs taken by PCVs. The health facilitator trainings will be monitored with a pre and post oral quiz (discussion), to verify that they have learned the material. Cynthia Cowgill will create and conduct the quiz. Attendance records will be kept. The trained health facilitators will report back to Cynthia Cowgill giving feedback on the success of the family lessons and construction of hand washing stations. At the end of the project, Cynthia Cowgill will note the information from the health facilitators, verifying each participating family’s adoption of improved hygiene habits.
prgmform: last updated, 06/26/2012 (pjh)