## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To provide high quality WASH education to 400 mothers in the project area through a network of 3 community health workers during the first 6 months of the project | Host trainings for the mothers on WASH education | November 2014 - January 2015 | 350 women 24 and older, 150 women 24 and younger | Increase in knowledge related to WASH education among 300 mothers. Increase in hand washing amongst 300 mothers through the construction of hand washing stations in 65 households | Health worker who conducted the baseline survey will work again with the PCV to conduct a post baseline survey.
To increase access to sanitation systems for 400 mothers and 300 children in the project area through construction of 65 latrines during the first 6 months of the project. | Constructing 65 new latrines and 65 new hand washing stationgs | December 2014- March 2015 | 340 female 24 years or older; 150 female 18 to 23 years old ; 135 females from 6 -17 years old ; 125 girls from 0-5; 270 males 24 years or older; 125 males 18-23 years old, 124 males 6- 17; 75 males 0 years or older | Increase in access to sanitation by constructing 65 latrines and 65 new hand washing stations.Increase in knowledge related to proper latrine usage and care among 300 mothers. Increase in proper disposal of feces and proper choice in location when defecating among 300 mothers | Health worker who conducted the baseline survey will work again with the PCV to conduct a post baseline survey.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The USAID Maternal and Child Health Integrated Program MCHIP 2005 “Household and Water and Sanitation” model was used to develop a pre- baseline survey and also later translated into Wolof by myself with the assistance of Peace Corps Staff. Eleven questions/observations were chosen for the baseline survey. Each question/observation was paired with certain coding categories. The coding categories were chosen to help decrease the time used when conducting the surveys. A simple scantron was used to collect data. My counterpart and I went from compound to compound and spoke with the head of the household and the first wife. The questions that were focused on WASH and child care were answered by the mothers and the questions that were focused on latrines were answered by the head of the household. The community members of Keur Katim were very open to participating in the survey. In one week, my counterpart and I surveyed 51 households, which is more than two-thirds of my community. After the latrines are constructed and the health workers train the mothers on WASH techniques, a post-baseline survey will be proctored for all the participants. The questions regarding the use of soap, hand washing, and defecating from the pre-baseline survey will be reused for the post baseline survey along with questions reflecting the WASH training in order to assess any behavior change improvements. The PCV will accompany the health worker again from household to household to conduct the post baseline survey. Like the pre-baseline survey, each question/observation will be paired with certain coding categories. The coding categories were chosen to help decrease the time used when conducting the survey. A simple scantron will be used to collect data.
prgmform: last updated, 06/26/2012 (pjh)