Project Plan

A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows if needed.

| Goals | Activities | Time frame for completion | Total Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible |
| --- | --- | --- | --- | --- | --- |
| Healthy outlets for children in the surrounding villages of Tiznit | Build 8 tire playgrounds | Nov 10th – Feb 10th | More than 8000 children – 1000 per playground | When all 8 playgrounds have been completed | Leanna Pohevitz |
|  |  |  |  | When the grant report is in! |  |
| Significantly increase volunteerism | Bring at least 4 youth volunteers with us to every build | Nov 10th – Feb 10th | 32 directly, innumerable indirectly | Minimum of 32 new volunteers along with us for the builds | Project leader – to insure these are not typical volunteers of the youth center but are recruits from outside our normal strong volunteer community |
| Spark Community Involvement | 8 community builds | Nov 10th – Feb 10th | The entire community of Tiznit province so hopefully, in some way 130,000 people will somehow hear about it, see it, use it, attend the meetings, come to the youth center etc. I realize this is a big goal, but I wouldn’t be in Peace Corps if I didn’t dream big. | 8 builds occur with enough people to complete them | Leanna Pohevitz - photos |
|  | 8 community meetings | “ ” |  | 8 meetings occur with an attendance of 25 or more (one in each community with the sites) | Project leader |
|  | Serious donation collection | “ “ |  | Being able to return some of the grant money!! | Leanna Pohevitz - financial paperwork in order and returned money noted! |
| New Leadership | Have 8 different people in leadership positions on these builds (one different person for each playground!) hopefully from all different associations to start the process of serious long term collaboration. | Nov 10th – Feb 10th | 8 | 8 different folks talking the lead for each project | Project leader and association presidents |

Also, here is our full timeline, in case that helps clear up the picture a bit.

Timeline

|  | Activity | Person(s) Responsible | Implementation Time |
| --- | --- | --- | --- |

| 1 | Meeting with site 1 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCV - Leanna Pohevitz | Mon, Nov 3rd, 2014 |
| --- | --- | --- | --- |
| 2 | Collecting donated supplies and purchasing first round of supplies for the build in November | PCVs and Project Leader | Wed, Nov 5th, 2014 |
| 3 | Training of Trainers for this Tire Playground Project | PCV -Leanna Pohevitz | Fri, Nov 7th, 2014 |
| 4 | First build | PCVs and community members with one association leader as coordinator. | Mon, Nov 10th, 2014 |
| 5 | Attempt to purchase all remaining supplies so we can get bulk discounts - to be stored in youth center | Project Leader and both PCVs in Tiznit (Leanna Pohevitz and Danielle Scheffler) | Tues, Nov 18th, 2014 |
| 6 | Meeting with site 2 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCVs and community members with one association leader as coordinator. | Wed Nov 19th, 2014 |
| 7 | Second build | PCVs and community members with one association leader as coordinator. | Sun Dec 7th and Mon Dec 8th, 2014 |
| 8 | Meeting with site 3 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCVs and community members with one association leader as coordinator. | Dec 16th 2014 |
| 9 | Third build | PCVs and community members with one association leader as coordinator. | Sun Dec 21st and Mon Dec 22nd, 2014 |
| 10 | Meeting with site 4 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCV and Project Leader | Tues Dec 30th, 2015 |
| 11 | Fourth build | PCVs and community members with one association leader as coordinator. | Sun Jan 4th and Mon Jan 5th, 2015 |
| 12 | Meeting with site 5 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCV and Project Leader | Tues Jan 6th, 2015 |
| 13 | Fifth build | PCVs and community members with one association leader as coordinator. | Sun Jan 11th and Mon Jan 12th, 2014 |
| 14 | Meeting with site 6 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCV and Project Leader | Tues Jan 13th, 2015 |
| 15 | Sixth build | PCVs and community members with one association leader as coordinator. | Sun Jan 18th and Mon Jan 19th, 2015 |
| 16 | Begin reports - specifically spend time editing photos and getting all information on purchases and donations in order. | PCV - Leanna Pohevitz | Mon Jan 19th-Sat Jan 24th, 2015 |
| 17 | Meeting with site 7 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCV and Project Leader | Tues Jan 20th, 2014 |
| 18 | Seventh build | PCVs and community members with one association leader as coordinator. | Sun Jan 25th and Mon Jan 26th, 2015 |
| 19 | Meeting with site 8 owner/proprietor to look over land, determine that is ready to be built on, bring some materials, and discuss which structures we will be building. | PCV and Project Leader | Tues Jan 27th, 2015 |
| 20 | Eighth build | PCVs and community members with one association leader as coordinator. | Sun February 1st, 2015 |
| 21 | ALL FINAL REPORTING for this grant! | PCV - Leanna Pohevitz | Feb 2nd - Feb 10th, 2015 |