## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
By June of 2015, 33 vulnerable mothers and/or caregivers in the communities of Sacus and Mumpampa will adopt practices to improve early childhood development for their children less than three years of age. | 1. Month one house visit theme: Train mothers on the correct use of their CRED/ development card in their homes 2. Train health promoters about importance of early childhood stimulation 3. Educative session in the home about practices of early childhood stimulacion | March, 2015 | 33 Mothers ages 22 and older, 6 Health Promoters ages 25 and older | 1. 33 Mothers can show the proper use of the CRED/ Development card 2. 33 mothers will be able to demonstrate at least 2 skills to promote early childhood stimulation of their child 3. 30 mothers will adopt skills of early child hood stimulation in their home. | Evaluation and observation of practices in the home/ volunteer
By the end of June 2015, 33 vulnerable mothers and/or caregivers with children less than two years of age in Sacus and Mumpampa will gain the skills to improve caring and feeding practices to improve maternal and child nutrition through sessions given by trained health promoters. | 1.Train health promoters about exclusive breast milk feeding and introduction of complimentary food 2. Educative session in the home about exclusive breast milk and introduction of complimentary food 3. Train health promoters about balanced nutrition 4. Educative session in the home about balanced nutrition 5. Educative session in the home with prepared food about how to prepare a balanced age apropriate plate for children 6. Train health promoters about prevention of anemia 7. Educative session in the home about how to detect and prevent anemia | April, 2015 | 33 Mothers ages 22 and older, 6 Health Promoters ages 25 and older | 1. 33 mothers will be able to identify at least three complementary feeding practices using locally available foods. 2.30 mothers will be able to demonstrate how to make a nutritious and balanced meal for the correct age of their child from locally available food. 3. 8 children 6 to 12 months of age will have received exclusively breast milk for their first 6 months of life. 4. 9 children ages 6-11 months will have received 3 feedings (three meals plus breast milk 8 times during the day) of the age appropriate quantity in the day preceding the assessment | Evaluation and observation of practices in the home/ volunteer
By the end of June 2015 65 mothers and 20 community members who worked on the committee of the project will cook meals on an improved cookstove | 1. Train 3 community members on how to build an improved cookstove 2. Purchase and transport materials for the cook stoves and Build improved cookstoves 3. Educative sessions in the home about how to correctly use and maintain an improved cookstove | June, 2015 | 33 mothers ages 22 and older, 12 male committee members ages 25 and older | 1. 45 community members received training about how to properly use an improved cookstove to reduce risk of sickness in their homes 2. 45 community members will have received training on how to properly maintain an improved cookstove | Evaluation and observation of practices in the home/ volunteer
By the June of 2015, 33 vulnerable mothers and/or caregivers will adopt practices that reduce their family’s risk of and impact from disease through trainings in the home held by trained health promoters | 1. Train health promoters about treatment and prevention of diahreal and respiratory infections 2. Educative session in the home about treatment and prevention of common childhood diseases 3. Educative session in the home about construction of a tippy tap model handwashing station | June, 2015 | 33 Mothers ages 22 and older, 6 Health Promoters ages 25 and older | 1. 33 mothers will be trained on prevention of respiratory illnesses and diarrheal infections through individual educative sessions held in their homes. 2. 33 mothers will receive improved cookstoves in their homes to reduce the risk of their children developing respiratory and diarrheal infections 3. 30 mothers will adopt at least three new practices to reduce the risk of diarrheal infection in their children. | Evaluation and observation of practices in the home/ volunteer
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The volunteer and health promoters will be visiting each mom at least once a month. During those visits I will be doing close observations to see if mothers have been making behavior changes in their homes. For example we will be participating in meal times every once in a while and observing if the mothers are feeding their children more nutritious meals. In addition an evaluation was done at the beginning of the program with each mom and a follow up evaluation will be completed at the end of the program. The questions in this evaluation closely match up with each indicator. Furthermore, every three months there will a meeting with all the moms in the program and the health promoters. During these meetings we will review some of the topics that we have spoken about in the sessions and play a game to check for learning at the end of the meeting. Based on their performance in the game we will have a better idea of topics and themes which mothers need more time learning about and understanding.
prgmform: last updated, 06/26/2012 (pjh)