## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To paint upwards of 50 portraits of families and men in the targeted region, who are affected by Chronic Kidney Disease non traditional or who have passed away from this illness. To paint a portrait of each deceased member of the participating family and to donate it to the participating family in the two month time frame of this project. To organize a large scale statement / installation of the work and to document it in film and photography and writing by March 15th. To send these images to the press sources by March 19th. To social media the entire process and progress on the community organizer's, La Isla Foundation, and project leader's, Aubrey Roemer, respective accounts. | To integrate Aubrey Roemer into the community of La Isla des la Viudas with the assistance of La Isla Foundation. Aubrey Roemer must paint upwards of 50 individuals, or as many possible affected families both live within the community and from photograph in her studio (all in Nicaragua). To set a specific site and date for installation of the paintings. To install, document, and social media the event on tentatively March 15th. To disperse the individual memorial portraits after the installation is complete. To send out press releases and kits to all participating media outlets. | Beginning the painting by Januray 22nd and commencing the installation by the 15th of March. The following week will be the distribution of portraits and the contacting of the press. Project (on the ground) ends on March 22nd. | Upwards of 50 women, 50 men, and 50 children within the community will be directly impacted. However, this project will potentially affect thousands of families of women, children, and men that have suffered through this epidemic by creating a global awareness of the issue. | The indicators used to determine if this project is a success or not will be knowledge and access. Specifically, knowledge and awareness of the CKDnt epidemic was raised by the project via social media responses and the number of publications reports pertaining to the epidemic via this project. For access it will be how many families have recieved memorial portraits of their male members that died due to CKDnt. | The data collection will be based on preexisting statistics from La Isla Foundation and garned by Aubrey Roemer during the process. Aubrey Roemer will be responsible to World Connect for reporting on whether or not the project was successful and in what way, i.e. 50 women recieved portraits of their deceased husbands and 50 families were painted on former protest banners and installed on March 15th, and 4 major press outlets are covering the project as it pertains to the epidemic.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Monitoring the success of the project will be based on the attainment of concrete goals. For example, if at least 20 families are painted (with an average size of 5 people including deceased members, which averages to 100 portraits) the target goal will have been met. An entire family can be painted in a little over a day, to illustrate a timeframe. A record will be kept of all participating members of the family, the date painted, and when the memorial portrait is delivered. A calender / timeline of all exhibitons, installations, and publications will be journaled. Aubrey Roemer will be responsible for organizing and chronicling all data and sharing it with La Isla and World Connect. An additional survey can be given during the distibution of the portraits, in hopes of accurately documenting the impact of the project.
prgmform: last updated, 06/26/2012 (pjh)