## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To increase access to a productive learning environment for 30 students per school year. | Complete the building of a new classroom. | The month of December. Building should be done by the end of Christmas break (early January) | Each year, one teacher over 30 years of age and 30 students between 12 and 16 years of age will benefit from an improved learning environment. | How many 7eme students have access to a quality classroom | Data will be based on the classroom attendence of 7eme students. PCV Kathleen will be responsible for data collection by being present for school roll calls before and after the building of the classroom.
To increase knowledge of the benefits of education. | Hold a community meeting on the importance of education. | The meeting will be held in January, as soon as possible after the completion of the classroom. | Meeting attendees (around 40 parents between the ages of 25 and 45 will increase their knowledge of the benefits of education. | How many meeting attendees change reported attitudes regarding education | Data will be based on a pre and post meeting survey conducted by PCV Kathleen
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)