## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Educate 1,390 youth within the Department of Velingara in business, waste management, health, and agriculture topics that will improve their practical life skills throughout the summer of 2013
| 1,390 youth will be trained in pertinent business skills: operations, strategic management, accounting, marketing, and inventory | By the end of June 2013 | 42 male and female youth leaders between the ages of 14 and 28 within the Department of Velingara | 1 .Increase knowledge related to operations, strategic management, accounting, marketing, and inventory skills to 42 youth 2. Increase dialogue and communication among 42 youth leaders to determine level of subject comprehension among trainees of youth leaders | A survey of all subject matter will be dispersed to youth before and after subject matter is presented to understand how much knowledge is acquired by youth given by PCV Kelly Blodgett. Monthly assessments of youth will be observed and documented in progress report after each training session by village visits of training sessions conducted by youth in their own community by PCV Kelly Blodgett and organization president. End of summer discussion will take place with youth and organization president to understand success and logistical fluidity of project from the viewpoint of youth and project leaders.
| 1,390 youth will be trained in practical waste management topics: reduce, reuse, recycle, and compost (part 1) | By the end of July 2013 | 42 male and female youth leaders between the ages of 14 and 28 within the Department of Velingara | 1. Increase knowledge related to reduce, reuse, and recycle principles as well as lecturing the importance and starting a compost pile to 42 youth; 2. Increase dialogue and communication among 42 youth leaders to determine level of subject comprehension among trainees of youth leaders | A survey of all subject matter will be dispersed to youth before and after subject matter is presented to understand how much knowledge is acquired by youth given by PCV Kelly Blodgett. Monthly assessments of youth will be observed and documented in progress report after each training session by village visits of training sessions conducted by youth in their own community by PCV Kelly Blodgett and organization president. End of summer discussion will take place with youth and organization president to understand success and logistical fluidity of project from the viewpoint of youth and project leaders.
| 1,390 youth will be trained in proper health: hand washing, nutrition, fitness, and malaria | By the end of August 2013 | 42 male and female youth leaders between the ages of 14 and 28 within the Department of Velingara | 1. Increase knowledge related to hand washing, nutrition, fitness and malaria to 42 youth; 2. Increase dialogue and communication among 42 youth leaders to determine level of subject comprehension among trainees of youth leaders | A survey of all subject matter will be dispersed to youth before and after subject matter is presented to understand how much knowledge is acquired by youth given by PCV Kelly Blodgett. Monthly assessments of youth will be observed and documented in progress report after each training session by village visits of training sessions conducted by youth in their own community by PCV Kelly Blodgett and organization president. End of summer discussion will take place with youth and organization president to understand success and logistical fluidity of project from the viewpoint of youth and project leaders.
| 1,390 youth will be trained in key agriculture practices: gardening, compost (part 2), and food security | By the end of September 2013 | 42 male and female youth leaders between the ages of 14 and 28 within the Department of Velingara | 1. Increase knowledge related to gardening, compost (lecturing on compost as well as seeing the finished product of our started pile during the waste management training session), and food security to 42 youth; 2. Increase dialogue and communication among 42 youth leaders to determine level of subject comprehension among trainees of youth leaders | Monthly assessments of youth will be observed and documented in progress report after each training session by village visits of training sessions conducted by youth in their own community by PCV Kelly Blodgett and organization president
Create 42 youth leaders within the Department of Velingara who will be able to share knowledge on the subjects of business, waste management, health, and agriculture to 1,348 of their peers throughout the summer of 2013
| 42 youth will be well versed in youth leadership and within the department will then be able to train the youth in their allotted areas | By the end of October 2013 | 1,390 male and female youth between the ages of 14 and 28 within the Department of Velingara | 1. Increase in leadership skills among 42 youth who will hold training sessions to the youth in their zone within the department; 2. Increase in knowledge related to business, waste management, health, and agriculture among 42 youth; 3. Increase in accountability in youth to keep records of their training session attendance while noting any questions or comments youth may have and reporting back findings to the organization | A survey containing leadership material will be presented to youth prior to training sessions and again after training sessions at the end of the summer to measure tactics and comprehension of leadership skills. Monthly assessments of youth will be conducted after each training session to observe how much information was retained and also village visits will be made to document in progress report and ensure youth are carrying out training sessions in their village by PCV Kelly Blodgett, organization president, and training session professionals
| 42 youth will be well versed in youth leadership and within the department will then be able to train the youth in their allotted areas | By the end of October 2013 | 1,390 male and female youth between the ages of 14 and 28 within the Department of Velingara | 1. Increase in leadership skills among 42 youth who will hold training sessions to the youth in their zone within the department; 2. Increase in knowledge related to business, waste management, health, and agriculture among 42 youth; 3. Increase in accountability in youth to keep records of their training session attendance while noting any questions or comments youth may have and reporting back findings to the organization | A survey containing leadership material will be presented to youth prior to training sessions and again after training sessions at the end of the summer to measure tactics and comprehension of leadership skills. Monthly assessments of youth will be conducted after each training session to observe how much information was retained and also village visits will be made to document in progress report and ensure youth are carrying out training sessions in their village by PCV Kelly Blodgett, organization president, and training session professionals
Create department solidarity between 1,390 youth by encouraging collaboration and competitiveness within the Department of Velingara throughout the summer of 2013
| 1,390 youth will be encouraged to build relationships amongst each other while creating a standard level of competence to boost the development of the department | Throughout the summer of 2013 | 1,390 male and female youth between the ages of 14 and 28 within the Department of Velingara | 1. Increase collaboration among 1,390 youth during training sessions and activities; 2. Increase in access to peers among 1,390 youth 3. Administer positive reinforcement to 42 youth in our training sessions and again when peers conduct their own training sessions | Daily dialogues of support and encouragement to youth will be practiced to ensure confidence and competence and will be noted in the progress report by PCV Kelly Blodgett and Organization President
| 1,390 youth will be able to build on a sense of competition with other youth in the department while also showing good sportsmanship | Throughout the summer of 2013 | 1,390 male and female youth between the ages of 14 and 28 within the Department of Velingara | 1. Increase in communication among 1,390 youth during entirety of project to ensure good sportsmanship; 2. Increase in knowledge related to sportsmanship among 1,390 youth | Monthly assessments of youth will be observed and documented in progress report after training sessions as well as youth activities by PCV Kelly Blodgett and Organization President
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Surveys will be given out to the 42 youth leaders prior to each training session as well as at the end of each training session to gage the level of knowledge learned from the youth during the training sessions in business, waste management, health, and agriculture. Surveys will be distributed by myself, Kelly Blodgett, and analyzed by myself and the organization president. A survey will be given to youth by myself during the month of May to determine the level of knowledge pertaining to leadership skills. Youth will be taught techniques during the period of the project to ensure successful training sessions. Youth will be observed in their training sessions by myself and organization president to document level of leadership and will be surveyed at the end of summer to determine leadership skills learned. Throughout the project myself and organization leaders will emphasize to youth verbally the importance of collaboration within peers in the department while games and activities within the training sessions and events will also encourage youth collaboration and sportsmanship. Notation in the project progress report journal by the organization president concerning youth collaboration skills and practices in the beginning and end of summer will aid in determining the learned level of collaboration across the youth.
prgmform: last updated, 06/26/2012 (pjh)