## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Expose 50 youth aged 8 to 10 to dynamic, hands-on activities in math, science, culture, creativity, and teamwork to inspire greater interest in education. | Organize and hold an Activity Day in the community of Amapala (with transportation for children from Los Limones) | Within 3 weeks after start of project. | 25 boys and 25 girls between the ages of 8-10 | Increase in knowledge related to math, science, culture, creativity, and teamwork among 50 youth. Increase in signs of more interest in education among 50 youth. Example of signs include attendance rates and better behavior in class. | Data will be collected by local teachers and World Vision volunteers using surveys and interviews with both the students and teachers.
| Organize a fieldtrip to the children's museum Tin Marin in San Salvador. | Within 5 weeks after start of project
Expose 50 youth aged 8 to 10 to an urban setting to develop their understanding of El Salvador. | Organize a fieldtrip to the children's museum Tin Marin in San Salvador. | Within 5 weeks after start of project | 25 boys and 25 girls between the ages of 8-10 | Increase in knowledge related to urban areas in general and a demonstration of a better understanding of the societal diversity within El Salvador among 50 youth. | Data will be collected by local teachers and World Vision volunteers using surveys and interviews with the students.
Expose and train 7 local leaders in dynamic, hands-on activities that they can reproduce using locally available resources. | Organize and hold an Activity Day in the community of Amapala (with transportation for children from Los Limones) | Within 3 weeks after start of project. | 2 local World Vision volunteers and 5 local teachers | Increase in knowledge in how to perform hands-on activities among 7 local leaders. Increase in confidence levels and ability to perform these activities. | Data will be collected by World Vision staff members and Peace Corps volunteers using surveys and interviews.
Help initiate and/or strengthen a working relationship between 7 local leaders, 3 local NGO staff members and the Tin Marin museum. | In organizing both the Activity Day and fieldtrip to Tin Marin, group meetings with all members involved will be conducted to dicuss logistics and divide responsibilities. | Continously throughout project, ending 6 weeks after start of project | 2 local World Vision volunteers, 5 local teachers and 3 World Vision staff members | Increase in access to important contact information relating to youth development. Increase in comfort levels in working with others among 7 local leaders and 3 World Vision office staff members. Decrease in conflict/miscommunications between previous mentioned actors. | Data will be collected by Peace Corps volunteers using surveys.
Help 7 local leaders and 3 local NGO staff members develop and practice logistical and organizational skills. | In organizing both the Activity Day and fieldtrip to Tin Marin, group meetings with all members involved will be conducted to dicuss logistics and divide responsibilities. | Continously throughout project, ending 6 weeks after start of project | 2 local World Vision volunteers, 5 local teachers and 3 World Vision staff members | Increase in knowledge and confidence levels regarding organizing projects and logistical steps involved among 7 local leaders and 3 World Vision office staff members. Decrease in Peace Corps volunteer intervention in project design and implementation. | Data will be collected by Peace Corps volunteers using surveys.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Due to the project’s multiple goals, its success will be measured among several factors, but with each following the guidelines set forth by World Connect for a baseline, midline, and final assessment. Via surveys filled out by students and interviews with teachers and World Vision volunteers, baseline assessments for the youths’ previous exposure to hands-on activities, level of interest in education, general background knowledge, previous exposure to areas outside of their communities, and views of their country will be taken. A baseline of attendance rates has already been taken: 23 out of 33 students enrolled in the fourth and fifth grades in Los Limones and 29 out of 38 of those in Amapala attend school on a regular basis. The World Vision volunteers and local teachers will be surveyed for previous experience and exposure to hands-on activities and their confidence levels in being able to carry them out individually. Finally, World Vision office staff members, World Vision volunteers, and local teachers will all be surveyed to rate their comfort level of working with the others participating and their ability and experience in organizing projects and activities. They will be asked to detail experience with specific tasks, such as preparing a budget or reviewing the material with youth. All of the baseline assessments will be made at the onset on the project. In order to measure a midline, the World Vision volunteers and local teachers’ confidence in being able to perform hands-on activities will be surveyed twice; midway through the Activity Day and at the end of day. Together with the World Vision office members, they will also be assessed for comfort levels working with others and organizing projects/activities. Finally, through surveys and interviews with teachers and World Vision volunteers, a midline for the students’ interest in education will be taken. Informally, the Peace Corps volunteers will be evaluating and providing feedback throughout the project. Using the same methods described above, a final assessment of the youths’ level of interest in education, exposure to areas outside of their communities, their views of their country, their ability to retain what they have learned, and attendance levels will be taken. World Vision volunteers and local teachers will be surveyed for confidence in carrying out activities. Together with the World Vision office members, they will once again be assessed for comfort levels working with others and organizing projects/activities. Specifically, they will be asked about their ability to do certain logistical tasks and tested to see whether they retained important information such as contact information and activity instructions.
prgmform: last updated, 06/26/2012 (pjh)