## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Increase income levels in community through a crop business project in order to purchase health insurance for 100% of families within the next three years.
| Conduct baseline survey of income levels based harvest yeild | 2014-12-01 | 689 | Find baseline income levels per households | Household survey distributed by Project Leader, Jean Baptiste with support of Spark
| Submit project proposal to Spark | 2014-12-01 | 689 | Full project proposal submitted with every field filled out accurately | Community, supported by Project Leader
| Collect monthly contribution of 200 RWF per month to be put towards business | 2014-12-01 | 689 | All communtiy members who regularly attend meetings | Community, supported by Project Leader
| Open bank account | 2014-09-01 | 689 | Bank account opened in nearest town center | Community, supported by Project Leader and executive committee
| Registration of business | 2014-01-01 | 689 | Register business with local government | Community, supported by Project Leader
| Rent house to host the business in | 2014-01-01 | 689 | One house rented to serve as the base for the business | Community, supported by Project Leader and Spark
| Buy start up products for the business | 2015-02-01 | 689 | All products including beans, sorghum, maize, sacks, calculator, and ledger books purchased | Community, supported by Project Leader and Spark
| Pay taxes monthly | 2015-02-01 | 689 | All taxes are paid in full and on time | Community, supported by Project Leader
| 6 month evaluation | 2015-06-01 | 689 | Conduct evaluation of household income | Household survey disributed by Project Leader
| Purchase health insurance for commutniy members who lack it | 2015-06-01 | 689 | For community members who are lacking health insurance, executive and supervising committee will purchase health insurance using the profits made from business so far | Community, supported by Project Leader
| 12 month evaluation | 2015-12-01 | 689 | Conduct evaluation of household income and percentage of households with health insurance. | Household survey disributed by Project Leader
| 18 month evaluation | 2016-06-01 | 689 | Conduct evaluation of household income and percentage of households with health insurance. | Household survey disributed by Project Leader
Increase civic engagement in communtiy | Weekly Spark faciliated metings | 2014-08-01 | 689 | Attendance of men, women, and youth at meetings | Household survey disributed by Project Leader and Monitoring Committee
| Weekly indepdent meetings | 2014-08-01 | 689 | Attendance of men, women, and youth at meetings | Community, supported by Project Leader
Increase female participation in communtiy | Weekly Spark faciliated metings | 2014-08-01 | 352 | Attendance of women at meetings and number of times they contributed to the meeting | Community, supported by Project Leader and Spark
| Weekly indepdent meetings | 2014-08-01 | 352 | Attendance of women at meetings and number of times they contributed to the meeting | Community, supported by Project Leader
| Gender empowerment training | 2014-10-01 | 352 | Attendance of women at meetings and number of times they contributed to the meeting | Spark facilitator
Increase group cohesiveness in communtiy | Weekly Spark faciliated metings | 2014-08-01 | 689 | Qualitative observations about how community interacts with each other and how close together they sit | Qualiative observations recorded in online Spark database by facilitator
| Weekly indepdent meetings | 2014-08-01 | 689 | Qualitative observations about how community interacts with each other and how close together they sit | Qualitative observation recroded by Project Leader and given to Spark facilitator
Build local leadership in community | Elect executive committee | 2014-08-01 | 3 | 3 local leaders democratically elected to manage the social impact project | Community supported by Spark
| Conduct leadership training in community | 2014-10-01 | 689 | Leadership training successfully conducted in communtiy meeting | Spark facilitator
| Elect suprevising committee | 2014-11-01 | 3 | 3 members democratically elected to supervising committee | Community, supported by Project Leader
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Spark monitors each community and project over time, collecting data to evaluate programs. We evaluate our two primary objectives: community capacity built and project impact over time. The process assists us both in tracking the success of individual projects, and in identifying what is and what is not working. Data collection to inform our process is collected by Spark Facilitators and gathered throughout Spark’s MicroGrant process, as well as in follow up sessions with each partner community. Community Visit Report Forms (CVRF) are completed by Spark Facilitators after each weekly meeting with our partner communities and are stored in an online database. The CVRF allows Spark to track basic meeting metrics such as attendance (overall and by gender), participation levels (overall and by gender) community time contribution, leadership involvement, engagement with outside actors (such as the local government or other organizations) for project support, and qualitative data such as challenges or concerns that arose and meeting accomplishments. This data allow us to track change over time, most especially in regards to capacity building. Spark utilizes an Individual Monitoring Questionnaire (IMQ), a survey that gathers information from 30% of the MicroGrant Planning Group (# of people that signed partnership). This questionnaire collects data on communities and MicroGrant funded projects over time to demonstrate project effectiveness and change over time in individual households. IMQs are conducted thrice throughout the MicroGrant process. Baseline IMQs (1) are conducted as soon as a community determines its project.Follow-up IMQs (2) are conducted six months post project implementation. Follow-up IMQs (3) are conducted 12 months post implementation. Follow-up IMQs (4) are conducted 18 months post implementation. Follow-up IMQs (5) are conducted 24 months post implementation. Spark employs a Community Monitoring Plan (CMP) to monitor community-wide change over time. Spark Facilitators complete CMPs seven times throughout the Spark process: at the beginning of our partnership with a community, during proposal finalization, one month post implementation, six months post implementation, twelve months post implementation, 18 months (1.5 years) post implementation and 24 months (2 years) Post implementation respectively. CMPs are Facilitator assessments and evaluate five pillars of the Spark MicroGrant process - group cohesiveness, civic engagement, female participation, and community ownership - based on a numerical score (1 through 5), as well as a collection of questions for community members regarding transparency and accountability, project understanding, challenges that have arisen since implementation, and proactivity in solving problems. The facilitators and project leader take the lead on collecting this data while it is synthesized by Spark's global M&E manager.
prgmform: last updated, 06/26/2012 (pjh)