## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
The Sarteneja Costura y Artensania will form as an effective, organized women's group of 15 members. | 1. Group Formation - By July 1, 2013, 10-15 women are formed as a cooperative. | July/August 2013 | 8 women aged 24+, and 7 women 18-23 | Increase in access for women ages 18+ to join in a local group among 2,500 villagers. 1. Number of women attending the group. 2. Number of participation agreements signed. | Sign-In Sheets, Participation Agreements & PCV, Community Partner
| 2. Attendance - (Ongoing) Within one year, 90% of the women are participating in meetings, trainings, workshops, and expo/market opportunities as a fully-functioning cooperative. | July 2013 - June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in knowledge related to sewing, handicrafts, business skills, and leadership among 15 women. 1. Number of women participating on a regular basis. 2. Number of women completed trainings, and partipated in market/expo. | Sign-In Sheets, PCV
| 3. BOD - By November 1, 2013, the women have selected a Board of Directors. | July 2013 - November 2013 | 8 women aged 24+, and 7 women 18-23 | Increase in leadership roles among 15 women after three months of project start. 1. BOD Roles and Responsibilities presented and group adopts. 2. Elections held, and officers accept roles. | Election Ballots, and Roles and Responsibilities Officer Description Signed, PCV and Community Partner.
| 4. Communication - By September 1, 2013, the women have determined primary means of communication with one another, and a calendar of activities is developed for the project. | July 2013 - September 2013 | 8 women aged 24+, and 7 women 18-23 | Increase in communications within the first month of project start among 15 women. 1. Communications are received and monitored; women are regularly attending meetings, workshops, trainings. 2. Calendar is developed and adhered to. | Text messages, Phone calls, Emails. Calendar of Activities planned, followed, and meetings run accordingly. Group, PCV, and Community Partner
Women are engaged, and actively participating in learning traditional handicraft and sewing techniques for preservation of tradition. | 1. Sewing - The women will share traditional sewing techniques and acquire new skills such as pattern-making. | August 2013-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in knowledge related to sewing among 15 women. 1. Group learns sewing techniques and demonstrate the skills learned. 2. Number who demonstrated knowledge and practical application. | Sewing products are produced. Each time the group meets for a session, progress on products will be checked. Product progress log. PCV, and Community Partner
| 2. Handicrafts - The women will share traditional handicraft techniques and acquire new skills such as crochet. | August 2013-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in knowledge related to handicrafts among 15 women. 1. Group learns handicraft techniques and demonstrate the skills learned. 2. Number who demonstrated knowledge and practical application. | Handicraft products are produced. Each time the group meets for a session, progress on products will be checked. Product progress log. PCV, and Community Partner
| 3. Instruction - By February 1, 2014, the women will be provided with advanced knowledge from an instructor related to sewing and handicrafts. | February 2014-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in access to advanced techniques among 15 women. 1. Women are ready and learn advanced techniques. | New, differentiated products are produced. Product progress log. PCV and Community Partner
| 4. Sewing and Handicraft Products - By January 31, 2014, the women will adopt best practices for utilizing materials in a resourceful and creative manner reducing the impacts of consumerism. | January 2014-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in resourcefulness after six months of project start among 15 women. 1. Women are trained to use what they have. 2. Number of women who show resourcefulness and creativity. | Women have learned to use what they have. Supply Checklist and Inventory Sheet. PCV
Create sustainable and positive economic development for 15 women aged 18+. | 1. Financial - By February 1, 2014, will have a financial plan for individual, group, and market/expo pursuits. | January 2014-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in knowledge related to financial security among 15 women. 1. Number of women involved with the planning. 2. Number of plans completed. | Plans completed. Attendance sheet at workshop, and financial plan documents. Women, PCV and Community Partner
| 2. Market/Expo - By November 15, 2013, the women will be ready and prepared to host the 1st Annual Market/Expo for the group at a community location. | October 2013-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in income from $0 per hour to $10 per hour among 15 women trained in sewing and handicraft techniques. 1. Market/Expo developed, planned and executed. 2. Number of products ready for market. | Market/Expo held. Photos, videos, and/or sales records of the event. Women, PCV, and Community Partner
| 3. Business Skills - By January 1, 2014, 90% of the women will attend basic business skills workshops on marketing, accounting and operations. | August 2013-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in knowledge related to business skills among 15 women. 1. Number of women attending the workshop. 2. Number of women who are demonstrating practical application of knowledge obtained. | Sessions held. Sign-In sheets, Completed marketing tool (label, poster, social media, etc,), completed accounting tool (log, profit loss/statement, balance sheet, pricing), completed operations tool (how to start a project, materials needed). Women, PCV, and Community Partner
| 4. Sustainability - By June 1, 2014, the group will have explored, and identified a funder to help the project continue. | January 2014-June 2014 | 8 women aged 24+, and 7 women 18-23 | Increase in access to funding sources among 15 women. 1. Number of women actively engaged in seeking funding sources. 2. Number of funders identified. | Funder list, and funder(s) selected.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
From the beginning of the project, and prior to the start of, the tools for collecting data will be created, and prepared accordingly. There will be files for each of the tools used, and these tools will be dated to assess at later date the impact the project has made. Data collection tools include sign-in sheets at all meetings, sessions, trainings, workshops which will be complied at the end of the project into an Excel Document to analyze the trend over the course of the project cycle. Another data collection tool, the product log will be used for both sewing and handicraft products, and will serve as an inventory log for tracking purposes. Checklists will be used to account for materials/supplies for the group, and each individual will be responsible for maintaining those as such. The women will be asked to provide this information on a periodic basis, including inventory. From the expo/market, and even for personal sales outside of those required for the project, women will be trained to track their sales on a sales record. On a regular basis, this information will be collected, assessed, and presented at the end of the project. There maybe an opportunity for a survey sometime near the end of the project to garner areas of interest and/or need for project continuation. Needs assessments and meetings have already been conducted prior to the planning of this project to make sure the project is an established need within the community. Everyone involved in the project will responsible for collecting the information, and the intent is that one or more of the women will take over the collection activity, and will learn the techniques throughout the duration of the project. The Peace Corps Volunteer will lead the analyzation of the data, and the community partner will serve in a support role. The intent here is that also one or more of the women will become involved with the data analyzation, and assume the position for project continuation.
prgmform: last updated, 06/26/2012 (pjh)