## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
By July 2013, Women United for a Better Future and the Development Association of Penas Blancas will improve their ability to set personal goals, project planning skills and business skills through the implementation of ProLiteracy and Interweave's "Success" training. | Complete 12 sessions of "Success" training | April 2013 - July 2013 | 13 women from the women's group in Penas Blancas and members of the Development Association | 1. # of participants who receive "Self-sufficiency" certifications 2. # of participants who demonstrate increased knowledge of the three aspects of self-sufficiency: of business practices, how to set personal goals, and understanding of the importance of collaboration at the community level | Indicator 1: Attendance list and completion of requirements to achieve certification, kept track of by PCV and Mayela Mata from women's group. Indicator 2: Pre-evaluation survey testing knowledge of business practices, setting personal goals, and how to develop community projects. During the workshop, small surveys will be given at the end of each session to monitor how well participants are learning information. A final evaluation will be carried out at the end of the workshop similar to the pre-evaluation to measure how much participants have learned. The surveys will be designed by the PCV facilitating the workshop.
By July 2013, Women United for a Better Future and the Development Association of Penas Blancas will improve their ability to set personal goals, project planning skills and business skills through the implementation of ProLiteracy and Interweave's "Success" training. | Each participant will develop a personal action plan to implement what they have learned | July 2013, or when workshop finishes | 20 participants | # of participants who develop a personal action plan with goals related to all three areas of self-sufficiency | Plans evaluated by classmates in small groups to check for thoroughness and to share suggestions. All plans reviewed by PCV.
By July 2013, Women United for a Better Future and the Development Association of Penas Blancas will improve their ability to set personal goals, project planning skills and business skills through the implementation of ProLiteracy and Interweave's "Success" training. | The participants will create a plan of action to carry out a community project identified during the workshop. | July 2013, or when workshop finishes | 20 participants | Final copy of a well developed action plan, complete with goals, objectives, activities, indicators, time frames and persons responsibles | Plan of action put together by group and evaluated by PCV
By the end of 2013, 15 additional small business owners or community members wishing to start a small business will receive the "Success" training from members from Women United for a Better Future and the Development Association who have completed the training. | In July 2013, participants from the "Success" training from May - July will evaluate the training in order to decide if any changes should be made before offering the training to other members of the community of Penas Blancas. | July 2013, or when workshop finishes | 20 participants | 1. # of participants who complete workshop evaluation 2. # of participants who participate in group discussion evaluating workshop and planning workshop to offer to the community | Evaluation survey and discussion questions will be designed by PCV. Discussion will be facilitated by PCV, but the secretaries from both groups will be responsible for taking minutes from the meeting.
By the end of 2013, 15 additional small business owners or community members wishing to start a small business will receive the "Success" training from members from Women United for a Better Future and the Development Association who have completed the training. | In August of 2013, facilitators will be chosen to run a new workshop, and at least 15 small business owners or aspiring business owners will be recruited to participate in the workshop. | 2013-08-01 | 2 facilitators, one from the women's group and one from the development association, and new participants from the community | 1. Work plan created by two facilitators to organize new training 2. # of community members who express interest in receiving the training 3. # of community members who actually enroll in the workshop | The work plan will be made by the two new facilitators and evaluated by the PCV. Attendance will be taken at an informative meeting to explain the purpose of the training, and a list will be made to keep track of community members who decide to enroll. Attendance and enrollment will be kept by new facilitators.
In 2013, participants from the workshop will implement what they have learned in their personal lives, community projects, and business practices. | Every two months after the completion of training, the participants will be asked to complete a survey to monitor and evaluate how they have carried out their personal plans of action, and a meeting will be held for the group to evaluate their progress. | August 2013 - desired end date, chosen by participants | 20 participants from workshop | 1. # of participants who increase participation in community projects 2. # of participants who have monitored their progress in achieving personal goals 3. # of participants who have successfully used a lesson learned about one of the 6 P's of business. Success will be measured by evaluating the managability and/or profitability of a business before and after a change in one of the 6 P's has been implemented. 4. # of participants who regularly attend follow up meetings | Indicators 1 - 3: participants will be asked to fill out survey indicating changes in behavior using lessons learned from training. The survey will be made by PCV together with two project partners from each group. For indicator 4, and attendance list and minutes will be kept at each meeting by the secretary of the women's group.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The project's goal is to increase each participant's self-sufficiency, which has three components: personal/home life, community and business. During the "Success" workshop, the goal is to increase the knowledge each participant has of these three components of self-sufficiency. This increase in knowledge will be measured by comparing a pre-evaluation and post-evaluation survey, as well as through smaller surveys at the end of each sesson. After the workshop, success of the project will be measured by changes in behavior and by successfully offering the training to other members of the community. The new training will be facilitated by one member of the women's group and one member of the Development Association, and its success will be measured by how well it is organized and then number of interested participants from the community. Changes in behavior amongst participants from the women's group and the Development Association will be measured through observation, periodic surveys, and meetings every two months. Observation will be carried out by the PCV, monitoring participation in group meetings and community projects and following up with participants individually. Every two months, a survey developed by the PCV and two project partners will collect data on changes in behavior that relate to self-sufficiency. If a participant is changing business practices, the PCV will help the participant isolate the effect of said change by quantitatively measuring the profitability of the business and qualitatively evaluating efficiency and administration of the business. The two project partners will facilitate discussions evaluating how participants have progressed through their action plans, how lessons learned from the workshop are being implemented, and how to keep improving.
prgmform: last updated, 06/26/2012 (pjh)