## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Give over 150 students at lycee Mame Cheikh Mbaye the opportunity to experience applying and interviewing for gainful employment | Distribute at least 150 intern applications complete with clear guidelines and a sample | by June 1, 2013 | approximately 200 students | Give access to employment opportunities/applications to at least 150 students | Track number of applications printed and distributed- Joseph Napel
| Receive at least 60 quality applications from qualified candidates | by June 30,2013 | approximately 60 students | 60 students will demonstrate knowledge of seeking employment by completing and submitting quality application | Track number of applications received- Joseph Napel
| Interview at least 20 applicants and give constructive feedback | by July 15, 2013 | approximately 20 students | 20 students will have have increased knowledge of interviewing processes by experiencing the internship interview and receiving feedback | Track number of interviews performed with feedback given- Joseph Napel
Increase knowledge of local NGOs' work | Distribute at least 150 "About the NGO" forms attached to the intern applications with descriptions of the NGOs, their work | by June 1, 2013 | approximately 200 students | 150 students will demonstrate knowledge of NGOs work by reading the NGO profiles and writing an essay about why they'd work for a particular NGO in their application | Track number of forms distributed- Joseph Napel
| Take initial survey of interns' knowledge of NGOs before, compare with survey at closing session | August/September | 10 interns | 10 interns will display increased knowledge about their NGO by taking a baseline survey of their knowledge followed by a final survey once the internship is complete | Conduct baseline and final survey- Jennifer Conner and Janet Smith
Increase professional skills of 10 interns | Create list of professional skills, have interns rank their confidence in their skills at beginning of internship, perform survey again at end of internship | August/September | 10 interns | 10 interns will display increased knowledge about professional skills by taking a baseline survey of their knowledge followed by a final survey once the internship is complete | Conduct baseline and final survey- Jennifer Conner and Janet Smith
| Each intern will attend a professional meeting during their five-week internship | August-September | 10 interns, NGO supervisors | All ten interns will have access to a professional meeting experience during their internship, as guaranteed by the partnering NGOs | Follow up with NGOs and interns- Jennifer Conner and Janet Smith
| Each intern will learn to write a resume based on their academic record and professional experience | September | 10 interns | All ten interns will display knowledge of being able to write a professional resume by attending the final workshop then completing and submitting a resume at the end of their internship | Evaluate resumes written and conduct resume workshop- Jennifer Conner and Janet Smith
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Two surveys will be used to measure an increase in the knowledge of NGOs' work in the community and an improvement in the interns' professional skills. For the goal of improving access to the experience of applying and interviewing for a professional position, it will be simply a matter of distributing the applications, reading carefully, and interviewing top candidates. Less measurable, but equally important, at the closing ceremony, we will spend time discussing what the students have learned, what their future goals are, how this experience changed their goals, and how to realize their goals and dreams.
prgmform: last updated, 06/26/2012 (pjh)