## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To develop the knowledge of 40 active community leaders to become legal promoters between the ages of 18 to 40 in the areas of human rights, Dominican law, statelessness, documentation and leadership/facilitation skills. | To hold six, four-hour workshops and one graduation throughout a three month period. Each community will have 4 promotors represented, and be responsible for a theme related home-work assignment before the next workshop. Curriculum includes: leadership, workshop facilitation and planning skills, professionalism, human rights, Dominican law related to documentation, late documentation, general documentation processes, common problems and solutions, network and community archive management, and community diagnostic/development skills. | October 2013 to December 2013. One workshop bi-weekly on Saturday afternoons. | local community leaders involved in the capacitation. Undocumented families. Local youth groups, community organizations or family organizations. | 1. Increase in local community knowledge of the documentation process, Dominican law and the additional curriculum themes. 2. Increase in families documenting their children on the day of birth of the child. | The indicators will be measured through activities conducted at each workshop as well as the results and data collection of each homework activity. The focus group, composed of 3 strong project partners and 2 PCV's, will be responsible for the training/ facilitation of each workshop.
At least 20 of these promotors would be active female community leaders between 18 and 40 years of age. | To ensure that each community has a female leader on their legal promotors team of representatives. | August 2013 to October 2013. | Female community members and the family-community dinamic. Due to women's higher liklihood to stay in the community and have stronger relationships with other females in the community. | 1. Increase in community mother's access to knowledgable female peers. 2. Increase in behavior towards women as professionals in the community. | The monitoring will be completed by one PCV and one project partner from the focus group during homework check-up visits to each community through out the workshop timeline.
To create a local network of at least 20 active, local legal promotors working to educate and support their communities in the documentation proccess, providing each other support, shared learnings, knowledge and accountability. | The course facilitators (a focus group of 3 Dominican project partners and 2 PCV's) will conduct 3 community visits to monitor progress and help the team create ways to continue communication after the workshops have ended. Communication information will be exchanged within the group of promotors, and the course will include a series of teamwork and trust activities to strengthen the relationships between communities. We would like each promoter to also be presented with ID cards to identify them in government offices. | October 2013 to December 2013, ideally into the future and including additional workshop series. | Undocumented families, especially children 0-16. Legal promotors. | 1. Increase in access to Dominican law, resolutions and relevant information, learnings and connections with the local documentation process. 2. Increase in use of local connections and peer help and a general sense of higher community cohesion in government offices related to the documentation process. | 1. The focus group will visit each group of promoters in their community after the graduation of the course to ensure the multiplication of their work. 2. Through out the following year, additional phonecalls, monthly meetings, and sharings will be organized by the focus group.
To document a target goal of at least 80 undocumented boys and girls from the each of the participating local Batey communities during the legal promotor's course timeline. | Homework activities related to workshop themes that include documentation awareness workshops conducted by course participants in each community, participant conducted census to identify 80 undocumented children, and the accompaniment of course participants through the documentation process with these undocumented families. | October 2013 to December 2013. | 80 undocumented children from each participating community between the ages of 0 to 16. Legal promoters. | 1. Increase in the number of children with birth certificates in the communities. 2. Increase of expecting parents or current parents with the knowledge and support available to become documented. | 1. Participants will support the documentation of 80 previously undocumented children (0 to 16 years of age) . 2. During focus group community visits, the visitation and monitoring of community groups and leaders' awareness of the importance of the documentation process.
For each legal promoter to accompany at least one undocumented family from the beginning and end of a documentation case to learn the process and develop relationships with their local government offices. | Each promotor will visit each local government office involved in the documentation process with course facilitators during the course. Towards the end of the course, each promotor will accompany at least one family to the civil office to support them in the process of attaining a birth certificate, double-checking with the family that they are adequately prepared to successfully attain the certificate(s). Promoters will share successes, challenges and learnings during workshops. | October 2013 to December 2013. | Undocumented families, especially children 0-16. Legal promotors. | 1. Increase in community members knowledge of the documentation process. 2. Increase of families willing to obtain their children's birth certificates due to legal promotor's sharing of knowledge or support. | 1. Participants will share their experiences and reflections in the process during workshops. 2. In the number of birth certificates obtained from families that have attended promotors community workshops, interviews.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)