## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Goal 1 - Objective 1.1 - Site Preparation - By May 15th, 2013, all materials will be delivered to site, and the location will be prepared for construction. | Site Preparation and materials procurement | 2013-05-13 | All project membes as wells as all students and faculty at the school. | Determination if the site has been cleared. Proper delivery of all building materials without damange. | The site preparation will be evaluated by all project members, and monitored by the supervising Peace Corps Volunteer. Progress will be measured following any site development activities, and at the end of each day during a small project group meeting, and recorded in a progress report book.
Goal 1 - Objective 1.2 - Construction - By May 31st, 2013, all materials will be procured and the greenhouse construction, as well as drip irrigation system will be installed and tested. | Assembly of materials with help of trained Amiran staff, and inspections of condition of materials. | 2013-05-31 | All project membes as wells as all students and faculty at the school. | Assembly of the materials, and evaluation of the condition of materials after transport. Arrival of the Amiran staff. | The greenhouse construction will be evaluated by all project members, the Peace Corps Volunteer and trained Amiran Staff. Construction progress will be discussed and measured against the set timeline at the end of each day during a small project group meeting and recorded in a progress report book.
Goal 1 - Objective 1.3 - Planting - By June 14th, 2013, all seeds will be planted, treated with fertilizer and agro-chemicals, and monitoring of crop growth will have started. | Seed planting and chemical treatments with fertilizers and pesticides. | 2013-06-14 | All project membes as wells as all students and faculty at the school. | Planting of seeds and application of fertilizers and pesticides. | Planting and crop protection will be monitored by Amiran staff, project members and the Peace Corps Volunteer. Planing and crop monitoring will be assessed each morning and evening during a small project group meeting and recorded in a progress report book.
Goal 1 - Objective 1.4 - Fee Waivers - 20 female students and 5 male students will be provided with school fee reduction waivers. | Fee waivers for students. | 2013-06-01 | Students working with the project. | Students receiving the waivers, and that fee balance has been reduced in the school records | School Staff as well as the students at the school will be provided with forms detailing the fees waivers. Fees waivers will only be given once Objectives 1.1 -1.3 have been achieved.
Goal 2 - Objective 2.1 - Planning - By May 8th, 2013, 10 school staff, and 25 students will have participated and finished the first project planning meeting regarding site development and material procurement. | Meeting on project status to date. | 2013-05-08 | Project members | Analysis of the project report book on met/unmet goals and adherance to the set timeline. | All project members will be present, and meeting minutes will be taken, and progress from the report book will be discussed with all project members. Analysis of the timeline and met and unmet goals will be discussed.
Goal 2 - Objective 2.2 - Planning - By May 31st, 2013, 10 school staff, and 25 students will have participated and finished the second planning meeting regarding greenhouse construction and set up. | Meeting on project status to date. | 2013-05-31 | Project members | Analysis of the project report book on met/unmet goals and adherance to the set timeline. | All project members will be present, and meeting minutes will be taken, and progress from the report book will be discussed with all project members. Analysis of the timeline and met and unmet goals will be discussed.
Goal 2 - Objective 2.3 - Planning - By June 14th, 2013, 10 school staff, and 25 students will have concluded all project meetings following the planting of seeds and application of fertilizers and agro-chemicals. | Meeting on project status to date. | 2013-06-14 | Project members | Analysis of the project report book on met/unmet goals and adherance to the set timeline. | All project members will be present, and meeting minutes will be taken, and progress from the report book will be discussed with all project members. Analysis of the timeline and met and unmet goals will be discussed.
Goal 2 - Objective 2.4 - Fee Waivers - 20 female students and 5 male students will be provided with school fee reduction waivers. | Fee waivers for students. | 2013-06-01 | Students working with the project. | Students receiving the waivers, and that fee balance has been reduced in the school records | School Staff as well as the students at the school will be provided with forms detailing the fees waivers. Fees waivers will only be given once Objectives 2.1 -2.3 have been achieved.
Goal 3 - Objective 3.1 - Workshop - By June 21st, 2013, 15 school staff, 120 students and 50 community members will have been provided with farming techniques and greenhouse technology in the first Nutritional Workshop. | Nutritional Workshops | 2013-06-21 | All project membes as wells as all students and faculty at the school. | Number of students, faculty, and community members trained on new farming techniques and greenhouse operation and construction will be measured. | All project members will be present for a meeting. Information will be collected at the end of each meeting by noting the attendance, through group discussions during the workshops, and through a survey following the conclusion of the workshop.
Goal 3 - Objective 3.2 - Workshop - By June 28st, 2013, 15 school staff, 120 students and 50 community members will have been provided with nutritional and balanced diet information. | Nutritional Workshops | 2013-06-28 | All project membes as wells as all students and faculty at the school. | Number of students, faculty, and community members trained on importance of a balanced diet and nutritional information will be measured. | All project members will be present for a meeting. Information will be collected at the end of each meeting by noting the attendance, through group discussions during the workshops, and through a survey following the conclusion of the workshop.
Goal 3 - Objective 3.3 - Fee Waivers - 20 female students and 5 male students will be provided with school fee reduction waivers. | Fee waivers for students. | 2013-07-01 | Students working with the project. | Students receiving the waivers, and that fee balance has been reduced in the school records | School Staff as well as the students at the school will be provided with forms detailing the fees waivers. Fees waivers will only be given once Objectives 3.1 - 3.2 have been achieved.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)