## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Reach 30 community based organizations and/or self-help groups by 2015 | Host on-site trainings, walk through demos, and supply prited materials | Within 18 months of project start date; 1/25/2015 | 30 Community Based Organizations | Number of organizations receiving educational training | Daily bookkeeping by Community Health Workers, weekly assessments by Phyllis Wanjiko and Volunteer
Provide free trainings to 15 secondary schools by 2015 | School visitation campaigns by Community Health Workers | Within 18 months of project start date; 1/25/2015 | 15 Secondary Schools | Number of secondary schools receiving educational training | Daily bookkeeping by Community Health Workers, weekly assessments by Phyllis Wanjiko and Volunteer
Provide free nutrition garden trainings to 10 HIV/AIDS groups by 2015 | Host on-site trainings, walk through demos, and supply prited materials | Within 18 months of project start date; 1/25/2015 | 10 HIV/AIDS Support Groups | Number of HIV/AIDS groups receiving educational training | Daily bookkeeping by Community Health Workers, weekly assessments by Phyllis Wanjiko and Volunteer
Increase sustainable methods measurable by the Ministry of Agriculture by 15% by 2015 | Crop rotation, water harvest and irrigation, composting, and vermaculture demos and materials | Within 18 months of project start date; 1/25/2015 | Nyandarua Central Farmers | % change in sustainable farming methods | As reported by Ministry of Agriculture and reviewed by Martin Njenga and Volunteer
Produce to sell tomatoes, yellow peppers, and strawberries, to surrounding rural areas at 15% less the local cost by 2015 | 4 harvest/year of tomatoes, yellow peppers, and strawberries | Within 18 months of project start date; 1/25/2015 | Nyandarua Central Households | % cost reduction in imported varieties made local | As reported by Ministry of Agriculture and reviewed by Martin Njenga and Volunteer
Replace 10% of imported produce with locally grown varieties by 2020 | 4 harvest/year of tomatoes, yellow peppers, and strawberries | Within five years of project start date; 1/25/2020 | Nyandarua Central Households | % decrease in imported varieties v. new local varieties | As reported by Ministry of Agriculture and reviewed by Martin Njenga and Volunteer
Increase the number of nutrition gardens in households by 20% by 2015 | Quarterly Community Health Worker outreach events | Within 18 months of project start date; 1/25/2015 | Nyandarua Central Households | % increase in households adding nutritional diversity to their kitchen gardens | As reported by Community Health Workers and reviewed by Martin Njenga and Volunteer
Teach and manufacture composted, vermacultured, and organic liquid fertilizers to 30 farmers by 2015 | Host on-site trainings, walk through demos, and supply prited materials | Within 18 months of project start date; 1/25/2015 | 30 Local Farmers | Number of new farmers using locally made organic fertilizers | As reported by Ministry of Agriculture and reviewed by Martin Njenga and Volunteer
Teach crop rotation and drip irrigation methods to 30 farmers by 2015 | Host on-site trainings, walk through demos, and supply prited materials | Within 18 months of project start date; 1/25/2015 | 30 Local Farmers | Number of farmers receiving crop rotation and drip irrigation training | Daily bookkeeping by Community Health Workers, weekly assessments by Phyllis Wanjiko and Volunteer
Provide and train 25 families with materials for micro-greenhouses by 2015 | Free Trainings and at-cost supplies | Within 18 months of project start date; 1/25/2015 | 25 Local Families | Number of families supplied with greenhouse materials | Daily bookkeeping by Community Health Workers, weekly assessments by Phyllis Wanjiko and Volunteer
Provide and train 5 community based organizations with materials for full-scale income generating greenhouses by 2015 | Free Trainings and at-cost supplies | Within 18 months of project start date; 1/25/2015 | 5 Community Based Organizations | Number of organizations supplied with greenhouse materials | Daily bookkeeping by Community Health Workers, weekly assessments by Phyllis Wanjiko and Volunteer
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)