## Project Plan Guidance - Table 1
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template - Table 1
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Improve NAT test scores for third grade students. Students will be able use two math manipulative tools to demonstrate a math algorithm. | All teachers at IMPACT Learning Center will have a one hour inservice on the use of the math manipulatives purchased for the kit. PC K. Tedford will conduct the inservice. | June 2013 to March 2014 | 90 third grade students | Teachers will use the text provided by DepEd to gage the need for manipulatives. Additional suggestions and demonstrations will be provided by PC K. Tedford in an inservice and as on going support in the implementation year. | Baseline data will be the 2011-2012 NAT test scores for third and sixth grades in math. third grade = 37.21% and sixth grade 37.9%.
Final data will be the 2013-2014 NAT score for third and sixth. These will be provided as soon as they are available.
Improve NAT test scores for sixth grade students. Students will be able use two math manipulative tools to demonstrate a math algorithm. | On going support will be provided by K. Tedford in the implementation year. Model lessons and demonstrations will be provided as needed or requested. |  | 90 sixth grade students | A log will be maintained by Ma’m Hedy to indicate who is checking out manipulatives. The principal, Ma’m Paulina Vibal, will include this indicator for remediation in her SIP plan for the school. | A secondary baseline will be a teacher survey on their knowledge of the math manipulatives purchased. Midline survey will follow after the inservice conducted by PC K. Tedford and the final survey will be administered at the end of the school year. Questions will center around identification of the manipulative and usage as a tool to teach the math algorithms and concepts.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The teachers and students at IMPACT Learning Center do not have any manipulative materials at their disposal. Individual students can bring materials to school but these individuals are a small fraction of the total population. Most teachers have not been inserviced on the possibilities that manipulatives offer. The exception is the first grade staff. Ma’m Hedy will be a co-facilitator in giving the inservice. She is currently using manipulatives such as straws to make bundles of 10 and 100 for her first grade. She is also using counters and domino math. The initial survey will be instructive because it will guide the PC and her counterpart as to the needs of the staff. If on going inservice is indicated after the initial offering, then both PC K. Tedford and Ma’m Hedy are willing to continue a group format or individual help will be provided to teachers. Surveys are a good visual indicator but there will also be verbal encouragement and Ma’m Vibal has agreed to make this an on going discussion at staff meetings.
prgmform: last updated, 06/26/2012 (pjh)