## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
To provide 18 women with the skills necessary to start a business through business education using a real-time start-up businees as a case study. | 1. Teach entrepreneurial finance, marketing, and management through formal courses once a week for 16 weeks. 2. Use salon business formation as a case-study where students apply the material learned to real-life issues. | 1. Within 4 months of project start date. 2. Within 4 months of project start date. | 18 women 24 years or older | Access Indicator: Increase access to business courses and coaching among 18 female aspiring entrepreneurs. Knowledge Indicator: An increase in business knowledge among 18 female students. | Data Collection Method: Exam grade and project grade before, midway, and after course course; survey of student's perception of business course/coaching availability in Brasilia before and after course completion. Person Responsible: Farid Mozafari (PCV Costa Rica)
3 Members of the women's group will successfully launch a salon business in their community that will generate monthly income. | 1. The 3 women will attend salon school to learn hair-styling techniques for male and female customers (once a week for 16 weeks) and receive certificates upon completion. 2. Construction materials will be transported from Upala to Brasilia (cost included in materials cost). 3. Construction of the salon on community contributed land will comence and complete. 4. Obtain salon equipment from beauty supply store they have located in Liberia. 5. Salon will open for business. | 1. Within 4 months of project start date. 2. Within 1 month of project start date. 3. Within 3 months of the project start date. 4. Within 4 months of project start date. 5. By December 31, 2013. | 3 Women aged 30 years or older | Income: Increase in income from $0/week to $20/week among 3 female entrepreneurs. Knowledge: Increase in knowledge of hair styling among 3 female entrepreneurs. Construction: Completion of a structure that will be used as the location for the salon business. | Data Collection Method: Survey with construction contractors to develop accurate construction schedule and measure actual progress on a weekly basis; conduct in-person interviews with salon school instructor and students to determine # of passing students; interview group leader to determine salaries of women. Person Responsible: Farid Mozafari (PCV Costa Rica), Meylin Grillo (Project Leader)
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
Farid Mozafari, the community economic development Peace Corps volunteer, and Meylin Grillo will be responsible for collecting the data. The primary data collection tool for the entrepreneurship courses will be exams and project grades. Exams will cover basic business terminology (4 Ps of Marketing, Income/Balance Sheets, Capital/Asset Ratios, etc...). The project will ask the students to come up with a business idea and formulate a business plan with coaching from PCV, Farid Mozafari. The 1st class (class after business exam) will assign the project, giving ample time for students to think of an idea the community needs using a priority/needs assessment of Brasilia. These projects will be graded by the PCV to determine their viability and practical use and then discussed 1-on-1 with the students. This portion of the class is about sustaining the project goals long after it's completion by giving women viable business plans to work with. An indicator is also to increase access to business education/coaching in Brasilia. A survey measured on a 1-10 scale (10 being very strong availability) will be given to the students both before and after course completion. If the average score improves, it will be evident that we increased it. The materials list for construction has already been compiled and is available on the PCPP application. The contractor gave an original estimate for time of construction to be 5 weeks. However, before the project start date, Farid Mozafari and Meylin Grillo will sit down with the contractor to develop an accurate realistic schedule of what portions of the construction will be completed by what date. This will be the baseline indicator and used to analyze the progress made on a weekly basis. Interviews with the 3 salon students and their teacher will need to be conducted in order to determine their knowledge of hair-styling before, during, and after the course is completed. If the students receive their certificates at the end, that will indicate the success of this part of the goal. The PCV will also interview these people to determine their progress and level of comfortability with the material. The salon course conducts exams. This exam will be used to indicate their progress in numbers. The project is aimed at improving income among the women. The salon business will provide income for 3 of the group's members. This data will be compiled by the group leader, Meylin Grillo and used to indicate whether the business has yet increased their levels of income from $0/week to $20/week.
prgmform: last updated, 06/26/2012 (pjh)