## Project Plan Guidance
Grant Application
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Project Plan | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Design project | Planning/organizing community information | Sept./2013 | 2 men 24+ and 1 woman 24+ | Behavior/Skill | PCV. Review of process of identifying target population/planning the project
Budget project costs | Visting/calling stores | Sept./2013 | 3 men 24+ | Behavior/Skill | PCV. Data collected directly on a line-by-line budget of water tanks, spout materials, transport, etc.
Data collection | Census house-to-house to investigate water demands and tank sizes | Sept./2013 | 11 homes; 30 community members | Knowledge | PCV
Materials transport | Community member solicits help of local public works to cover expense | Oct./2013 | 1 man 24+, 1 woman 24+ | Knowledge | Project leader, Elvio Cabrera
Transport of water tanks | Coordinating transport of tanks to the community | Oct./2013 | 11 families; 30 community members | Access | PCV, project leaders
100% of homes in community having what we deem as 'adequate' water storage capability | Delivery of tanks and installing water spouts. Observing use. | Oct./2013 | 11 families; 30 community members | Access | PCV, project leaders, community organization
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
The majority of the project’s stages have already been monitored and measured to date. The community identified a problem and a project serving as a solution for families lacking their own cistern access. The community then collected information from four different vendors of water tanks to get all of their size options, materials needed for an access spout, and transport costs. We measured this activity as successful in so far that all the necessary model sizes, materials, and transport costs were collected from four sources and we will were capable of analyzing our best options for the project. The next activity was to visit each potential beneficiary’s home (the 11, or approximately 20% of homes in the community without cistern water storage capability). The PCV spoke with people from each home to review their water needs, model options, and their fiscal community to the project. This census yielded a request for 14 water tanks from three sizes. This data collection tool was an informal survey of each of the homes. If funds are received, the next steps would be to formally order the tanks and spout materials. Materials transport will be solicited during this time via a community member and local government. After coordinating a delivery date, two local laborers in the community will be paid to install water spouts to their tanks. This will be funded by the community via a raffle or raffles held during the community organization’s meetings. Each laborer will be paid 500 pesos (standard one day’s work for skilled labor) to then install spouts at the bottoms of the 14 installed tanks. Monitoring and evaluation of these steps will be self-evident in their fruition or failure. A final step will be to see if all beneficiaries are using their water tanks. This data will be collected by the PCV, project leaders, and members of the community organization through observation and informal follow up with the tank’s owners.
prgmform: last updated, 06/26/2012 (pjh)