## Project Plan Guidance
Grant Application |  |  | Goals:
Page 5 - Guidance for Project Design, Monitoring and Evaluation
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan.
Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.”
Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible.
Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available.
Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.”
Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as:
1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was.
2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end.
3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement.
Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected.
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
By the end of 2014 at least 60 students will have attended and completed a basic month long computing course through an extra curricular class at the school. | Students will attend lessons and complete necessary assignments and exams in order to attain basic computing skills. Lessons and the syllabus need to be created and implemented in the class. Computers need to be transported and installed at the school. | 1/13-11/13 | 5 Women above age 24, 80 Women between age 15 and 24, 10 Men above age 24 and 50 men between the age of 15 and 24 | Knowledge- Increase in knowledge related to computers prevention among 60 secondary school students. Access- Increase in access for 145 students to online information. Behavior- An increase in the average mean scores of classes using the computer lab by at least 10% within the first year. | I will be responsible for measuring the differences in knowledge and behavior. Exams will be given throughout the computer class to measure the success of the students. Average exam scores for classes will also be measured at the start of the year and the end to measure the difference in the mean scores.
By the end of 2014 the computer lab will be ready to be used as a community resource center in order to begin generating income for the school as a place of internet and computer use by community members. | The computer lab will need to have designated hours assigned so that it will be open to the community to use while not interrupting school functions. Rates and materials must be planned out for charging for computer use. | 1/13-11/13 | 300 Women above age 24, 400 women between the ages of 15-24, 200 girls below age 15. 300 men above age 24, 500 men between age 15-24, and 200 men below age 15. | Knowledge- Increase in knowledge related to how to use the computer lab effectively as a resource center. Access- Increase access for 1900 community members to use computers. Income- Increase in income from $20/week to $30/week among the school finances. | I will be responsible for collecting data initially for how the computer lab will be used as a resource center. I will be check prices of other cyber cafes to compare the rates that we will charge. Once I leave it will be the responsibility of the school to monitor the funds that come in and how they are used to further finance the computer lab.
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
I will be responsible for monitoring the success of the computer class. Exams will be given at the start, two in the middle, and one at the end of the class in order to check the progress of the students along the way. Teachers who will be teaching the class once I leave will also be tested with the same exams. At the end of each term mean scores for classes using the computer lab for lessons will be recorded with the differences in mean scores calculated and analyzed. For the resource center I will collect data from other cyber cafes in order to calculate the rates that the school will charge for the computer lab. I will be responsible for collecting and analyzing all data.
prgmform: last updated, 06/26/2012 (pjh)