## Project Plan Guidance
|  |  | Goals and Objectives for the Skills Implementation Center |  | Activities and Timeline for the Skills Implementation Center | [11 empty] | Total Expected Beneficiaries for the Skills Implementation Center |  |  |  |  | Indicators, People Responsible, and Data Collection Methods, for the Skills Implementation Center
Grant Application |  |  | Goal 1: | 45 CETPRO students use the Skills Implementation Center to gain real-world technical and theoretical experience. | [13 empty] | Men, 25 and older | Women, 25 and older | Men, 15-24 | Women, 15-24 |  |  | Indicators | People Responsible | Data Collection Methods
Page 5 - Guidance for Project Design, Monitoring and Evaluation |  |  | Objective 1.1 | By November 2013, CETPRO staff (3 members) and the two specialization committees (10 students) will oversee all aspects of operations and finances for the Skills Implementation Center. | Activity | Person(s) Responsible | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | # of direct beneficiaries who will have increased capacity due to this small grant | 2 | 15 | 1 | 31 | ACCESS Goal 1: | 45 CETPRO students use the Skills Implementation Center to gain real-world technical and theoretical experience.
Below we have included information to help you in the process of developing a strong Project Plan with clear goals, activities and indicators for measuring success throughout the life of your project. Please use the information below to complete your detailed Project Plan. |  |  | Objective 1.2 | By March 2014, 45 CETPRO students will gain real-world technical and hands on experience at the Skills Implementation center. | CETPRO staff and the two specialization committees shall meet to decide the construction and general management of the Skills Implementation Center. This includes the hours of operation, rates for given services, rotation of students within the Center, and management of records. | All CETPRO staff, two specialization committees and Peace Corps Volunteer. | [10 empty] | # of indirect beneficiaries who will have increased capacity due to this small grant | 10 | 35 | 5 | 95 | Objective 1.1 | By November 2013, CETPRO staff (3 members) and the two specialization committees (10 students) will oversee all aspects of operations and finances for the Skills Implementation Center. | 1. # of meetings held; 2. # of people present throughout meetings; 3. # of agreed-on decisions to manage the Skills Implementation Center; 4. Official collection of data and records in a financial book; 5. Frequency of data entry into a financial book. | Both secretaries from the two specialization committees, Director of CETPRO Vilma Atanacio and Peace Corps volunteer Anel. | Attendance sheet, a record of the minutes from each meeting, and signed documentation of roles and responsibilities by specific individuals. | bar: 2013-10-01 to 2014-07-01
|  |  | Goal 2: | 45 CETPRO students will demonstrate improved financial literacy skills for future employment or entrepreneurship. | Director Vilma Palma and Peace Corps volunteer Anel Guel will have purchased equipment necessary for the Skills Implementation Center. All equipment shall be purchased from either the country capital of Lima or the regional capital of Huaraz in the department of Ancash. | Director of CETPRO Vilma Atanacio and Peace Corps Volunteer Anel Guel. | [15 empty] | Objective 1.2 | By March 2014, 45 CETPRO students will gain real-world technical and hands on experience at the Skills Implementation center. | 1.# of students who regularly attend the Skills Implementation Center; 2. # of students who can demonstrate gained skills in textiles arts and cosmetology; 3. # of students who can demonstrate improvement within customer service. | Director of CETPRO Vilma Atanacio and Peace Corps volunteer Anel Guel. | Day-by-day records, pre and post tests (demostrations and observations) | bar: 2013-10-01 to 2014-07-01
| Goals: Goals are intended to help you define the success of your project. Think about what you want to accomplish and how to express it in a measureable and attainable fashion. Make sure that your goals are SMART: specific, measurable, attainable, relevant and time-bound and be clear about your target population (numbers, location, characteristics). Here is an example of a SMART goal, “To provide high quality HIV/AIDS prevention education to 5,000 at-risk women in the project area through a network of 200 community health workers during the first 6 months of the project.” |  | Objective 2.1 | By February 2014, CETPRO staff (3 members) will integrate financial literacy into the CETPRO curriculum modeled after the ‘Young People: Your Future, Your Money’ manual, and will focus on the four themes of: Managing Money, Financial Services, Financial Negotiations, and Earning Money. | The Skills Implementation Center shall be officially opened to the public. The Skills Implementation Center shall be under full functionality throughout Peru’s “Summer Vacation” (January-February 2014). | All CETPRO staff and students and Peace Corps Volunteer. | [15 empty] | KNOWLEDGE Goal 2: | 45 CETPRO students will demonstrate improved financial literacy skills for future employment or entrepreneurship. | bar: 2013-10-01 to 2014-07-01
| Activities: This is where you will need to describe everything that needs to happen in order to achieve your project’s goals. Using the example above, an activity to achieve that goal could be to “Host training for at-risk women about HIV/AIDS prevention.” Please be as specific as possible. |  | Objective 2.2 | By July 2014, 45 CETPRO students will demonstrate improved financial literacy skills relating to the four themes of: Managing Money, Financial Services, Financial Negotiations, and Earning Money. | From the inauguration of the Skills Implementation Center in December 15, 2013, the two specialization committees and CETPRO staff shall meet every month to discuss the overall management and present state of the Skills Implementation Center. All students will be welcomed. | All CETPRO staff, two specialization committees and Peace Corps Volunteer. | [15 empty] | Objective 2.1 | By February 2014, CETPRO staff (3 members) will integrate financial literacy into the CETPRO curriculum modeled after the ‘Young People: Your Future, Your Money’ manual, and will focus on the four themes of: Managing Money, Financial Services, Financial Negotiations, and Earning Money. | 1. # of classes taught; 2. # of students present; 3. # of tests given and scores; 4. # of meetings held by CETPRO staff to plan course | Director of CETPRO Vilma Atanacio and Peace Corps volunteer Anel Guel. | Attendance will be taken throughout each class, weekly co-developed lesson plans will be drafted, and all tests and respective scores will be collected and filed. | bar: 2013-10-01 to 2014-07-01
| Time Frame: This is where you will include a deadline for each activity indicating when you aim to have that activity completed by. With the example above, the training for at-risk women could have a time frame of “within six months of project start.” Again, be as specific as possible, including dates if available. |  | Goal 3: | 45 CETPRO students (43 female, 2 male) will demonstrate improved knowledge about the importance of gender development and life skills. | From the inauguration of the Skills Implementation Center in December 15, 2013, all CETPRO students and staff will have quarterly meetings year round (March, June, September, December) to discuss the current and future management of the Center. | All CETPRO staff and students and Peace Corps Volunteer. | [15 empty] | Objective 2.2 | By July 2014, 45 CETPRO students will demonstrate improved financial literacy skills relating to the four themes of: Managing Money, Financial Services, Financial Negotiations, and Earning Money. | 1. # of classes taught; 2. # of students present; 3. # of final exams distributed and class scores. 4. # of students who can demostrate gained knowledge and skills related to financial literacy | Director of CETPRO Vilma Atanacio and Peace Corps volunteer Anel Guel. | Attendance will be taken throughout each class, weekly co-developed lesson plans will be drafted, and final test scores will be collected and filed. | bar: 2013-10-01 to 2014-07-01
| Total Expected Beneficiaries: Here you will describe the specifics of your target population for each activity. We are looking for a description of who and a quantity of how many. With the example above, the training for at-risk women could be expected to reach “200 women 24 and older and 50 girls 23 and younger.” |  | Objective 3.1 | By February 2014, CETPRO staff (3 members) will integrate a gender development and life skills course into the CETPRO curriculum modeled after the ‘Caras del Futuro’ manual and will focus on the themes of: teamwork; self-esteem; communication skills; gender roles and rights; mind, spirit, and body; leadership; and planning for the future. | The two specialization committees and CETPRO staff will draft a report documenting the half-year progress of the Skills Implementation Center. Suggestions for improvement and a new half-year work plan will be drafted. | All CETPRO staff, two specialization committees and Peace Corps Volunteer. | [15 empty] | BEHAVIOR Goal 3: | 45 CETPRO students (43 female, 2 male) will demonstrate improved knowledge about the importance of gender development and life skills. | bar: 2013-10-01 to 2014-07-01
| Indicators: Indicators are intended to help you measure whether or not you are meeting your project’s goals. You will need to select an indicator for each goal. **When selecting your indicators, please be sure to include AT LEAST TWO from the list of World Connect Common Indicators (described in detail further below). This is CRITICAL so that we can summarize the success of the projects that we support. It is key to measure your progress at different points throughout your project, such as: |  | Objective 3.2 | By July 2014, 45 CETPRO students will developed a better understanding of gender development and life skills relating to the themes of: teamwork; self-esteem; communication skills; gender roles and rights; mind, spirit, and body; leadership; and planning for the future. | A monitoring and evaluation system will be developed by CETPRO staff, the two specialization committees, and the Peace Corps volunteer to foresee the management progress of the Skills Implementation Center. | All CETPRO staff, two specialization committees and Peace Corps Volunteer. | [15 empty] | Objective 3.1 | By February 2014, CETPRO staff (3 members) will integrate a gender development and life skills course into the CETPRO curriculum modeled after the ‘Caras del Futuro’ manual and will focus on the themes of: teamwork; self-esteem; communication skills; gender roles and rights; mind, spirit, and body; leadership; and planning for the future. | 1. # of classes taught; 2. # of students present; 3. # of tests given and scores; 4. # of meetings held by CETPRO staff to plan course | Director of CETPRO Vilma Atanacio and Peace Corps volunteer Anel Guel. | Attendance will be taken throughout each class, weekly co-developed lesson plans will be drafted, and all tests and respective scores will be collected and filed. | bar: 2013-10-01 to 2014-07-01
| 1. Baseline: This is your starting point. You will need to collect this information to show where you began. Continuing with our example of HIV/AIDS prevention education, you will need to measure what the group of at-risk women being trained knew prior to your stellar training. You can then use the same instrument (a survey, for example) at the end of your training to show how successful your project was. |  |  |  | Director Vilma Atanacio and Peace Corps Volunteer Anel Guel, using the ‘Young People: Your Future, Your Money’ manual, will teach a financial literacy course that addresses the needs of students and will focus on four themes: Managing Money, Financial Services, Financial Negotiations, and Earning Money. | Director of CETPRO Vilma Atanacio and Peace Corps Volunteer Anel Guel. | [15 empty] | Objective 3.2 | By July 2014, 45 CETPRO students will developed a better understanding of gender development and life skills relating to the themes of: teamwork; self-esteem; communication skills; gender roles and rights; mind, spirit, and body; leadership; and planning for the future. | 1. # of classes taught; 2. # of students present; 3. # of final exams distributed and class scores. 4. # of students who can demostrate gained knowledge and skills related to financial literacy | Director of CETPRO Vilma Atanacio and Peace Corps volunteer Anel Guel. | Attendance will be taken throughout each class, weekly co-developed lesson plans will be drafted, and final test scores will be collected and filed. | bar: 2013-10-01 to 2014-07-01
| 2. Midline: Measuring progress made on completed activities half-way through your project is a great way to ensure that things are on track or to make necessary adjustments. Using our example, you could learn at midline that you are increasing knowledge within your target of at-risk women on some topics but not on others. You can then make adjustments to ensure that your overall goal is achieved by the project’s end. |  |  |  | Director Vilma Palma and Peace Corps volunteer Anel Guel will have planned, prepared for, and outlined the timeline of the course Young People: Your Future, Your Money by Candance Nelson written in 2008. | Director of CETPRO Vilma Atanacio and Peace Corps Volunteer Anel Guel. | bar: 2013-10-01 to 2014-07-01
| 3. Final: It is essential to measure your indicators at the completion of your project. This will allow you to celebrate your success based on data. For example, if at baseline your students scored an average of 60% on your HIV / AIDS knowledge pre-test, but scored a stellar 99% on the post-test you’ve shown considerable achievement. |  |  |  | Students will be given a larger mid-term project regarding how to better the Skills Implementation Center. The Center will be used as an actual business model to supplement the theory of the financial literacy course. | Director of CETPRO Vilma Atanacio and Peace Corps Volunteer Anel Guel. | bar: 2013-10-01 to 2014-07-01
| Data Collection Method & Person Responsible: This is where you should specify who is responsible for measuring the indicator and how it will be done. Using our example, you could measure the changes in knowledge among at-risk women using a survey and it could be the responsibility of the project leader to make sure all the data are collected. |  |  |  | A special workshop will be given to students regarding resume composition, how to increase their competiveness in the job market, and the “next steps” post graduation. | Director of CETPRO Vilma Atanacio and Peace Corps Volunteer Anel Guel. | bar: 2013-10-01 to 2014-07-01
World Connect Common Indicators: In selecting the indicators for your project, you must include AT LEAST TWO indicators from the list below. We have provided a general format that you can use to plug in the specifics related to your project.
KNOWLEDGE
Use a KNOWLEDGE indicator if your goal is to improve education related to HIV/AIDS prevention, family planning methods, nutrition, cultural history, local flaura and fauna, recycling, musical performance, etc.
General Format: Increase in knowledge related to (type of information) among (how many)(describe population)
Example: Increase in knowledge related to HIV/AIDS prevention among 5,000 at-risk women
ACCESS
Use an ACCESS indicator if your goal is to improve access to local nutritious food sources, clean water, sanitation, family planning methods, HIV/AIDS screening, recycling bins, sports equipment, music classes, educational resources, etc.
General Format: Increase in access to (specify what) among (how many) (describe population)
Example: Increase in access to locally produced eggs among 150 families
BEHAVIOR
Use a BEHAVIOR indicator if your goal is to demonstrate a postive change in behavior among the target population such as exclusive breastfeeding, incorporating local nutritious foods into diet, increased school attendance, decreased incidences of delinquency, increase in recycling, etc.
General Format: Increase in (behavior/skill) among (how many) (describe population)
Example: Increase in exclusive breastfeeding immediately after birth among 25 new mothers
INCOME
Use an INCOME indicator if your goal is to increase the amount of funds available to your target population by supporting them to learn a marketable skill, start a small enterprise, etc.
General Format: Increase in income from (what) to (what) among (how many) (describe population
Example: Increase in income from $0/week to $10/week among 20 women trained in sewing techniques
Advance to Project Plan Template --->

## Project Plan Template
Grant Application
Project Plan
Instructions: A strong plan for monitoring and evaluating your project is critical to its success. We cannot emphasize enough how important this step is in developing your project. Complete the template below with as much detail as possible about your goals, all relevant activities, time frame, expected beneficiaries and indicators of success. Please refer to the guidance on the preceding page. This is your opportunity to illustrate that your project is well designed and has a strong plan for implementation and measuring success. Add additional rows and merge cells as needed.
Goals | Activities | Time Frame (Month / Year) | Expected Beneficiaries | Indicators | Data Collection Method & Person Responsible
Provide a narrative for how you plan to monitor and measure your project's success. Please include a detailed explanation of the data collection tools you plan to use (interviews, surveys, etc.) and who will be responsible for collecting and analyzing the data.
prgmform: last updated, 06/26/2012 (pjh)