**PROJECT RESULTS AND STATUS SUMMARY**

|  |  |  |
| --- | --- | --- |
| **Planned work** | **Intended results and changes** |  |
| **Goal** |  | **Activities** | **Achievement Progress** | **Comments** |
| **Target** | **Achieved** |
| To contribute towards Environmental conservation and forest regeneration through Eco-friendly income generations activities of 120 households | Eco-friendly businesses that thrive and support livelihoods of community members. | Community Sensitization Training in Eco-friendly income generation activities | 5 | 3 | 3 community awareness meetings done.  |
| Training in basic Business and Entrepreneurship and Leadership | 3 | 3 | 1 training with women and 2 trainings with youths done |
| Establishment of Self Help groups for Business support | 5 | 2 | These have started being functional. |
| 15 women and 20 youths trained in Mushroom production and Brickets making | 20 youths and 15 women | 20youths trained in Brickets making | 15 women to be trained in brickets making in MayMushroom production houses being constructed. Spawning to begin end April |
| Increase capacity in Business and Entrepreneurship for women and youth and Establish 2 business labs | Increased capacity in B&E will improve the efficiency of the Youth and women in Business and Identification of opportunities.  | Training of 10 mentors and establishment of 2 business labs | 10 mentors and 2 business labs | 10 mentors undergoing training | The Business labs will be established and become operational in May |
| To contribute towards an Increase capacity in Forest regeneration approaches and Management to 5 community environmental clubs | Forest well regenerated and more trees replanted | Training in the Practice of FMNR and CMNR principles | 2 |  | This activity will be conducted in May, 2018 |
| To contribute towards increase in capacity for Advocacy in Environmental protection and management for 5 community  | Improved protection and management of Kholonje Hills | training in advocacy and lobbying for environmental protection | 2 | - | The trainings will be done between May in preparation for June to September when bush fires are rampant |
| Training in environmental ambassadorship roles and responsibilities | 3 | - | The training will be conducted in May and June |
| To train and empower 5 village Savings and Loans Associations in group business, financial management and Leadership | Improved efficiency in the management and organization of the Village savings and loans | training of 5 VSLAs in Business, financial management plus leadership | 3 | 1 |  8 VSLAs established and being engaged. |

NOTE: Under the project, to-date the project has planted 1300 trees in NKholonje Hill.